Water Services Delivery Plan

Wairarapa Tararua Water Services Organisation

South Wairarapa District Council

August 2025

Table of Contents

Overview of this Water Services Delivery Plan	3

Part A: Statement of financial sustainability, delivery model, implementation plan and assurance	4

A1: Statement of financial sustainability	4

A2: Proposed delivery model	5

A3: Implementation plan	11

A4: Consultation and engagement	16

A5: Assurance and adoption of this Water Services Delivery Plan	17

South Wairarapa District Council	19

Part B: Network performance	20

B1: Investment to meet levels of service, regulatory standards and growth needs	20

Part C: Revenue and financing arrangements	41

C1: Revenue and charging arrangements	41

C2: Funding and financing arrangements	45

Part D: Financial sustainability assessment	48

D1: Confirmation of financially sustainable delivery of water services	48

D2: Financial sustainability assessment - revenue sufficiency	51

D3: Financial sustainability assessment - investment sufficiency	53

D4: Financial sustainability assessment - financing sufficiency	56

Part E: Projected financial statements for water services	59

Water Services Delivery Plan: additional information	71

Significant capital projects	71

Risks and assumptions	74

Part F: Wairarapa Tararua WSCCO combined financial summary	75

Appendix 1: Commitment Agreement	87

Appendix 2: Modelling assumptions	88

Appendix 3: MDC 20 August 2025 Council resolution	89

Appendix 4: Capital programme assurance report	90

# Overview of this Water Services Delivery Plan

This Water Services Delivery Plan (WSDP) is an individual WSDP for South Wairarapa District Council (SWDC). It should be read alongside the WSDPs for Masterton, Tararua and Carterton District Councils.

The Councils’ WSDPs are structured in the following way:

- PART A – delivery model and implementation plan (common part) – this section summarises the agreements the four Councils have reached on the WSCCO’s operating model and commercial terms, and sets out an implementation plan for how the Councils will work together to establish the WSCCO and transfer water services from Councils to the new entity

- PART B – network performance (Council-specific part) – this section summarises the scope and service area of the Council’s water services, the water assets and their condition, planned capital investment in the network over the next 10 years, and a statement of regulatory compliance that confirms the Council meets current and anticipated regulatory standards for water services

- PART C – revenue and financing (Council-specific part) – this section summarises current and future charging arrangements for customers, financing arrangements, and future revenue requirements

- PART D – financial sustainability assessment (Council-specific part) – this section summarises how the Council within the WSCCO will meet DIA’s three key financial sustainability measures and confirms the Council within the WSCCO will be financially sustainable by 30 June 2028

- PART E – projected financial statements for the Council (Council-specific part) – this section shows the Council’s financial position within the WSCCO and demonstrates that the Council can meet the relevant financial sustainability requirements

- PART F: Integrated/combined financial projections for the water entity (common part) – this section provides the financial statements for the WSCCO and demonstrates that the WSCCO can meet the relevant financial sustainability requirements

- Additional information (Council-specific part) – this section summarises the Council’s major capital projects and the risks to their delivery

- Appendices 1-3 (common part) – these appendices include the signed Commitment Agreement with key governance and commercial agreements reached between Councils and iwi, and the modelling assumptions underpinning the financial information in the WSDP.

# Part A: Statement of financial sustainability, delivery model, implementation plan and assurance

## A1: Statement of financial sustainability

South Wairarapa, Tararua, Masterton and Carterton District Councils (Partner Councils), together with Rangitāne and Ngāti Kahungunu, have undertaken to establish a Water Services Council Controlled Organisation (WSCCO) on or before 1 July 2027. This includes all necessary transitional arrangements, governance documentation, service level and operational agreements, and operationalising a planning and accountability framework that meets legislative and regulatory requirements

South Wairarapa District Council (SWDC) confirms that this Water Services Delivery Plan (WSDP) ensures the financially sustainable delivery of water services by 30 June 2028. This confirmation is based on financial modelling and assessments included in Part D, E and F of this Plan.  This WSDP demonstrates that by FY28:

Wairarapa Tararua WSCCO

- Water services revenue will meet operational, capital and compliance costs. Per connection revenue requirements in the WSCCO financial statements (Part F) are average requirements across the four Councils; Councils have decided to ring-fence prices for the period of the WSDP so per connection revenue and charges vary between Councils and these are reflected in Part E for each Council.

- Sufficient investment will be delivered to meet levels of service requirements, regulatory requirements, and increased levels of demand. There is sufficient borrowing capacity to deliver on the combined capital programme (under Councils’ current phasing).

- The WSCCO will meet a 10% FFO to debt target by FY32.  It will meet the 9% LGFA covenant by FY31. The WSCCO meets the ICR requirement from year one of operation and maintains this throughout the WSDP period.

South Wairarapa District Council within the WSCCO

- SWDC within the WSCCO is projected to generate sufficient revenue to meet the full cost of water services delivery, including operating expenditure, asset renewals, and debt servicing. This is underpinned by a shift to a WSCCO with a target capital structure generating sufficient revenues over the forecast period. It is acknowledged that this will require price increases that will challenge affordability.

- SWDC average water charges per connection are forecast to increase from around $3,000 in FY25 to around $6,605 in FY34 (in nominal terms), around 4.8% of median household income in the district. These increases are required due to the Council’s starting debt position, capital programme over the WSDP period, and decision to ring-fence prices. This is an acknowledged affordability challenge which will need to be managed, and this plan proposes a review of the capital programme as part of the transition to identify opportunities to manage cost.

- South Wairarapa’s transition to the 10% FFO target has been modelled over four years (i.e., by FY32) to smooth required price increases for the community; LGFA has reviewed the WSCCO’s and SWDC’s financial position and has confirmed they would support the WSCCO and SWDC through this transition period.

- Operating surpluses over the 10-year period are forecast at $13.4m, with an operating deficit in years 1 and 2 of the WSCCO (FY28 and FY29) and increasing surpluses from FY30.

- The WSDP includes $150m in forecast capital investment over the 10-year period, including renewals to maintain existing levels of service and asset reliability, upgrades to achieve compliance with drinking water standards and to improve network resilience, and growth-related projects to service projected increases in demand. This value of this programme has been reduced to $150m on the basis of an independent assurance review of Wellington Water’s costing approach. This review is attached as Appendix 4.

- This WSDP, unless stated otherwise, presents SWDC’s position within the proposed WSCCO. A combine set of financial statements for the WSCCO can be found in Part F.

The financial statements and forecast position of the WSCCO are based on the Partner Councils’ existing investment programmes as set out in their respective Long-Term Plans (LTP) and Annual Plans, with current priorities and phasing. The SWDC 2025/34 LTP is available here SWDC-2025-34-Long-Term-Plan-Final2.pdf (Note the SWDC programme is included in the 2025/34 LTP for the first two years and removed from years 3 onwards given the expected establishment of the WSCCO. The programme has been included in this WSDP, with a cost reduction following an independent review of the programme – Appendix 4). The financial model also makes key assumptions about levels of operational efficiency that the WSCCO will achieve, financing costs, FFO to debt target, and additional overhead costs incurred by the WSCCO (refer Appendix 2).  In general terms, the modelling takes a conservative approach to the assumptions to demonstrate financial sustainability.

The WSCCO will have choices about how it manages the capital programme and, through the development of the Water Services Strategy, Councils expect to see an early assessment of the phasing and priorities of works to manage costs for customers, achieve efficiencies through bundling of work, or to better reflect a regional view of necessary investment. South Wairarapa and Tararua have particular affordability challenges given their starting debt position and large capital programme, and this WSDP includes a planned reassessment of that part of the programme through the transition, with a particular emphasis on non-compliance related or essential renewal work, to effectively manage delivery and costs for the community.

## A2: Proposed delivery model

South Wairarapa, Tararua, Masterton and Carterton District Councils, together with Rangitāne and Ngāti Kahungunu, are proposing to establish a WSCCO under the Local Government (Water Services) Bill to deliver water services to their districts.

This three-waters entity will have approximately 25,000 connections and be responsible for drinking, waste and stormwater services. Responsibilities for water services will transfer from the Partner Councils to the WSCCO on or before 1 July 2027. This will include associated revenue, expenditure, assets and liabilities.

Figure 1 below provide a snapshot of the communities in the Wairarapa-Tararua region and the scope of existing water services which would transfer to the WSCCO. Currently the region’s water services are delivered directly under contract by three of the four Councils (Carterton, Masterton, and Tararua District Councils) and via Wellington Water Limited (the current Wellington regional CCO) for South Wairarapa District Council.

Establishment and transition activities have begun, with ways of working and commercial terms agreed and set out in the appended Commitment Agreement (Appendix 1). The Commitment Agreement confirms Councils’ commitment to work with iwi and implement this WSDP and establish the WSCCO once the WSDP is accepted. Work is expected to accelerate following the acceptance of this WSDP by the Secretary for Local Government.

Figure 1: Wairarapa Tararua region and water services

Why a joint Water Services Organisation?

The proposal to establish a regional WSCCO was taken after careful consideration of other models and engagement with the community and iwi on the benefits of different approaches. The detail of the consultation undertaken is summarised later in this section.

The Partner Councils have similar sized communities, geography and climate and face similar infrastructure challenges and opportunities. Rangitāne and Ngāti Kahungunu are mana whenua iwi across Wairarapa and Tararua, and both iwi have general and specific rights and interests in fresh-water bodies across our region arising from their respective Treaty Settlements. These circumstances making a grouping of these four Councils and two iwi a logical choice when it came to considering the future of water services delivery.

Through their collective consideration of potential delivery models, the four Councils and two iwi have identified the following benefits of the Wairarapa Tararua model:

- more affordable and resilient water services for communities,

- increased access to finance to enable delivery of necessary investment programmes,

- operational efficiency and cost savings resulting from a single entity planning, contracting and delivering works across the region,

- regional employment opportunities from a larger, locally based infrastructure provider, and

- enabling an entity solely focused on water services delivery.

Establishment principles

The following principles or objectives have guided the Councils and iwi in their consideration of the proposed delivery model and will continue to be used to direct the establishment of and transition to the new entity. These principles are included in the appended Commitment Agreement.

- Deliver long-term benefits to the region (recognising these benefits take time to accrue)

  - Efficient operational delivery

  - Affordable water services

  - Adequate investment in infrastructure through time

  - Financially resilient and sustainable

  - Working with iwi

- Manage shorter-term transition impact on individual shareholding communities and Councils

  - Manage any cost/price changes

  - Ensure transparency in transition pathways

  - Maintain service continuity and reliability for customers and minimise staff disruption

  - Manage Councils’ operational and/or financial risk

- Ensure statutory and regulatory compliance

  - Operate within statutory planning and accountability framework

  - Meet DIA and Commerce Commission financial sustainability requirements

  - Meet regional Council and Taumata Arowai environmental standards

- Where possible, provide flexibility in the design for the new entity and Councils to adapt to changing circumstances over time.

- Recognise the independence of the new entity and provide it with the autonomy to make decisions necessary for success

- Keep it simple, with straightforward arrangements easy for the community to understand.

Ownership arrangements

The WSCCO will be structured under the Local Government Act 2002 and the Local Government (Water Services) Act 2025 (WSA25) (once the Local Government (Water Services) Bill is enacted). A summary of the governance and ownership arrangements is provided here and the appended Commitment Agreement. These arrangements will be developed further and are expected to be confirmed in Q4 2025 (refer Implementation Plan).

The WSCCO would be owned by the four Councils according to the following shareholding arrangements based on the connections within each Council district. Table 1 provides an indicative shareholding allocation; this would be updated and confirmed through the transition.  The Shareholders’ Agreement will contain principles for the entry and exit of shareholders, including in the eventuality of future Council amalgamation or expansion of the WSCCO, and other situations which may require adjustments to shareholdings. The basis for rebalancing shareholding over time will be determined through the transition.

Table 1: Indicative shareholding allocation

| Shareholding Council | Indicative shareholding | Estimated day 1 connections |
| --- | --- | --- |
| Masterton District Council | 44% | 10,911 |
| Tararua District Council | 23% | 5,716 |
| South Wairarapa District Council | 20% | 4,935 |
| Carterton District Council | 13% | 3,203 |
| Total | 100% | 24,765 |

Governance and oversight arrangements

Figure 2 summarises the governance and oversight arrangements for the WSCCO. Councils and iwi have chosen to establish a Stakeholders’ Forum as the mechanism by which they coordinate ownership rights and responsibilities and to enable effective partnership with iwi, Rangitāne and Ngāti Kahungunu. Figure 2 summarises the roles and responsibilities of the Stakeholders’ Forum and the terms sheet in Appendix 1 contains further detail.

The Stakeholders’ Forum is expected to have a fixed membership of six members, one from each Shareholding Council and one from each of Rangitāne and Ngāti Kahungunu. Members are appointed to the Forum by an appointment process determined by the appointing party. SWDC anticipates appointment by resolution of the Council.

Figure 2: WSCCO governance and oversight arrangements

The Board of the WSCCO, once operational, would have flexible membership of five to seven members; this flexibility reflects the need to balance meeting skills requirements and ensuring diversity of views for quality decision making, with managing costs of governance, ensuring effective and efficient decision making, and providing the ability to adjust overtime according to the priorities or lifecycle of the Company.

Appointment of Board members is expected to be staggered through the two stages of the programme. During the establishment period, at least two directors are expected to be appointed by March 2026 with remaining Directors appointed ahead of operational transition. It is anticipated that appointment terms of the initial Board members will be varied to ensure future staggered turnover and to enable initial Directors to be appointed who have expertise in standing up/establishing new organisations.

Councils and iwi have determined the following skills are required on the Board and these will be reflected in the Constitution. This reflects the skills that are required on the Board as a whole, not requirements for all individuals to meet.

- Governance and senior leadership experience

- Experience in utilities and infrastructure industries, preferably water

- Commercial and financial expertise, including Director(s) with relevant qualifications to chair the Audit and Risk Committee

- Understanding of the relevant public accountability, legislative and regulatory context

- Asset management experience

- Commitment to partnership and upholding the Treaty of Waitangi, tikanga and te ao Māori

- Knowledge and experience in te ao Māori and te taiao Māori and Treaty of Waitangi principles and implementation, including the Treaty Settlements of Rangitāne and Ngāti Kahungunu

- Understanding and commitment to the four communities the organisation serves

- Commitment to strong stakeholder management with the four Shareholding Councils.

Organisational structure

The organisational structure and operating model for the new organisation will be developed as part of the organisation and people workstream in the transition. Councils have not developed this detail at this point as it needs to be developed and agreed with the WSCCO Board once appointed.

Service delivery, pricing and charging

The WSCCO will provide all drinking water, wastewater and storm water services within the four Councils’ jurisdictions, where these are currently provided by Councils. Currently services are delivered directly by Tararua, Carterton and Masterton District Councils and via Wellington Water Limited (existing multi-Council owned CCO) for South Wairarapa District Council.

All related water assets will be transferred to the WSCCO with limited exceptions, based on their primary purpose. Water race assets will continue to be owned by Councils. Any other details on transfer arrangements for specific assets will be developed through the preparation of the Transfer Agreement.

Part C of this plan sets out the Council’s current pricing structures for water services. Prior to the transfer of water services to the WSCCO, Councils will continue to collect water revenues according to its own pricing structures. These arrangements would be retained by the WSCCO at establishment and the WSCCO will then determine the future tariff structure, as required under the Local Government (Water Services) Bill.

Through transition planning it will be determined whether Councils will continue to collect water charges on behalf of the WSCCO for a period, or whether the WSCCO will charge customers directly from day one. However, the WSCCO will be responsible for determining the amount of revenue to collect and advising on the tariffs to be applied, consistent with the current tariff structure. It is intended that the WSCCO will directly charge and invoice customers in the future with the timing of billing transition to be determined through establishment and transition planning.

Pricing principles

Pricing was a key concern raised by communities through consultation processes. To respond to community feedback, Councils have determined a set of pricing principles to be incorporated into the Constitution to ensure the WSCCO is considering issues of importance to Councils and communities in making its pricing decisions. These principles include:

- Ensure transparency between pricing and investment requirements

- Undertake appropriate engagement with communities in setting or changing pricing

- Manage/smooth the transition impact of any changes to pricing

- Balance affordability for customers with investment and financial sustainability requirements

- Consider the distributional impacts of pricing decisions, and

- Adopt a cost-to-serve approach, with a future review point.

Councils have agreed that the WSCCO will operate a cost-to-serve model for nine years, after which time the matter will be reviewed by the Board and Shareholding Councils. Concern about subsidising across Council jurisdictional boundaries was a particular issue raised in consultation by Masterton and Carterton communities.

The decision to move away from a cost-to-serve approach and adopt harmonised pricing is retained by the Shareholding Councils, with advice to be received from the WSCCO Board, and would be subject to any legislative or regulatory direction. A review of pricing will be undertaken after nine years and will several factors, including:

- That there is sufficient reliable information available about future investment requirements to provide reliable and transparent estimates of costs to ratepayers

- The impact of any proposed changes on each shareholder’s customers (including distributional impacts within and between Council districts)

- Other benefits and costs of the new proposed approach relative to current approach (e.g., impact on operating costs/efficiencies for the entity)

- Whether other compensatory measures could be put in place to manage any significant impact (if any) on subsets of customers.

While prices are non-harmonised, the board of the WSCCO will be responsible for determining the revenue to be collected from each Council district, including advising the Council of the level of charges to be set for each scheme and category of customer, consistent with Councils’ existing tariff structures. Councils will supply information from their rating databases to the WSCCO for this purpose, as provided for within the Local Government (Water Services) Bill.

SWDC notes that there are affordability challenges associated with its water services. Through the transition, the Council will reassess the capital programme and expects the WSCCO, through the development of the Water Services Strategy, to review the investment programme and identify early opportunities for efficiencies and savings.

Meeting ring-fencing requirements

As part of the establishment of the WSCCO, water services revenues and expenses will be separated from other Council financials. Separate financial management systems will be established for the WSCCO, and, if adopted, any shared services arrangements between the WSCCO and Shareholding Councils will be at arm’s length and on commercial terms. The WSCCO will be responsible for preparing the Water Services Strategy, Annual Budgets and Annual Reports.

Financing arrangements

The WSCCO will borrow from the LGFA and be managed within the LGFA’s specified financial covenants. Parts D and E of this WSDP demonstrate that SWDC within the WSCCO can operate within financial sustainability requirements. Part F of this WSDP demonstrates that the WSCCO can operate within financial sustainability requirements.

Financial modelling prepared for this WSDP targets a more conservative 10% FFO-to-debt target, compared to the LGFA’s 9% covenant requirement. Achievement of the 10% target has been phased in over a four-year period post WSCCO establishment, by adjusting revenue requirements to manage affordability for the South Wairarapa community. Masterton, Carterton and Tararua Councils can meet the 10% target by FY30; South Wairarapa can meet the target by FY32. This results in the WSCCO achieving 9% by FY31 and 10% by FY32. This phasing has been tested with the LGFA who have confirmed they would support this approach as part of their commitment to assist WSOs meet their covenants over a transition period.

It is anticipated that the Council will transfer water-related debt to the WSCCO over a transition period as tranches of debt mature and hedging is unwound. Interest costs incurred by the Council on retained water-related debt over this period will be met by the WSCCO. Establishment costs will be borrowed by Councils and transferred to the WSCCO. Final transfer arrangements will be included in any future Transfer Agreement.

While the WSCCO operates a cost-to-serve model, Councils anticipate guaranteeing the WSCCO debt based on the value of debt outstanding for each jurisdiction. If, or when, the Board advises shareholders on an alternative approach to pricing, the Board will also be required to advise shareholders on an appropriate ongoing approach to the guarantee of debt (e.g., based on shareholding).

The Councils have agreed that the WSCCO will not pay dividends to shareholding Councils for at least nine to 12 years; and that any surpluses would be used to either reduce prices for customers across the region and/or to accelerate priority investment across the region. The governing arrangements will leave the possibility of future dividend payments open.

## A3: Implementation plan

Councils have agreed that the WSCCO will be legally established on or before 1 July 2026 and operational on or before 1 July 2027. The accompanying Commitment Agreement (Appendix 1) sets out the governance and management arrangements for the Programme to ensure the entity is established and operational within these timeframes.

The transition will be governed by a Project Steering Group (PSG) and the project led by a Programme Director, reporting to the PSG, supported by a Project Team of Council staff, iwi representatives and external legal and advisory support. Workstream leads will be assigned for each Programme workstream (refer Figure 3).

Following the local body elections, the Stakeholders’ Forum would be established, and this group would work alongside the PSG to provide oversight to the transition going forward. When the WSCCO initial Directors are appointed, the transition will be jointly overseen by the Stakeholders’ Forum and the WSCCO Board, with programme reporting provided to both governance bodies.

Figure 3: Programme governance and management

Programme workstreams

The key workstreams for the programme are expected to include:

- Governing documentation and establishment – this workstream includes the preparation and negotiation of all relevant governing agreements (Constitution, Shareholders’ Agreement, Stakeholders’ Forum Terms of Reference, Statement of Expectations, and Transfer Agreements), the establishment of new governance structures (Stakeholders’ Forum and WSCCO Board), and approach to Treaty Settlement obligations.

- Organisation and people – this workstream includes development of the organisation’s operating model and management structure, recruitment of Chief Executive and Tier 2 leadership roles, transition of Council staff and contractors (other than long-term physical works contracts) to the WSCCO, the development of organisational policies, new regulatory reporting requirements, and establishment of the physical office.

- Finance and commercial – this workstream includes the determination of new insurance arrangements for the entity, confirmation of financing arrangements with LGFA and Council parent guarantee, debt transfer arrangements, financing strategies and establishment of treasury and banking functions

- Digital, systems and customer – this workstream covers the digital strategy, development of billing arrangements, customer contact, finance, compliance and asset management systems for the WSCCO and the transition from existing Council systems to new arrangements, including any transitional or shared services arrangements that may apply for a time limited period.

- Operations and service delivery – this workstream covers the scoping, planning and delivery of the separation of the operational and service requirements from Councils and their transfer to the new entity (except staff transition which is managed separately). It also includes development of transition for existing contractual arrangements for the Councils’ current service provision, which are expected to be novated over to the WSCCO on transition. It will also include integration with Council planning requirements, including district plans, growth and development strategies, and LTPs, and any corresponding changes required in Council policies.

- Mātauranga Māori – this workstream includes the review of Treaty Settlement obligations, Iwi Environmental Management Plans and other iwi rights and interests and incorporation of these, as relevant, across the other workstreams.  It also includes details of how the WSCCO will report to iwi and how treaty obligations will be considered within the asset management plans.

- Risk and compliance – this workstream determines the WSCCO’s enterprise risks and controls and establishes the compliance requirements, including DWSQAR, RMA and health and safety.

- Communications – a communications plan will be developed to support the programme, which will include regular reporting for the four Councils and iwi governing bodies and executive leadership teams, Council staff and contractors, ratepayers and communities, and key regional stakeholders.

Once Directors are appointed, the Programme Director will work with Councils and the WSCCO Board to confirm any Council operational decisions relating to water services (e.g., changes in the capital programme) that will be taken in the transition period that require the agreement of the WSCCO Board, and these decisions will be included as part the transition programme.

Transition milestones

The programme will be delivered in two stages in line with Council commitments on establishment dates:

- Stage 1 (legal establishment) will run from the adoption of the WSDP by the four Councils in August and be complete at the legal incorporation of the WSCCO and the appointment of initial/establishment Directors.  This will be achieved by the end of 2025/26 at the latest; the intention is to deliver earlier.

- Stage 2 (transition) will run from legal establishment through to the end of 2026/27 at the latest; the programme will be developed to achieve milestones at the earliest opportunity.

Figure 4 shows high level timing for the programme and Table 2 sets out the priorities and milestones for establishment and transition stages. These represent an overall view of the required work and milestones; further work on detailed roles and responsibilities will be developed in the transition planning. Any changes to these milestones will be agreed by the PSG prior to agreement/confirmation by the WSCCO Board and/or Stakeholders’ Forum, as appropriate.

Wherever possible, the transition will be expedited to mitigate the impact of two significant change process for South Wairarapa District Council, given the Council’s pending exit from Wellington Water Limited, and the operational transition of Wellington Water to Metro Water (new Wellington WSCCO). Although the pace of the programme will ultimately balance this specific transition driver with overall programme delivery risk and relevant needs of the other Partner Councils.

Metro Water is currently intended to be operational by July 2026 ahead of the Wairarapa Tararua WSCCO in July 2027, creating a need for an interim solution for South Wairarapa for the 2026/27 year. SWDC is currently working with Wellington Water and its shareholders, and other Wairarapa Tararua Councils on options for these interim arrangements. These options include an interim contractual relationship with MetroWater or a new contractual arrangement delivering SWDC services for a defined period. Any new contract would be novated across to the new Wairarapa Tararua WSCCO on transition, in the same way as Partner Councils’ other contractual arrangements.

Figure 4: Programme timing

Table 2: Programme priorities and milestones

| Programme stage | Priorities and milestones | Indicative timeframe |
| --- | --- | --- |
| Legal establishment | - Achieve acceptance of WSDP by Secretary for Internal Affairs and publish WSDP | December 2025 |
|  | - Plan and prepare for operational transition according to priority workstreams above (with transition expected to begin following appointment of Directors). This will include initiation of key work in financial and commercial and systems workstreams to prepare for handover for completion to WSCCO Board. | December 2025 |
|  | - Appoint members to Stakeholders’ Forum following election and induction of new Councils | November/December 2025 |
|  | - Complete Shareholders’ Agreement, Constitution, Stakeholders’ Forum Terms of Reference | September 2025 |
|  | - Recruit two (minimum) initial Directors | March 2026 |
|  | - Complete legal incorporation and required registrations – including Companies Office, Deed of Indemnity for Directors | March 2026 |
| Operational transition | - Prepare Statement of Expectations for discussion with WSCCO Board | June 2026 |
|  | - Transition SWDC operations from Wellington Water Limited to new transitional arrangements | June 2026 |
|  | - Complete governing documentation (i.e., Transfer Agreements) and negotiate agreement with WSCCO Board. Complete adoption of Transfer Agreement by each of the four Councils. | September 2026 |
|  | - Undertake staff change process to confirm roles and staff that will transition to the new entity. Timing for movement/transfer of staff to be confirmed ahead of operational transition. | December 2026 |
|  | - Development of future systems requirements, including temporary billing arrangements to be administered by Councils (if confirmed approach) | December 2026 |
|  | - Develop insurance, treasury and financing arrangements, with WSCCO Board to finalise | December 2026 |
|  | - WSCCO Board to develop WSO operating model and undertake CEO and Tier 2 role recruitment | December 2026 |
|  | - WSCCO Board to prepare Water Services Strategy to give effect to Statement of Expectations | December 2026 |
|  | - WSCCO Board to set up the new organisation, including office location, corporate policies, bank accounts, brand, website etc. | June 2027 |
|  | - Transfer assets, contracts, responsibilities, remaining staff following Council and Board confirmation of readiness for go live. | June 2027 |

## A4: Consultation and engagement

The Wairarapa Tararua Councils have explored the options for future water services delivery over two key phases, both in partnership with iwi, Rangitāne and Ngāti Kahungunu, and in consultation with communities. An Advisory Oversight Group comprising elected member representatives from each Council and iwi representatives oversaw this process.

In 2024 (phase 1) Wairarapa Tararua Councils initiated work on a potential Wairarapa Tararua delivery option to enable the three Wairarapa Councils to consider it against the Wellington region 10 Council option they were also exploring, and Tararua District Council to consider it against a Manawatu Whanganui Councils option. Through this project Council staff and iwi representatives jointly undertook a Multi Criteria Analysis to determine the outcomes they were seeking from a new delivery model. Councils then assessed the Wellington region and Manawatu/Whanganui region options against the Wairarapa Tararua option, and standalone/status quo options for each Council. The conclusion of this work was that the Wairarapa Tararua Councils decided to consult with their communities on a Wairarapa Tararua arrangement alongside the status quo option for each Council. Information on that process is available here Local Water Done Well - SWDC.

In 2025 (phase 2), the four Councils carried out community consultation on two options – the Wairarapa Tararua Water Services Organisation and the status quo delivery model (or form of status quo delivery). This consultation occurred over the following dates and consultation documents are available in Table 3.

- MDC – 21 March to 22 April 2025

- TDC – 14 March to 22 April 2025

- CDC – 14 March to 22 April 2025

- SWDC – 7 March to 6 April 2025

Table 3: Council consultation documents and findings

| Masterton | LWDW Consultation Document Agenda of Ordinary Council Meeting - Wednesday, 21 May 2025 |
| --- | --- |
| South Wairarapa | 162dd310c98c6daf6013e02d621fc603_LWDW Consultation_final_digital.pdf https://sthwaidc-my.sharepoint.com/:b:/g/personal/comsec3_swdc_govt_nz/ERshbc5N7k5KnrUgcOA5SeYB4zUC5w7o-_kIWYv_LLV15Q?e=I3uZE3 |
| Carterton | Carterton District Council – Local Water Done Well Consultation (14 March 2025) https://carterton.infocouncil.biz/Open/2025/05/CO_20250514_MIN_3416.PDF |
| Tararua | LWDW-Consultation-One-Pager-14-March-2025.pdf Agenda of Extraordinary Council meeting - Wednesday, 11 June 2025 |

Community feedback from all four Councils’ consultations show support for a regional water services organisation – 88% SWDC submitters, 65% Tararua submitters, 70% Carterton submitters and 60% Masterton submitters supported the Wairarapa Tararua regional model.

Key themes from the community feedback included the importance of local delivery and accountability, pricing structures and affordability for communities, reliable and quality water services, trust in the new delivery model, and recognising past investment in services and infrastructure in the region’s communities.  This feedback has informed the Councils’ development of the WSDP and the operating model for the new organisation.

## A5: Assurance and adoption of this Water Services Delivery Plan

On 8 May (SWDC), 6 June (TDC), 9 July (MDC) and 9 July (CDC), Partner Councils agreed to progress a joint WSCCO. This SWDC WSDP has been prepared on this basis.

The development of this WSDP has been overseen by the Wairarapa Tararua Councils’ Chief Executives and prepared according to each Council’s internal assurance processes. The starting point for the plans is the latest 2025/34 LTP for South Wairarapa District Council, with appropriate adjustments to reflect a move to a WSCCO.  The operating model and implementation plan within Part A is common to all four Councils’ plans and sets out how the four Councils and iwi will work together to establish the WSCCO.

Parts B to E of the WSDP, represent the financial position of water services for the Council, on the assumption that it is part of a WSCCO. A consolidated set of financial statements for the Wairarapa Tararua WSCCO can be found in Part F. Individual Council and combined WSCCO financial information throughout this plan have been prepared using a common financial model and agreed set of assumptions.

The following external reviews and assurance have been undertaken:

- Financial modelling and assessment of financial sustainability has been undertaken by independent advisors

- Modelling assumptions were developed in consultation with independent advisors, reviewed by Council CFOs and Infrastructure General Managers, and signed off Chief Executives. These assumptions are included as Appendix 2 of this plan.

- A generally conservative approach has been taken to setting assumptions and targets (e.g., in relation to the target capital structure, the costs of finance and assumed efficiencies) to demonstrate the viability of the WSCCO and scope for the WSCCO to make choices once the entity is operational

- Additional modelling scenarios have been tested internally for key issues to provide Council, community and regulatory confidence in the entity (e.g., price paths for South Wairarapa, and testing the impact of Masterton priority investments occurring beyond the WSDP period)

- Preliminary conversations have been had with LGFA on the need for targeted transition support to achieve LFGA covenants and enable a smoother price path for South Wairarapa District Council.

In addition to the external assurance provided to all Councils, SWDC sought an independent assurance review of its capital programme costs, which resulted in the costs of the programme being reduced and these numbers are the basis of the programme in this plan. This review is provided in Appendix 4.

Council resolutions to adopt the WSDP

Council resolutions to adopt this WSDP were achieved on the dates set out in the Table 4.

Table 4: Council WSDP adoption resolutions

| Council | Date | Resolution |
| --- | --- | --- |
| Masterton District Council | 20 August 2025 | Not yet available online – refer Appendix 3 |
| South Wairarapa District Council | 20 August 2025 | Council 20 August 2025 - SWDC |
| Carterton District Council | 20 August 2025 | Minutes (PDF) |
| Tararua District Council | 20 August 2025 | Minutes of Extraordinary Council meeting - Wednesday, 20 August 2025 |

South Wairarapa District Council Chief Executive Certification

I certify that:

- This Water Services Delivery Plan complies with the Local Government (Water Services Preliminary Arrangements) Act 2024; and

- The information contained in this plan is true and accurate.

________________________________________

Janice Smith

Chief Executive

Date: 28 August 2025

# South Wairarapa District Council

# Part B: Network performance

## B1: Investment to meet levels of service, regulatory standards and growth needs

Serviced population

The current population of South Wairarapa is just over 11,800 (2023 Census data). Properties receiving all three waters services (water supply, wastewater and stormwater) total 3,681. Properties with water connections total 4,402, wastewater connections 4,109 and 4,000 properties are serviced by the urban stormwater network.

The current population that does not receive water services are generally located outside the urban areas of Martinborough, Featherston, Greytown, and Pirinoa.  These rural residents typically manage their own water supply and wastewater systems privately. Water is commonly sourced from rainwater collection systems, stored in tanks, or drawn from bores or streams, depending on location and availability. Wastewater is treated on-site using septic tanks or other private treatment systems, which are maintained by property owners. Stormwater infrastructure is primarily concentrated in urban areas. In rural settings, stormwater is managed through natural drainage features such as roadside ditches and culverts.

The South Wairarapa District encompasses an area of 248,455 hectares; it is a sparsely populated district and one of the smaller local authorities. Population growth is predicted to increase slightly over the period of the 2025/34 LTP, from internal migration. The projections indicate that the district’s resident population will grow from just over 11,800 in 2023 to 13,011 in 2032 and 14,811 by 2052. This represents an average growth of 1.1% over the life of the LTP and 1.3% from 2023 to 2052.

SWDC Table 1: Serviced properties

| Projected serviced properties | FY2024/25 | FY2025/26 | FY2026/27 | FY2027/28 | FY2028/29 | FY2029/30 | FY2030/31 | FY2031/32 | FY2032/33 | FY2033/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Serviced by Water Supply | 4,083 | 4,128 | 4,169 | 4,211 | 4,253 | 4,296 | 4,338 | 4,382 | 4,426 | 4,470 |
| Serviced by Wastewater | 4,378 | 4,426 | 4,470 | 4,515 | 4,560 | 4,606 | 4,652 | 4,698 | 4,745 | 4,793 |
| Serviced by Stormwater | 3,984 | 4,028 | 4,068 | 4,109 | 4,150 | 4,191 | 4,233 | 4,276 | 4,318 | 4,362 |
| Total properties with one or more waters | 4,696 | 4,719 | 4,766 | 4,814 | 4,862 | 4,911 | 4,960 | 5,010 | 5,060 | 5,111 |
| Total residential properties with one or more waters | 4,179 | 4,200 | 4,242 | 4,284 | 4,327 | 4,371 | 4,414 | 4,459 | 4,503 | 4,549 |
| Total commercial properties with one or more waters | 517 | 519 | 524 | 530 | 535 | 540 | 546 | 551 | 557 | 562 |

Note:  SWDC does not currently split water connections between residential and non-residential, as the Revenue & Financing Policy does not differentiate between these categories. We have used an assumption of 89% residential and 11% non-residential based on the commercial & residential split of land use in the urban areas of the district.

Serviced areas

South Wairarapa has four serviced areas of Martinborough, Greytown, Featherston and Pirinoa. The total cost for water services is not split into regions, rather a total cost allocated across all towns and divided by the total number of connections gives us a rate per SUIP (Separately Used or Inhabited Part). For properties that have the potential to connect to services the charge is 50% of the rate; in 2023/24 there were 198 serviceable connections across the public water supply systems.

Water services is a significant activity with several key performance indicators over the life of the 2025/2034 Long-term Plan. In 2019, Council agreed to become a shareholder of Wellington Water Ltd (WWL). This means that WWL currently manages Council’s three waters assets, but Council retains ownership and responsibility for the assets.

Water supply – the water supply activity goals are to: provide reliable and sustainable reticulated water supplies to the townships of Greytown, Featherston, Martinborough and Pirinoa, to provide stock water supply networks, and encourage conservation of this valuable resource.

SWDC Table 2: Water supply assets (note information on connections by water source is not available)

| Water Sources | Urban | Rural | Treatment | Pump Stations | Reservoirs | Network |
| --- | --- | --- | --- | --- | --- | --- |
| Featherston | Boar Bush Gully Catchment – operated as an emergency supply only Taits Creek Intake Weir – operated as an emergency supply only Waiohine River | Tauwharenikau (Longwood Water Race) | UV (4-log protozoa, bacteriological) + Chlorine gas | 4 Bore Pumps | 8ML treated water reservoir 0.4ML reservoir | Gravity fed from reservoir |
| Martinborough | Ruamāhanga Wells Huangarua – operated as an emergency supply only Pirinoa bore |  | UV (4-log protozoa, bacteriological) + Chlorine gas + Greensand filtration | 3 Bore Pumps | 4 x 0.4ML reservoirs | Gravity fed from reservoir |
| Greytown | Waiohine River Memorial Park | Waiohine River (Moroa Water Race) | UV (4-log protozoa, bacteriological) + Chlorine gas | 1 Bore Pump | None | Directly fed from bore pump |

Statement of Service Performance – Water Supply

Performance indicators will transfer to the WSCCO following transition and will be reported by the WSCCO from the 2027/28 year.

SWDC Table 3: Performance indicators – water supply

| Service Level | Key Performance Indicators | Performance Targets (for the financial year) |  |  |  |  |  |  | How it will be measured |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline | 2023/24 (actual) | 2024/25 (target) | 2025/26 | 2026/27 | 2027/28 | 2028-34 |  |
| The water provided is safe to drink | The extent to which the local authority’s drinking water supply complies with the following parts of the drinking water quality assurance rules: (a) 4.4 T1 Treatment Rules; (b) 4.5 D1.1 Distribution System Rule: (c) 4.7.1 T2 Treatment Monitoring Rules; (d) 4.7.2 T2 Filtration Rules. (e) 47.3 T2 UV Rules; (f) 4.7.4 T2 Chlorine Rules; (g) 4.8 D2.1 Distribution System Rule; (h) 4.10.1 T3 Bacterial Rules; (i) 4.10.2 T3 Protozoal Rules; and (j) 4.11.5 D3.29 Microbiological Monitoring Rule. | Not fully compliant | Not fully compliant | Fully Compliant | Fully Compliant | Fully Compliant | Fully Compliant | Fully Compliant | National Water Information Database |

| Service Level | Key Performance Indicators | Performance Targets (for the financial year) |  |  |  |  |  |  |  | How it will be measured |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline | 2023/24 (actual) | 2024/25 (target) | 2025/26 | 2026/27 | 2027/28 | 2028-34 |  |  |
| Maintenance of the reticulation network | Percentage of real water loss from the Council's networked reticulation system (calculated using minimum night flow) | 42% | 42% | 40% | 40% | 39% | 38% | Maintain or improve on 38% | The information is recorded by Wellington Water Limited. |  |
| Customer satisfaction | Number of complaints received about drinking water clarity, taste, odour, pressure or flow, continuity of supply and local authority response on these issues | 18.4 | 18.4 | Less than 20 per 1000 connections | Less than 20 per 1000 connections | Less than 20 per 1000 connections | Less than 20 per 1000 connections | Less than 20 per 1000 connections | The information is recorded by Wellington Water Limited. |  |
| Potable water demand | Average consumption of drinking water per day per resident within the district | 583 litres | 583 litres | Less than 575 litres | Less than 575 litres | Less than 575 litres | Less than 575 litres | Less than 575 litres | The information is recorded by Wellington Water Limited. |  |

| Service Level | Key Performance Indicators | Performance Targets (for the financial year) |  |  |  |  |  |  | How it will be measured |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline | 2023/24 (actual) | 2024/25 (target) | 2025/26 | 2026/27 | 2027/28 | 2028-34 |  |
| Fault response times where the Council attends a call- out in response to a fault or unplanned interruption to the network reticulation system | Median response time to call-outs to a fault or unplanned interruption to the network |  |  |  |  |  |  |  |  |
|  | a) Attendance at urgent call outs | 58mins | 58mins | Median response time of 60 minutes or less | Median response time of 60 minutes or less | Median response time of 60 minutes or less | Median response time of 60 minutes or less | Median response time of 60 minutes or less | The information is recorded by Wellington Water Limited |
|  | b) Resolution of urgent call outs | 3.4hrs | 3.4hrs | Median response time of 8 hours or less | Median response time of 8 hours or less | Median response time of 8 hours or less | Median response time of 8 hours or less | Median response time of 8 hours or less | The information is recorded by Wellington Water Limited |
|  | c) Attendance at non- | 3days | 3 days | Median response time of 2 working days or less | Median response time of 2 working days or less | Median response time of 2 working days or less | Median response time of 2 working days or less | Median response time of 2 working days or less | The information is recorded by Wellington Water Limited |
|  | d) Resolution of non- urgent call outs | 3 days | 3 days | Median response time of 5 working days or less | Median response time of 5 working days or less | Median response time of 5 working days or less | Median response time of 5 working days or less | Median response time of 5 working days or less | The information is recorded by Wellington Water Limited |

Wastewater

The wastewater activity goal is to collect, treat and dispose of wastewater from the urban areas of Featherston, Greytown, Martinborough and Lake Ferry –to provide public health protection with minimal effects on the environment.  The wastewater schemes provided for properties in the district (excluding those premises with their own septic tanks) are the urban schemes of Featherston, Greytown, and Martinborough. Lake Ferry is a rural scheme servicing the Lake Ferry settlement. These systems include pipes, pumps, ponds and plant facilities to collect and discharge the wastewater. In South Wairarapa district, there are four wastewater systems, to which 4,870 pans are serviced and 193 properties that are serviceable (able to connect).

Trade waste management is undertaken in-house by Council as required and is not identified as a separate activity within Council services or with any registered costs or income. With trade waste being incorporated with wastewater management under new legislation, it is expected that the new Water Services Organisation would consider trade waste service delivery in terms of new regulatory requirements.

SWDC Table 4: Wastewater system

| Featherston - Urban | Greytown - Urban |
| --- | --- |
| Gravity system (95%) minor pumping 5% Primary & Secondary oxidation ponds with a total surface area of 38,000 – clay sealing layer, polyethylene sealed sides and wavebands. Ultra-violet pond effluent disinfection which is discharged via an open channel to Donald’s Creek. The Featherston WWTP is subject to a new 10-year consent application (lodged 2024), which anticipates use of Council owned land for the trial of disposal of treated effluent. Council’s goal is to discharge 100% of wastewater to land by 2039 and a process is under way to seek resource consents for the discharge of Featherston wastewater. | Gravity system (95%) minor pumping 5% 90% of Greytown urban area is connected to the wastewater system, the balance is on septic tanks. Wastewater gravity flows from individual connections through mains to primary and secondary ponds. Pond 1 has an area of 18,500m2 and Pond 2 15,000m2. Both ponds are clay lined and have concrete wavebands. An internal boulder wall filter was constructed in 2000 for Pond 2, as a resource consent requirement to improve effluent quality. Effluent discharges into the Papawai Stream, which flows into the Ruamāhanga River, some 1,500m downstream of the effluent discharge point. Actions: Council has purchased 116ha of farmland adjacent to the current Papawai site as part of the consent process to irrigate to land. UV disinfection was commissioned in 2020 and irrigation to 30ha of this land to eliminate discharges to water during low flow conditions has been commissioned. The Council plan to discharge 100% of wastewater to land by 2041. Greytown wastewater treatment plant capacity was designed for 2,220 connections, the 2024 estimate of current connections stands at 2,780. WWL have advised that no further connections can be made, which impacts growth. |
| Martinborough - Urban | Lake Ferry Settlement |
| Martinborough operates entirely as a gravity system. Wastewater flows from individual connections through the mains to a single oxidation pond. The pond has an area of 16,300m2 and incorporates a clay sealing layer and waveband. Mechanical aerators were installed in 1998, and four maturation ponds were constructed in 2006 to improve effluent quality. There is an UV disinfection plant after the maturation ponds. Treated effluent is discharged via an outlet structure into the Ruamāhanga River, except in low flow conditions when the treated effluent is irrigated to 6ha of land adjacent to the plant. Council’s goal is to discharge 100% of wastewater to land by 2041. In August 2022, an abatement notice was received for the plant requiring Council to place a freeze on new connections. Desludging (reactivation) and capacity modelling is under way. This has since been removed. | This small community system services properties at the Lake Ferry settlement and was commissioned in 2007. Serviced properties retain on-site septic tank systems and the effluent from the septic tanks is either pumped or gravitated, depending on location, to local pump stations and then to a centralised treatment lant and disposal field east of the settlement. |

Statement of Service Performance – Wastewater

Performance indicators will transfer to the WSCCO following transition and will be reported by the WSCCO from the 2027/28 year.

SWDC Table 5: Performance indicators – wastewater

| Service Level | Key Performance Indicators | Performance Targets (for the financial year) |  |  |  |  |  |  | How it will be measured |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline | 2023/24 (actual) | 2024/25 (target) | 2025/26 | 2026/27 | 2027/28 | 2028-34 |  |
| Council provides wastewater services that effectively collect and dispose of wastewater | Number of dry weather sewerage overflows from the Council’s system. | 1.1 | 1.1 | Less than 10 per 1000 connections | Less than 10 per 1000 connections | Less than 10 per 1000 connections | Less than 10 per 1000 connections | Less than 10 per 1000 connections | The information is recorded by Wellington Water Limited. It is reported by council as a Breach of Consent. |
|  | Median response time to sewerage overflow resulting from a blockage or other fault to the Council's sewerage system |  |  |  |  |  |  |  |  |
|  | Attendance time (from time of notification to the time service personnel arrive onsite). | 65 mins | 65 mins | Median response time of 60 minutes or less | Median response time of 60 minutes or less | Median response time of 60 minutes or less | Median response time of 60 minutes or less | Median response time of 60 minutes or less | The information is recorded by Wellington Water Limited. |
|  | Resolution time (from time of notification to resolution of fault). | 3.6 hours | 3.6 hours | Median response time of 4 hours or less | Median response time of 4 hours or less | Median response time of 4 hours or less | Median response time of 4 hours or less | Median response time of 4 hours or less | The information is recorded by Wellington Water Limited. |

| Service Level | Key Performance Indicators | Performance Targets (for the financial year) |  |  |  |  |  |  | How it will be measured |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline | 2023/24 (actual) | 2024/25 (target) | 2025/26 | 2026/27 | 2027/28 | 2028-34 |  |
| Wastewater disposal does not create any smells, or health issues and causes minimal impact on the environment | Compliance with the Council's resource consents for discharge from its sewerage system measured by the number of: abatement notices, infringement notices, enforcement orders or convictions received by the Council in relation to those resource consents | 3 | 3 | 0 notices, orders or convictions | 0 notices, orders or convictions | 0 notices, orders or convictions | 0 notices, orders or convictions | 0 notices, orders or convictions | The information is recorded by Wellington Water Limited. It is reported by council as a Breach of Consent. |
|  | Number of complaints received about any of the following: sewerage odour, sewerage system faults, sewerage system blockages and the Council’s response to issues with its sewerage system. | 21 | 21 | less than 30 per 1000 connections | less than 30 per 1000 connections | less than 30 per 1000 connections | less than 30 per 1000 connections | less than 30 per 1000 connections | The information is recorded by Wellington Water Limited |

Stormwater

The stormwater activity goal is to provide and maintain waterways to collect and dispose of excess surface water to protect amenities, reduce flooding, avoid erosion and establish a safe environment. The overall level of stormwater protection is provided by a combination of a primary and a secondary stormwater system. The primary stormwater system consists of reticulation pipes, culverts, open drains and access chambers. It is designed to collect stormwater resulting from moderate rainfall and discharge it into watercourses.

The primary stormwater system is intended to minimise what is often termed as nuisance flooding. The secondary system generally comprises overland flow-paths designed to convey excess floodwater with a minimum of damage when the primary system is unable to cope; roads often serve as secondary flow-paths. Secondary flow-paths are generally provided for at the time of subdivision. Over the long-term, Council intends to provide protection of properties in all urban areas and to ensure stormwater is contained in channels, pipes and structures to direct the flow in a controlled manner across Council-owned/vested land to a waterway or other suitable discharge points. Council’s policy is that unused stormwater is disposed of onsite through appropriate means.

SWDC Table 6: Wastewater system

| Stormwater Assets (urban) | Metres of pipe | Metres of channel |
| --- | --- | --- |
| Featherston, Martinborough, and Greytown | 17,925 | 20,151 |
| The overall level of stormwater protection is provided by a combination of a primary and a secondary stormwater system. The primary stormwater system is the system of reticulated pipes, culverts, open drains and access chambers. It is designed to collect stormwater resulting from moderate rainfall and discharge into watercourses. Based on operational knowledge, critical stormwater assets include culverts, dams. And where pipe intersects state highway carriageway. There is further work to be undertaken regarding urban stormwater networks when the Water Services Authority release stormwater performance measures. |  |  |

Statement of Service Performance - Stormwater

Performance indicators will transfer to the WSCCO following transition and will be reported by the CCO from the 2027/28 year.

SWDC Table 7: Performance indicators – stormwater

| Service Level | Key Performance Indicators | Performance Targets (for the financial year) |  |  |  |  |  |  | How it will be measured |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline | 2023/24 (actual) | 2024/25 (target) | 2025/26 | 2026/27 | 2027/28 | 2028-34 |  |
| Stormwater drains are well operated and maintained by the Council | Number of flooding events that occur in the district. Dept of Internal Affairs defines a flooding event as an overflow of stormwater from a territorial authority’s stormwater system that enters a habitable floor. | 0 | 0 | 10 events or less achieved | 10 events or less achieved | 10 events or less achieved | 10 events or less achieved | 10 events or less achieved | The information is recorded by our contractor Wellington Water Limited. |
|  | For each flooding event, the number of habitable floors affected. | 0 | 0 | Less than or equal to 1/1000 connections | Less than or equal to 1/1000 connections | Less than or equal to 1/1000 connections | Less than or equal to 1/1000 connections | Less than or equal to 1/1000 connections | The information is recorded by our contractor Wellington Water Limited. |

| Service Level | Key Performance Indicators | Performance Targets (for the financial year) |  |  |  |  |  |  | How it will be measured |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Baseline | 2023/24 (actual) | 2024/25 (target) | 2025/26 | 2026/27 | 2027/28 | 2028-34 |  |
| Consent Compliance | Compliance with Council resource consents for discharge from its stormwater system, measured by the number of abatement notices, infringement notices, enforcement orders and convictions received by the Council in relation to those consents | 100% | 100% | 100% | 100% | 100% | 100% | 100% | The information is recorded by our contractor Wellington Water Limited and monitored by Greater Wellington Regional Council. |
|  | Median response time to attend a flooding event (from time of notification to the time service personnel arrive onsite) | No flooding events | No flooding events | 3 hours or less | 3 hours or less | 3 hours or less | 3 hours or less | 3 hours or less | The information is recorded by our contractor Wellington Water Limited. |
|  | Number of complaints received about the performance of the Council’s stormwater system | New baseline to be established | N/A | No more than 3 per 1000 | No more than 3 per 1000 | No more than 3 per 1000 | No more than 3 per 1000 | No more than 3 per 1000 | Council records |

SWDC Table 8: water services schemes

| Serviced areas (by reticulated network) | Water supply # schemes | Wastewater #schemes | Stormwater # catchments |
| --- | --- | --- | --- |
| Residential areas (If more than one identify separately) | Featherston 1,360 serviced and 52 serviceable Greytown 1,579 serviced and 102 serviceable Martinborough and Pirinoa 1,487 serviced and 38 serviceable water connections | Featherston 1,280 serviced and 56 serviceable Greytown 1,473 serviced and 111 serviceable Martinborough and Lake Ferry 1,316 serviced and 41 serviceable water connections | Stormwater is considered part of the general rate across the urban areas. SW 3,984 total connections across urban Featherston, Greytown, and Martinborough |
| Non-residential areas (If more than one identify separately) | N/A | N/A | N/A |
| Mixed-Use rural drinking water schemes (where these schemes are not part of the council’s water services network) | N/A | N/A | N/A |
| Areas that do not receive water services (If more than one identify separately) | The majority of rural zoned land is not serviced by Water Supply networks. | The majority of rural zoned land is not serviced by Wastewater networks. | No widespread provision of stormwater in rural areas (not serviced). |
| Proposed growth areas - Planned (as identified in district plan) - Infrastructure enabled (as identified and funded in LTP) | Featherston, Greytown and Martinborough brownfields development Extra dwellings by 2051: Greytown – 434 dwellings Featherston – 418 dwellings Martinborough – 283 dwellings Tauherenikau – 147 dwellings Aorangi Forest – 111 dwellings Kahutara – 100 dwellings | Featherston, Greytown and Martinborough brownfields development. Martinborough and Greytown WWTP planned works Extra dwellings by 2051: Greytown – 434 dwellings Featherston – 418 dwellings Martinborough – 283 dwellings Tauherenikau – 147 dwellings Aorangi Forest – 111 dwellings Kahutara – 100 dwellings | Featherston, Greytown and Martinborough brownfields development Extra dwellings by 2051: Greytown – 434 dwellings Featherston – 418 dwellings Martinborough – 283 dwellings Tauherenikau – 147 dwellings Aorangi Forest – 111 dwellings Kahutara – 100 dwellings |

Source for connections: SWDC – Rating Database Extracts – Rates Factors _4 June 2025

Growth

South Wairarapa has a growing population, with a demographic shift. Featherston has been identified as a Growth Node in the South Wairarapa Spatial Plan and is expected to have greater diversity in youth and ethnicity going forward. The Featherston Masterplan is an example of how the council is preparing for future growth (Final-SWDC-Featherston-Mastertplan-June-2024-compressed.pdf).

The 2025-34 LTP is based on Sense Partners’ median growth projections. South Wairarapa is not a high or medium growth district for the purposes of the National Policy Statement for Urban Development and in terms of local economic growth. However, Sense Partners’ projections are that South Wairarapa population will grow 1.4 times more than the average of the Wellington Region, and 1.2 times the national average. Because of this, the medium growth scenario is more likely over the life of the 2025-34 LTP. Significant investment is needed, especially in the wastewater network and treatment plants to enable growth to occur.

SWDC is acutely aware that the current impact of the capacity constraints (no further connections) for both Martinborough and Greytown wastewater treatment plants restricts future growth aspirations. The Council has kept the water investment programme within the 2025-34 Infrastructure Strategy (here SWDC-2025-34-Long-Term-Plan-Final2.pdf) for the first three financial years of the Strategy outlining the infrastructure issues the district is facing. The funding for these years has been retained at the levels recommended by Wellington Water. Funding levels of the remainder of the WSDP period (i.e., after transition to the WSCCO) have been adjusted on the basis of the independent assurance review undertaken by the Council.  The focus of the Infrastructure Strategy has been to put building blocks in place for three waters assets to support sound decision making. The collection of additional information to improve underlying asset data is essential to adequately prepare for operational transition to a new water services provider.

The Martinborough and Greytown WWTPs Growth and Capacity Study (2024) assesses the capacity of the Martinborough and Greytown wastewater treatment plants (WWTP’s) to cater for future population growth while complying with their resource consent requirements. The current consents, granted in 2016, assumed zero population growth over the 35-year consent duration. Martinborough’s resident population is now projected to grow from 1,900 in 2024 to 2,600 by 2051. Greytown’s resident population is expected to grow from 2,800 to 3,700 by 2051. This will require additional capital investment in the WWTP and irrigation systems.

Following planned improvement works to address compliance issues at both plants over the next five years, irrigation modelling indicates that the expected population growth (medium growth scenario) and associated increased flows can be catered for on the current planned Stage 2A irrigation areas by increasing the winter storage volume over what was originally envisaged in the consent applications. Alternatively, additional irrigation areas could be developed instead of increased storage. The current plan is to expedite stage 2A and discharge a greater proportion of wastewater effluent to land. In doing this it is expected that resource consent compliance will improve and consequently promote the case for allowing new connections to resume.

Asset condition

SWDC Table 9: Asset condition information

| Parameters | Drinking supply | Wastewater | Stormwater |
| --- | --- | --- | --- |
| Average age of Network Assets | Treatment plant assets are between 1 and 30-years old, which is quite young. 14.0 years old for pipes 29.0 years old for hydrants 23.7 years old for valves 17.1 years old for reservoirs 12.6 years old for treatment plants | Treatment plant assets have a design life of 50 years – a significant portion of treatment plant assets will require renewal in the next 20 years. 29.3 years old for pipes 16.3 years old for pump stations 24.8 years old for treatment plants | 37.5 years for pipes 53.0 years for channels |
| Critical Assets | Very High Criticality Assets (VHCA) 19km of pipe assets, about 10% of pipes 127 or about 25% of water treatment plant assets, and 11 reservoirs. | 15 pump stations 81.1km pipes | [identified / not identified] Moroa water race, which flows through Greytown Dorsett Square stormwater grate, Featherston |
| Above ground assets - Treatment plant/s - Percentage or number of above ground assets with a condition rating - Percentage of above –ground assets in poor or very poor condition | 5 [<20%]* [<1%]** Limited condition surveys have been completed of the water supply assets to assess the current state. A hybrid approach was adopted using the multiple data sets and condition inferred – based on the % of remaining useful life. Approximately $7m replacement value of reservoirs are in poor condition. | 4 [<20%]* [<5%]** Limited condition surveys have been completed to assess the current asset state. The inferred asset condition is based on the percentage of remaining useful life. Undertaking planned condition surveys of the above and below ground wastewater assets is a high priority to inform future renewals. | 17.9 km of pipes, 20.2 km of channels [<20%]* [36%]** Asset condition has not been formally assessed for the stormwater network to date. Inferred stormwater condition is based on the percentage of remaining useful life. |
| Below ground assets - Total Km of reticulation - Percentage of network with condition grading - Percentage of network in poor or very poor condition | Pipes 161.6 Km - which accounts for approximately 70% of replacement value. Approximately $24m water service pipes are in poor or very poor condition. Valves - 1,041 Hydrants – 609 Reservoirs – 11 (pg. 34 IS) Note: while most pipe assets have not reached their theoretical design life, based on operational and technical knowledge, there are approximately $30m worth of renewals up to 2040. | Pipes 81.651 km – which accounts for approximately 65% of the portfolio in replacement value. Approximately $10m replacement value of wastewater pipes are in poor condition and less than $1m in very poor condition. (Note: the inferred condition of the WW Treatment Plants is Fair with approximately $50m replacement value ascribed) | Pipes – 17,927m (17.9 km) Channels – 20,151m (20.1 km) Channel and SW pipes $3M replacement value in poor condition. |

Source: 3 Waters Asset Data for Infrastructure Strategy.xlsx

Date: December 2024

*Currently, only limited condition surveys of three water assets have been completed to assess the current asset state.

**The percentage of assets in poor or very poor condition is calculated based on an aged, inferred condition as % remaining useful life (RUL). The grades for categorising inferred conditions are: Poor - 40% ˃ % of RUL ≥ 10%, Very poor - % of RUL < 10%.

Asset management approach

At time of writing, Wellington Water Ltd is the operator and carrying out asset renewals under the master service agreement Management Services Agreement (MSA) shared with other Wellington councils. Since 2019, Wellington Water Ltd has had responsibility for managing and providing three waters services to Council. This has involved providing advice to Council on investment priorities it its planning processes. The current split between asset ownership and operation causes significant challenges and inconsistencies in asset management approach.  It has also meant that SWDC has relatively limited information on the condition of the assets and resulting limited ability to scrutinise the capital programme. The Council’s priority in the transition will be to build a better understanding of asset condition and resulting prioritising of the capital programme.  This will help inform the WSO’s determination of a regional programme and to the manage the costs for the SWDC customers.

Asset management practices have been at a basic maturity level, based on operational knowledge. The 2024-2025 Infrastructure Strategy (IS) addresses the key issues in managing these assets over the next two years, prior to the WSCCO becoming operative in 2027. It outlines options to address these issues, alongside cost and delivery implications. The IS also outlines the most likely scenario for the management of our infrastructure assets during its 31- year period, the estimated costs of managing those assets, the nature and timing of expected significant capital expenditure decisions and the assumptions on which the scenarios are based. Within the context of water reform, the focus for the 2024 Strategy has been to establish the requisite building blocks to prepare for the future and improve practices for managing three water assets, particularly improving data reliability. Good planning work has been done for managing three water assets, but it is recognised that the practices for managing the three water assets still need to improve.

South Wairarapa District Council’s standard infrastructure financial and insurance valuations are conducted biennially, with the next scheduled revaluation in 2026. Current water assets replacement value at 30 June 2024 was $146.9m. In preparation, Council has committed to engaging additional engineering assessments, with a particular focus on the condition of treatment plants. To ensure asset values are accurate and up to date at the point of transition, an out-of-cycle revaluation is planned for 2027. This approach will support a robust and transparent transfer of assets to the new entity.

SWDC has recently (1 July 2025) taken over capital project delivery for system renewals and upgrades for levels of service and growth. Council voted to keep operational expenditure with the water management entity for another year. This decision was made with the assumption that alternative options would be explored and implemented for service provision for the 2026/27 financial year – these options are being actively explored but are not yet resolved at the time of submitting this plan. The benefits of managing capital expenditure in-house include more cost control, cost efficiency, on-time delivery, and local contractor delivery. It will also lend itself to programme optimisation leading into the new entity as part of the transition process with partner councils. Over the 2025/26 year, the priorities for the capital programme are preparation of resource consent applications, completing work programmes to return to compliance with the existing resource consent conditions, refining the capital programme and ensuring that water infrastructure requirements for our communities are clearly articulated to support the development of the WSCCO’s delivery strategy. Part of this work involves the preparation of an Implementation Plan, which will detail the programmed work over the next two-years, including timeframes and detailed costings. This will ensure that there is sound understanding of asset condition and prioritised work plans, prior to asset transfer to the WSCCO.

The Council will transfer responsibility for water services to the WSCCO on or before 1 July 2027. It is expected that the WSCCO will develop its own asset management policy and approach based on industry best practice and expected levels of service, informed by the work the Council does in the transition period to review asset condition and the capital programme.

Statement of regulatory compliance

Within SWDC’s 2025/34 Long-Term Plan, water services have been funded for the continued safe maintenance and operation of our water assets based on programme advice from Wellington Water to meet regulatory standards and growth needs. Critical investigations are being completed to ensure the water supply and wastewater services meet the minimum regulatory standards set by the Water Services Act 2021. Other actions include all monitoring activity being carried out to comply with our consent conditions, running automated control systems that a critical to core operation of the water networks, and limited planned maintenance activities on the high priority assets, such as ultraviolet treatment on our wastewater treatment plants.

It is acknowledged that reliably maintained and functioning equipment is a key part of consent compliance. To that end, appropriate maintenance is being undertaken at our wastewater treatment plants for continuous improvement towards compliance.  Featherston and Lake Ferry wastewater treatment plants are compliant; however, Greytown and Martinborough wastewater treatment plants have compliance matters that are being managed and require major investment to support growth.  All four SWDC drinking water plants are compliant with drinking water standards.

Wastewater

SWDC is addressing wastewater consenting renewal as a priority. It is acknowledged that consent condition compliance with aged wastewater infrastructure may be restrictive and costly for the community. There are also significant challenges with future upgrades and affordability issues for ratepayers. This means that the prudent way forward is to commit to addressing the long-standing wastewater issues that will be fit-for-purpose into the long-term and foster growth. Interrelated issues to consider include growth, freshwater management and the new Water Services Authority Taumata Arowai performance measures. It will take some time to develop a robust long-term investment plan for wastewater, with a view to improving freshwater quality of the receiving environment. In the intermediary period, SWDC will further consenting projects and work towards actively addressing growth constraints due to lack of wastewater plant capacity. A key outcome is to be able to accept new wastewater connections in Martinborough and Greytown.

On 4 July 2025, SWDC received a request for investigation from GWRC into non-compliant effluent quality discharged from the Greytown WWTP [consent WAR080254]. The query related to ongoing exceedances of effluent quality standards over the last 16 months on various occasions. In addressing this matter, SWDC are moving at pace towards discharge to land anticipated as stage 2A in the Greytown and Martinborough resource consents and the 2011 SWDC Wastewater Strategy. On 31 July 2025, SWDC received advice that the To Do Abatement Notice A1099 requirements had been fulfilled. This relates to Martinborough WWTP Dewatering Consents WAR250002 [39756].

The successful desludging work at the Martinborough Wastewater Treatment Plant involved the removal of 660 tonnes of sludge, the pond now needs time to settle before its new performance can be measured. Greater Wellington Regional Council and South Wairarapa District Council will continue to work together in planning next steps towards maintaining compliance going forward. It is noted that desludging does not increase the capacity of a wastewater treatment plant, however it is an essential step to improve operations, meet compliance requirements and reduce environmental and public health risks. Council is actively exploring options to increase capacity, with funding allocated in the 2025-34 Long-Term Plan.

Preparations are now under way to begin desludging at the Greytown Wastewater Treatment Plant later in 2025. A capacity study has been completed, and the findings will help guide future capacity upgrades. The ability to increase capacity is closely tied to irrigation to land, and funding for this work is included in the 2025-34 Long-Term Plan.

SWDC Table 10: Resource consent information

| Service Type | Project & Consent # | Background & Timeline | Key Outcomes |
| --- | --- | --- | --- |
| Wastewater | Featherston WWTP Discharge and ancillary consents WAR970080 [2625] WAR970080 [23139] | The resource consent process has been ongoing since 2012. Resource consents WAR970080 [2625][23139] expired in 2012 and an application lodged for replacement consents in that same year. GWRC concerns with the application resulted in an alternative application being lodged and publicly notified in May 2018. The alternative application also had on-going concerns for GWRC. As a result, in 2020 SWDC withdrew the alternative application in favour of preparing and lodging a third application with GWRC in 2020. Resource consent application WAR230290 was lodged with GWRC on 1 May 2023. This was publicly notified in October 2024 and has progressed to the hearing stage - July 2025. | The purpose of the consenting project is replacement of expired consents. The consent duration is 10-years (likely expiry 2035). A decision is expected mid-2025. Proposed improvements offered as consent conditions: 2025/26 Field investigations, early construction works and procurement. 2026/27 Construction - DAF 2027/28 Construction – Stage 1 land application 2028/29 No capex activity 2029/30 Re-mobilise / design 2030/31 Stage 2 land application |
| Wastewater | Martinborough WWTP Dewatering Consents WAR250002 [39756] | The GWRC consent (WAR250002 [39756]) was granted on 27 September 2024. This construction consent expires on 27 September 2029. Martinborough’s WWTP has not been cleared of sludge since the 1970s, which has contributed to treated wastewater quality compliance issues at the WWTP. To address the compliance issues, the plan is to remove the sludge and dewater in geotextile bags within a lined and drained bund. This required an earthworks resource consent from GWRC and an Outline Plan of Works. SWDC sought no changes to the Plan. | The purpose of the consenting project is to de-sludge WWTP ponds and improve treated wastewater quality. The laydown area was constructed in 2025. Desludging was completed in July 2025. Dewatering of the sludge is expected to take 3-5 years. |
| Wastewater | Martinborough & Greytown WWTP Growth and Capacity Study (2024) | The Martinborough and Greytown WWTPs Growth and Capacity Study (2024) assesses the capacity of the Martinborough and Greytown wastewater treatment plants (WWTP’s) to cater for future population growth while complying with their resource consent requirements. It is a high-level growth planning exercise to determine upgrades required at both the Martinborough and Greytown WWTP to accommodate growth in the catchment. Work to date indicates likelihood of needing to revisit resource consents for both WWTPs to accommodate growth. | The Martinborough & Greytown WWTP Growth and Capacity Study sets out the preferred WWTP upgrade strategies for both communities to cater for forecast growth to 2050. Planned Improvement Works: 2025-2030 Addressing compliance issues at both WWTPs through: A) Pond desludging B) Inlet screens C) UV replacement (Martinborough only) D) Pond hydraulic improvements E) Nitrogen removal upgrades F) Stage 2A irrigation schemes 2030 – 2040 Constructing Stage 2B winter storage lagoons and or additional irrigation areas to manage increased wastewater volumes and comply with consent river discharge limits. Under the resource consent conditions, this work must be completed by 2035 (Martinborough) and 2039 (Greytown). Irrigation modelling indicates that the expected population growth (medium growth scenario) and associated increased flows can be catered for on the current planned Stage 2A irrigation areas by increasing the winter storage volume over what was originally envisaged in the consent applications. Alternatively, additional irrigation areas could be developed instead of increased storage. |
| Wastewater | Resource consent compliance issues | The main issues relate to: discharge volume to river non-compliances, nitrogen non-compliance, E.coli non-compliances, and Stage 2B irrigation capacity. | Discharge volume to the river - high levels of infiltration/inflow and issues with the current irrigation systems lead to exceedances of annual volume limits to the Ruamāhanga River (Martinborough) and Papawai Stream (Greytown). The non-compliances will likely continue until commissioning of the Stage 2A irrigation schemes, currently scheduled for completion in 2030. |
|  |  |  | Nitrogen non-compliances – both WWTPs struggle to meet their treated wastewater total and ammoniacal nitrogen standards. The pond treatment plants were not designed to remove ammonia or total nitrogen, and upgrades are needed to achieve compliance. |
|  |  |  | E.coli non-compliances - The UV system at Martinborough performs poorly and is to be replaced soon. |
|  |  |  | Stage 2B irrigation capacity – Stage 2B operation has significantly reduced river availability for Martinborough and none for Greytown, requiring the construction of winter storage lagoons. The Stage 2 irrigation schemes were designed based on current populations and did not envisage population growth. Additional winter storage and/or land area will be required to cater for growth. |
| Wastewater | Greytown WWTP Discharge Consents WAR080254 [26633], [33180] [33181] [33182] | The Greytown WWTP Discharge Consents were granted in 2016 and are due to expire in February 2051. | The consent conditions of the Greytown WWTP Discharge Consents include key milestone dates for upgrades. |
| Stormwater | Discharge permit: Stormwater to land/water WAR220186 [38049] South Wairarapa Stage 1 Stormwater Consent | The Stormwater discharge permit was granted on 17 April 2025 and expires on 17 April 2030. Within six-months of granting of the consent (October 2025) the Stormwater Monitoring Plan (SMP) is to be submitted for certification. No later than 31 December 2026 the Stormwater Management Strategy progress report is due. No later than 30 July 2029 the draft Stormwater Management Strategy (SMS) is due with GWRC. This 5-year global consent is a stage 1 consent required under the Natural Resources Plan (R52). It was lodged in 2021 and the application started November 2024. Work towards lodging another consent application would likely commence in 2027. | Discharge of stormwater from the South Wairarapa District Council owned stormwater network to freshwater and land where it may enter water. The area that this applies to are the various water courses and land around the urban centres of the South Wairarapa District, Wairarapa, including Featherston, Greytown, and Martinborough. The SMP (based on the 15 October 2024 draft) will serve to establish the baseline state of the receiving water into which stormwater from the urban stormwater network discharges into, to monitor the contaminant concentrations of the stormwater discharged, and to monitor and manage acute effects to human health. No later than 31 December 2025, a written report is required detailing the known interaction between the reticulated wastewater network (including pumpstations) and the urban stormwater network for Featherston, Greytown, and Martinborough. |
| Water Supply | Greytown (Memorial Park) Water Take Consents | Existing resource consent granted by GWRC in 2012 for the take of water associated with the existing bore (WAR120244[31689]) and allows for a take of up to 900,000m3/year, up to 5,184m3/day from September to May inclusive and up to 3,000m3/day from June to August inclusive, at a maximum pumping rate of 60 litres/second. It also includes water being taken from the existing Greytown Memorial Park bore. | A variation for this consent will be sought by November 2025 to install a second bore pump for the Greytown (Memorial Park) water treatment plant. |
| Water Supply | Greytown and Featherston Water Take Consents WAR200062 [36429] WAR120244 [31689] | The Greytown and Featherston water take consents expire in September 2037. The water supply for Greytown and Featherston is sourced from four bores next to the Waiohine River WAR200062 [36429]. WAR120244 [31689] provides water supply to Greytown only, via a groundwater bore. | A new resource consent application for water take would need to be lodged in March 2037. |
| Water Supply | Martinborough Water Supply takes WAR120245[31690] | The Martinborough Water Supply takes consents expire in November 2037. Three bores next to the Ruamāhanga River provide water supply to Martinborough. | A new resource consent application for water supply take would need to be lodged in May 2037. |
| Water Supply | Pirinoa Water Supply Take WAR250221 | The existing consent expires on 30 September 2040. | Minor works needed. |
| Water Race | SWDC water take consents back-up supply WAR120050[31362] [31366] WAR120051 [31366] | These consents expire September 2030 and provide for the take and back-up use of water for Featherston and Martinborough. | There is no intent to renew these water take consents. The existing infrastructure supporting the potential occasional use of this water supply would need assessment and investment to be considered a preferred water source. |
| Water Race | SWDC water race consents WAR200185[36638-36641] Longwood - Featherston | The Longwood water race consents expire on 30 September 2029. The Longwood water race is 40km long and services 1500ha of farmland. | Application for renewal of consent would have to be lodged by 30 March 2029. Flow monitoring, customer survey projects and bylaw renewal not yet started. |
| Water Race | SWDC water race consents WAR010200 [21378][21379] [21586][21587] Moroa – Greytown | The Moroa water race consent expired on 13 April 2025. Consent application WAR250088 was lodged on 11 October 2024, six months in advance of expiry. This has ensured continuance of operation through the consenting journey. On 3 December 2024 GWRC confirmed acceptance of the consent application. Council has responded to all questions regarding the s92 Additional Information request. | SWDC has applied for the renewal of the resource consents WAR010200 to take water from the Waiohine River to operate the Moroa Water Races. |

SWDC Table 11: Regulatory compliance

| Parameters | Drinking supply | Wastewater | Stormwater |
| --- | --- | --- | --- |
| Drinking water supply - Bacterial compliance (E.coli) * - Protozoa compliance * - Chemical compliance * - Boiling water notices in place - Fluoridation - Average consumption of drinking water - Water restrictions in place (last 3 years) - Firefighting sufficient | 3 WTPs compliant T3, D3 rules, 1 via T2, D2 3 WTPs compliant via T3 rules, 1 via T2 4 WTPs compliant via G rules 0 No schemes are fluoridated [583 litres/person/day] Yes No – Featherston and Greytown | n/a | n/a |
| Resource Management - Significant consents (note if consent is expired and operating on S124) - Expire in the next 10 years - Non-compliance: - Significant risk non-compliance - Moderate risk non-compliance - Low risk non-compliance - Active resource consent applications - Compliance actions (last 24 months): - Warning - Abatement notice - Infringement notice - Enforcement order - Convictions | Water supply take [6] Water discharge [0] 2 (Longwood & Moroa Water Race consents) 0 0 0 0 0 0 0 0 0 | Wastewater discharge water/land/air [12] Network [0] 4 (Featherston WWTP) 2 0 2 2 1 4 0 0 0 | Stormwater discharge 0 Network 1 1 (Global SW Consent) 0 0 0 0 0 0 0 0 0 |

*Note G, D1-3, T1-3, S1-3 relate to modules of the New Zealand Drinking Water Quality Assurance Rules 2022 (revised 2024)

Capital expenditure required to deliver water services

The significant capital investments are identified in the Additional Information in this plan. In summary, the general trend of capital investment over the coming ten years and beyond is that of renewal and improvement to existing assets in the short to medium term, followed by a return to focus on growth in the later part of the period. There are significant upgrades planned to water supply infrastructure in Greytown, and to wastewater infrastructure, particularly treatment plants, in all three towns within the district.

Wellington Water has advised Council on investment priorities in its planning processes and Council has made the final investment decisions. Council took a largely hands-off approach under this arrangement, with reliance on Wellington Water to provide requisite information to aid decision making. This means that Wellington Water has not always been actively scrutinised by Council as the client and asset owner.

In bringing project management of capital projects back in-house from Wellington Water from 1 July 2025, Council will be actively reviewing investment priorities and planning processes. The advantages to bringing the capital works programme back in-house are:

- Tighter programme control – allows more cost control, cost efficiency, on-time delivery, local contractor delivery of the overall programme

- Programme optimisation – allows for an optimised programme, with costs and risks, to be prepared leading into the new entity

- Data quality – direct control of the capital works programme ensures that as built are up-to-date in the Council’s system.

SWDC is actively taking ownership of its capital investment programme in the lead-up to transition. We are independently reviewing the investment required to meet consent conditions, regulatory obligations, and future growth, drawing on new and emerging information (e.g., updated growth projections, evolving regional council requirements, changes in national regulation, and independent expert advice) to ensure we are well placed to provide sound investment information to the WSCCO. Part of this work involves the preparation of an Implementation Plan, which will detail the programmed work over the next two-years, including timeframes and detailed costings. This will ensure that there is sound understanding of asset condition and prioritised work plans, prior to asset transfer to the WSCCO.

Following independent advice on the level of capital spend (Appendix 4), a 45% reduction adjustment (relative to the Council’s LTP programme) has been made to the projected capital costs from the 2027/28 financial year onwards. This adjustment was based on external assurance work commissioned by Council due to concerns relating to Wellington Water’s cost estimates.  Wellington Water (WWL) has an established method for cost estimation. Where projects are at early stages of development, there is a large degree of contingency and funding risk applied; WWL uses a 40% contingency and 60% Funding Risk for Level One Estimates. In addition, WWL allocates a 10% cost to all capital project for the overall programme management of the capital programmes, including providing Strategic Advisory memos. A 10% management fee is considered at the higher end of industry practice. Contingencies and funding risk allocations applied during the early stages of cost estimation can exceed 100% of the project’s base cost, effectively more than doubling the overall cost estimate. This substantial uplift is driven by a theoretical approach to risk-based cost estimating, rather than grounded in practical three waters expertise. Furthermore, the WWL risk assessment appears to be broadly based on project value and a general risk profile, rather than being proportionate to the actual complexity of the project. Note the programme (i.e., projects and phasing) has been retained as provided by Wellington Water; it is the costs of the programme that have been adjusted based on the independent review.

SWDC Table 12: Water services investment requirements

| Projected investment in water services | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Drinking water |  |  |  |  |  |  |  |  |  |  |
| Capital expenditure - to meet additional demand | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Capital expenditure - to improve levels of services | 4,397 | 3,829 | 2,736 | 534 | 1,846 | 1,866 | 2,068 | 2,036 | 2,041 | 1,742 |
| Capital expenditure - to replace existing assets | 4,955 | 5,187 | 4,163 | 1,394 | 1,394 | 2,083 | 2,443 | 2,720 | 2,787 | 3,235 |
| Total projected investment for drinking water | 9,352 | 9,016 | 6,899 | 1,928 | 3,241 | 3,949 | 4,510 | 4,756 | 4,829 | 4,977 |
| Wastewater |  |  |  |  |  |  |  |  |  |  |
| Capital expenditure - to meet additional demand | 0 | 993 | 2,984 | 5,225 | 3,300 | 2,199 | 0 | 0 | 0 | 0 |
| Capital expenditure - to improve levels of services | 3,110 | 2,251 | 8,954 | 8,870 | 11,021 | 5,478 | 5,503 | 5,983 | 2,344 | 3,819 |
| Capital expenditure - to replace existing assets | 646 | 936 | 577 | 378 | 295 | 2,382 | 2,364 | 2,433 | 2,353 | 2,342 |
| Total projected investment for wastewater | 3,756 | 4,180 | 12,515 | 14,473 | 14,617 | 10,059 | 7,867 | 8,416 | 4,697 | 6,161 |
| Stormwater |  |  |  |  |  |  |  |  |  |  |
| Capital expenditure - to meet additional demand | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Capital expenditure - to improve levels of services | 0 | 0 | 0 | 110 | 385 | 935 | 1,649 | 2,199 | 1,786 | 1,181 |
| Capital expenditure - to replace existing assets | 206 | 293 | 293 | 162 | 201 | 187 | 187 | 186 | 186 | 186 |
| Total projected investment for stormwater | 206 | 293 | 293 | 272 | 586 | 1,122 | 1,836 | 2,385 | 1,972 | 1,366 |
| Total projected investment in water services | 13,315 | 13,488 | 19,708 | 16,674 | 18,443 | 15,130 | 14,214 | 15,557 | 11,498 | 12,504 |

Historical delivery against planned expenditure

The overall capital works programme for water services has been delivered at levels indicated in the Council’s LTPs, with variation by investment type.

- Investment has been concentrated in water supply and wastewater assets, reflecting strategic priorities and community needs. Focus has been more on renewals than improvements or growth due to prioritising replacement of aging network. Renewals also reduce the frequency of operating costs on repairs and maintenance.

- Actual delivery has varied across years and asset types, with water supply assets showing a mix of under- and over-achievement relative to planned targets.

- Delivery has been influenced by factors such as contractor availability, project readiness, and resource constraints.

Over the next two financial years, Council will enhance asset planning and project scoping to better define and confirm the capital programme for the 2025/26 and 2026/27 years. The Annual Plan process will be used to refine and update capital investment figures annually, ensuring alignment with current priorities and delivery capacity. The Council aims to refine the investment profile as we better understand our water services assets. Undertaking planned condition surveys is a high priority, which will inform future renewals. We have made provisions in our renewal budget to enable works to be undertaken as we progress. This information will be shared with the WSCCO to inform regional asset management planning and programme.

Our renewal forecast has been developed to address our future asset needs. It has considered the following factors:

- Council’s debt ceiling in the first two years for capital works

- Additional renewals as asset conditions are better understood

- Cost smoothing to reduce financial impact on Council

- Capital works achievability based on historical performance and

- Outputs from the latest asset valuation to inform the cost of renewal.

SWDC Table 13: Delivery against planned investment

| Delivery against planned investment | Renewals investment for water services |  |  |  | Total Investment in water services |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | FY2024/25 | FY21/22 - FY23/24 | FY18/19 - FY20/21 | Total | FY2024/25 | FY21/22 - FY23/24 | FY18/19 - FY20/21 | Total |
| Total planned investment (set in the relevant LTP) | 1,366 | 3,180 | 2,648 | 7,195 | 17,404 | 16,799 | 6,147 | 40,351 |
| Total actual investment | 1,068 | 10,322 | 8,028 | 19,417 | 5,471 | 17,557 | 17,673 | 40,700 |
| Delivery against planned investment (%) | 78% | 325% | 303% | 270% | 31% | 105% | 287% | 101% |

# Part C: Revenue and financing arrangements

## C1: Revenue and charging arrangements

Note for reader
As set out in Part A, proposed charging arrangements for water services will be subject to further discussions between the Partner Councils and the WSCCO. These arrangements will reflect the legislative requirements signalled in the Local Government (Water Services) Bill.  Current charging structures are expected to continue under the WSCCO for a period – the WSCCO will be responsible for determining the amount of revenue to collect according to financial sustainability requirements and existing tariff structures. The WSCCO will review tariff structures, including consideration of metering, as required under the Local Government (Water Services) Bill. The feasibility of the WSCCO directly billing and invoicing customers from day one will be determined through establishment and transition planning.

Charging and billing arrangements

Currently, SWDC water services are charged uniformly across all supply schemes and catchments. Rates are levied in four instalments annually, and water usage is treated as a rate, invoiced annually for most properties, with an additional mid-year invoice issued to high-use properties. There is no differentiation in charging based on scheme, geographic area, or property usage category. Other water-related income is invoiced and collected directly by the Council. Charging is done on a per cubic metre rate and adjusted each year, based on the BERL LGCI.

In the future, it will be the responsibility of the WSCCO to charge for water services. The specific charging mechanisms for each supply scheme or catchment are yet to be determined. Whether the current charging approach is retained or revised will be decided by the WSCCO, which will also be fully responsible for revenue collection. Part A of this plan notes the WSCCO will be required to review and confirm its tariff structure as required by the Local Government (Water Services) Bill.

Responsibility for revenue collection from day 1 will be determined through the transition planning – as Part A indicates, it is yet to be determined exactly how billing arrangements are established for the WSCCO, however, if feasible, shareholding councils will work towards the entity to be enabled to independently bill for day one. The current assumption is that Councils will collect revenue on the WSCCO’s behalf for a determined period to manage the risk of transition (with revenue requirements set by the WSCCO to meet financial sustainability requirements). In any interim arrangement, councils would act solely as agents, with no liability for collection, and all revenue would be passed through to the WSCCO via Council balance sheets in a manner consistent with the treatment of regional council rates. During the transition, any payments mistakenly made to Council will be transferred to the WSCCO and will not be treated as Council revenue.

Water services revenue requirements

Under this Plan, water services require significant revenue to meet financial sustainability requirements, support ongoing operations, meet regulatory standards, and fund capital investment. These requirements are currently met through a combination of targeted rates, user charges, development contributions, and government grants.

- Water Supply: Council levies a fixed targeted rate for water supply, applied differentially based on service availability. Properties not connected but serviceable receive a 50% discount. Each serviced property is allocated 250 m³ of water annually, with an additional targeted rate applied for usage exceeding this threshold.

- Wastewater: A fixed targeted rate is levied, also applied differentially. Non-connected serviceable properties receive a 50% discount, and non-residential properties pay an additional rate per extra pan.

- Stormwater: Funded via a targeted rate based on capital value, applied to properties within urban zones. No differentials are applied.

- Other Revenue: Council collects financial contributions from development for capital expenditure related to infrastructure growth.

Based on current forecasts, SWDC anticipates water services operating expenses (excluding depreciation) of $88.3 million over the WSDP period, against $192 million in operating revenues, generating $103.8mmillion in cash surpluses. Individual Funding Impact Statements in Part E set out the projected level of revenue by expected source. Capital revenues are a combination of development contributions and debt. The information in the table below identifies sources of revenue.

As SWCO is transitioning water services to a WSCCO, the WSCCO will be required to meet the LGFA’s financial covenants, including FFO-to-debt and interest coverage ratios, with the partner councils setting a target capital structure that maintains an FFO-to-debt at 10%, against the LGFA covenant of 9%. By moving to this capital structure, the WSCCO will not need to fund depreciation from cash/revenue in the same way as SWDC, instead the WSCCO will use debt to finance investment to ensure equitable sharing of costs over time, while maintaining borrowing within prudent limits to be determined by the board of the WSCCO, consistent with LGFA limits and agreed council support arrangements.

Future sources of revenue

Sources of revenue in the future will be set by the WSCCO but are expected to be similar to current arrangements for a transition period. Initially charging and billing is likely to be undertaken by SWDC and passed through to the WSCCO, with the Board responsible for determining the amount of revenue to collect and advising on the tariffs to be applied consistent with the current tariff structure.  Part E outlines the forecast split and sources of operating and capital revenues for each water service. Foundational principles of the charging framework are expected to ensure transparency and equity in charging. The framework aligns with the principles of cost recovery, water conservation, and affordability.

Note to the reader

This section has been completed based on the Council’s current approach to charging and pricing, as set out in the 2025/34 LTP, with some adjustments which have been applied across the four Councils.  Key adjustments have been made to ensure conservatism in the forecasts, include Taumata Arowai and Commerce Commission levies, incremental costs associated with a WSCCO including audit, board and management costs, and debt funding establishment costs, and incorporate changes in financing cost assumptions to align with current LGFA rates. A summary of modelling assumptions can be found in Appendix 2.

SWDC Table 14: Forecast water services funding impact statement

| Funding impact statement ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sources of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |
| General rates |  |  | 87 | 58 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Targeted rates |  |  | 10,843 | 11,815 | 12,819 | 15,157 | 17,409 | 19,991 | 22,957 | 26,357 | 25,757 | 26,706 |
| Subsidies and grants for operating purposes |  |  | 1,000 | 542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Local authorities fuel tax, fines, infringement fees and other receipts |  |  | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Fees and charges |  |  | 45 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |
| Total operating funding |  |  | 11,975 | 12,580 | 12,918 | 15,196 | 17,449 | 20,031 | 22,996 | 26,396 | 25,796 | 26,746 |
| Applications of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Payments to staff and suppliers |  |  | 8,754 | 8,746 | 7,233 | 7,268 | 8,882 | 7,959 | 7,194 | 7,976 | 7,211 | 7,993 |
| Finance costs |  |  | 951 | 1,530 | 2,236 | 4,154 | 5,056 | 5,814 | 6,281 | 6,597 | 6,753 | 6,812 |
| Internal charges and overheads applied |  |  | 1,018 | 980 | 998 | 857 | 856 | 883 | 874 | 881 | 876 | 880 |
| Other operating funding applications |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of operating funding |  |  | 10,723 | 11,257 | 10,467 | 12,280 | 14,794 | 14,656 | 14,349 | 15,454 | 14,840 | 15,685 |
| Surplus/(deficit) of operating funding |  |  | 1,252 | 1,324 | 2,451 | 2,916 | 2,655 | 5,375 | 8,647 | 10,942 | 10,957 | 11,061 |
| Sources of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Subsidies and grants for capital expenditure |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Development and financial contributions |  |  | 416 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 |
| Increase/(decrease) in debt |  |  | 10,610 | 11,765 | 16,857 | 14,607 | 15,388 | 9,355 | 5,166 | 4,214 | 142 | 1,044 |
| Gross proceeds from sales of assets |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Other dedicated capital funding |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total sources of capital funding |  |  | 11,025 | 12,165 | 17,257 | 15,007 | 15,788 | 9,755 | 5,566 | 4,614 | 542 | 1,443 |
| Applications of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital expenditure - to meet additional demand |  |  | 0 | 993 | 2,984 | 5,225 | 3,300 | 2,199 | 0 | 0 | 0 | 0 |
| Capital expenditure - to improve levels of services |  |  | 7,507 | 6,080 | 11,690 | 9,514 | 13,253 | 8,278 | 9,221 | 10,218 | 6,172 | 6,742 |
| Capital expenditure - to replace existing assets |  |  | 5,807 | 6,415 | 5,034 | 1,934 | 1,890 | 4,652 | 4,993 | 5,339 | 5,327 | 5,762 |
| Increase/(decrease) in reserves |  |  | (1,037) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Increase/(decrease) in investments |  |  | 0 | 0 | 0 | 1,250 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of capital funding |  |  | 12,278 | 13,488 | 19,708 | 17,924 | 18,443 | 15,130 | 14,214 | 15,557 | 11,498 | 12,504 |
| Surplus/(deficit) of capital funding |  |  | (1,252) | (1,324) | (2,451) | (2,916) | (2,655) | (5,375) | (8,647) | (10,942) | (10,957) | (11,061) |
| Funding balance |  |  | (0) | 0 | 0 | 0 | (0) | 0 | 0 | 0 | 0 | 0 |

Affordability for communities

South Wairarapa District faces a unique set of affordability challenges in delivering water services. The district’s infrastructure is fragmented, with separate treatment plants and networks for each town, much of which is aging and in need of critical upgrades over the next decade. With a relatively low number of households and businesses to share the cost, the financial burden of maintaining and improving this infrastructure is high. Based on this, SWDC is projecting prices to increase from $3,000 in FY25 to $6,605 (in nominal (inflated) terms) by FY34 (or $5,170 in real (uninflated) terms), noting this price path is based on the reduced size of the capital programme. This is an acknowledged affordability challenge that will require management – however, SWDC is not financially sustainable on a standalone basis and prices in a WSCCO model are less than they would be under an alternative in-house model.

Whether or not South Wairarapa participates in the WSCCO, these investments must be made to meet regulatory and service level requirements. However, the WSCCO offers a financially sustainable pathway that Council alone cannot achieve. Unlike Council, which is constrained by the Local Government (Rating) Act 2002 and LGFA borrowing covenants, the WSCCO has access to financial tools and mechanisms that allow it to smooth the impact of investment over time and across a broader base. This includes the ability to manage debt and revenue in ways that reduce sharp price increases for individual communities.

Councils have adopted a cost-to-serve, ring-fenced pricing approach for nine years, ensuring that each Council’s pricing reflects its own infrastructure needs while still meeting the overall financial sustainability requirements of the WSDP. In summary, while water service costs will inevitably rise due to necessary infrastructure investment, the WSCCO provides the only financially sustainable option for SWDC to manage these costs in a way that protects affordability for households and businesses. However, to achieve this SWDC requires a four-year transition path post WSCCO establishment, to meet the 10% FFO-to-debt target to manage affordability impacts. A shorter, 2-year transition was considered, but increased costs to communities.

The WSCCO will be able to further consider the South Wairarapa capital programme to determine whether there are options to manage these price increases. The Council will begin the work of assessing the programme through the transition period to consider whether there are changes to phasing or prioritisation that could be made, particularly for projects that are not compliance related or core renewals work.

SWDC Table 15: Average charge per connection

| Average charge per connection including GST |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Average drinking water bill (including GST) |  |  | 1,578 | 1,644 | 1,760 | 1,884 | 2,142 | 2,136 | 2,253 | 2,299 | 2,309 | 2,329 |
| Average wastewater bill (including GST) |  |  | 1,172 | 1,400 | 1,519 | 1,945 | 2,225 | 2,824 | 3,347 | 3,993 | 3,713 | 3,827 |
| Average stormwater bill (including GST) |  |  | 250 | 167 | 168 | 174 | 185 | 193 | 250 | 346 | 413 | 449 |
| Average charge per connection including GST |  |  | 3,000 | 3,211 | 3,447 | 4,003 | 4,551 | 5,152 | 5,850 | 6,637 | 6,435 | 6,605 |
| Water services charges as % of household income |  |  | 2.9% | 3.0% | 3.2% | 3.5% | 3.9% | 4.3% | 4.7% | 5.1% | 4.8% | 4.8% |

## C2: Funding and financing arrangements

Borrowing requirements

Over the WSDP period, SWDC requires substantial capital investment to meet regulatory standards, maintain service levels, and support growth. This will necessitate significant borrowing, particularly in the early years, with projected debt peaking during the initial infrastructure upgrades and network renewals. While this may exceed Council’s current debt covenants with LGFA, the Council does not require individual services to adhere to the Council’s parent debt to revenue, and the investment is essential to meet minimum standards and future-proof infrastructure in anticipation of changing consent conditions and regulatory requirements.

Over the forecast period, water services are forecast to require $150m in capital investments (a reduction of 45% on the initial programme on the basis of independent advice – Appendix 4). To support this investment, borrowing of approximately $78.5m is required, supported by $4m in development contributions and the balance funded from revenue. The tables below identify investment required and net debt, with net debt associated with water services transferred to the WSCCO in FY28.

SWDC required investment can be accommodated within the WSCCO’s borrowing limits but does have implications for affordability for SWDC customers as noted above. SWDC will meet the entity’s targeted 10% FFO to debt ratio by FY32, a transition which has been confirmed with the LGFA. Further consideration will be given during the transition to the phasing of the capital programme to manage affordability without compromising regulatory compliance.

SWDC Table 16: Water services borrowing requirements and net debt (by debt to revenue ratio and FFO to debt)

| Net debt to operating revenue |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total net debt (gross debt less cash) |  |  | 34,072 | 45,837 | 62,694 | 77,301 | 92,689 | 102,044 | 107,210 | 111,425 | 111,566 | 112,610 |
| Operating revenue |  |  | 11,975 | 12,580 | 12,918 | 15,196 | 17,449 | 20,031 | 22,996 | 26,396 | 25,796 | 26,746 |
| Net debt to operating revenue |  |  | 285% | 364% | 485% | 509% | 531% | 509% | 466% | 422% | 432% | 421% |

| Projected water services debt headroom (FFO) | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Water services FFO covenant (LGFA) | 9.0% | 9.0% | 9.0% | 9.0% | 9.0% | 9.0% | 9.0% | 9.0% | 9.0% | 9.0% |
| Free funds from operations (LGFA) ($m) | 1.5 | 1.5 | 2.7 | 3.1 | 2.9 | 5.6 | 8.8 | 11.1 | 11.2 | 11.3 |
| Net debt ($m) | 34.1 | 45.8 | 62.7 | 77.3 | 92.7 | 102.0 | 107.2 | 111.4 | 111.6 | 112.6 |
| Debt headroom to FFO covenant ($000s) | (17.8) | (28.9) | (33.2) | (42.7) | (61.0) | (40.1) | (8.9) | 12.4 | 12.4 | 12.5 |

Financial strategy and debt repayment

The WSCCO will arrange borrowings through the LGFA, supported by a Council guarantee or uncalled capital, with the final security arrangements and financial covenants to be agreed between the participating Councils and the LGFA. In doing so, the expectation is the water organisation will be required to comply with two key LGFA financial covenants:

- FFO-to-debt ratio: The ratio of FFO- to-debt must remain above 9%. This metric incorporates 50% of Development Contribution revenues in the FFO calculation, based on LGFA guidance.

- Interest coverage ratio (ICR): The ICR must be maintained above 1.5x, based on LGFA covenants.

Overall, the WSCCO achieves 10% FFO-to-debt by FY32. This approach has been tested with the LGFA, who have indicated that this is within their expectations and guidance on transitioning to a new capital structure.

Financial projections for SWDC’s components of the WSCCO indicate that both covenants will be met over the planning horizon, targeting a 10% FFO-to-debt ratio against the LGFA covenant of 9% and an interest coverage ratio above the 1.5x covenant. SWDC is anticipated to take four years to meet the 10% target (by FY32), however this is consistent with LGFA expectations and guidance issued to Councils in April 2025. 9% FFO-to-debt is achieved in FY32 as well.

As part of its broader financial governance, the Council will continue to adhere to its Treasury Management Policy, which sets a whole-of-Council borrowing limit of 175% net debt to revenue during the transition period. The transfer of water services to the WSCCO is expected to improve Council’s position against this benchmark, creating additional headroom for future non-water investments. Further information is outlined in Part D.

The WSCCO will utilise debt financing for long-lived capital expenditure, such as infrastructure upgrades and compliance-driven projects. Short-term liquidity needs may also be met through borrowing; however, operating costs will be funded through water revenues. This approach supports intergenerational equity and aligns with sound financial management principles. While the WSCCO’s forecasts are structured to show debt aligned with investment needs, rather than explicitly modelling principal repayments, the debt strategy assumes the use of FFO as the primary mechanism for managing debt over time.

In practice, this means the WSCCO will treat its debt portfolio as a flexible facility to support ongoing investment, while using excess operational cashflows to manage debt within overall LGFA covenant limits and shareholder expectations. The focus will be on maintaining liquidity, servicing interest costs comfortably, and ensuring that debt levels remain aligned with long-term revenue capacity, infrastructure need, and intergenerational equity. By maintaining debt within its borrowing limits and targeting FFO, the WSO can manage its debt exposure without prematurely constraining its investment programme or placing undue burden on current ratepayers.

Comprehensive treasury and financing policies will be developed as part of the transition as part of the financial and commercial workstream.  This will include policies for managing liquidity and interest rate risks, and arrangements for transactional banking, working capital and loan facilities.

Internal borrowing

SWDC does not employ any internal borrowing arrangements and does not expect to do so prior to the transition to the WSCCO.  Any internal borrowing would be recorded and managed through Council’s financial systems to ensure full compliance with ringfencing requirements. This includes clear separation of water service finances from other council activities and regular reporting to maintain transparency.

Attribution of debt related to water services

Historically, SWDC has adopted a project-specific borrowing methodology, ensuring that debt is directly attributable to the activities it funds. This approach has provided clarity and transparency in financial management, particularly for water services. During earlier rounds of water reform, this methodology was reviewed and endorsed by DIA, confirming its appropriateness for ringfencing and accountability purposes. As at 30 June 2024, the net debt attributable to water services was $22.4 million.

Insurance arrangements

Currently, SWDC purchases the following insurance cover for water services - machinery breakdown, environmental liability, and material damage.  Above-ground assets are insured at 100% replacement value and underground assets are insured at 40%, with the remaining risk covered by central government disaster recovery provisions. Asset insurance valuations are conducted biennially, with adjustments made for demolition costs and inflation to ensure accurate coverage levels. Delegations and reporting on insurance are the responsibility of the Chief Executive and CFO respectively.

South Wairarapa District Council’s standard infrastructure financial and insurance valuations are conducted biennially, with the next scheduled revaluation in 2026. In preparation, Council has committed to engaging additional engineering assessments, with a particular focus on the condition of treatment plants. To ensure asset values are accurate and up to date at the point of transition, an out-of-cycle revaluation is planned for 2027. This approach will support a robust and transparent transfer of assets to the new entity.

Following transition, the WSCCO will be the asset-owning entity and will therefore be responsible for holding appropriate insurance policies for water services assets, conducting valuations, and developing risk and insurance management policies. The WSCCO will need some new insurances not currently held by Councils e.g., Directors’ and Officers’ liability cover. WSCCO insurance requirements will be developed through the financial and commercial transition workstream.

# Part D: Financial sustainability assessment

Note for reader

Part A confirms the financial sustainability of the WSCCO by 30 June 2028. Given the decision to adopt cost-to-serve pricing, this Part D section refers to the financial sustainability of SWDC within the WSCCO. Financial statements included as Part E provide the detail for SWDC financial sustainability and Part F provides the detail to support the statements regarding the WSCCO’s financial sustainability.

Revenue projections are based on revenue required to meet the Council’s investment plans as set out in latest LTP, with a transition to a WSO in FY28 for water services. Additional operating costs are included for the WSCCO to ensure adequate allowance for overheads, financing costs, and additional overheads associated with a WSO (e.g. Board, management and audit costs).  A copy of the underlying assumptions can be found in Appendix 2.

## D1: Confirmation of financially sustainable delivery of water services

This Part D confirms that SWDC, within the WSCCO, achieves the financially sustainable delivery of water services by 30 June 2028, assuming LGFA acceptance of the proposed transition period to meet the targeted 10% FFO to debt ratio.

Revenue sufficiency

SWDC (from FY28) is projected to generate sufficient revenue to meet the full cost of water services delivery, including operating expenditure, asset renewals, and debt servicing. This is underpinned by a shift to a WSCCO with a target capital structure generating sufficient revenues over the forecast period.

Operating surpluses (including depreciation) over the 10-year period are forecast at $13.4m, with deficits expected until FY30 when a return to surplus is expected. Note these deficits are accounting, not cash, deficits and are the result of the inclusion of depreciation funding.  However, the WSCCO will not fund depreciation from revenue as the Council does now; instead it will use debt funding to more equitably spread the costs of investment over a longer time period. Strong cashflow surpluses over the period are forecast at $104m, underpinned by price increases, to fund required investment and meet the FFO-to-debt covenant.

SWDC average water charges per connection are forecast to increase from around $3,000 in FY25 to around $6,605 in FY34 (in nominal terms) (or $5,170 in real terms), which is forecast to represent around 4.8% of median household income in the district.  This is an acknowledged affordability challenge that will require management – however, SWDC is not financially sustainable on a standalone basis and prices in a WSCCO model are less than they would be under an alternative in-house model.

Investment sufficiency

The WSDP includes $150.5m in forecast capital investment over the 10-year period (this programme value reflects the adjusted cost based on the independent review undertaken by the Council). This programme includes:

- Renewals to maintain existing levels of service and asset reliability.

- Upgrades to achieve compliance with drinking water standards and to improve network resilience.

- Growth-related projects to service projected increases in demand.

SWDC requires substantial infrastructure upgrades to meet drinking water, wastewater, and stormwater performance expectations. These investments are front-loaded, with critical work needed in the early years to address regulatory compliance, consent conditions, and service reliability.

The proposed investment meets the investment sufficiency test and is fully funded by forecast revenues and access to finance. The projects in the proposed programme have been determined and prioritised by Wellington Water to meet compliance and levels of service requirements. Projected growth requirements come towards the end of the programme and the requirements for investment to meet these projections has also been incorporated by Wellington Water as the entity responsible for operating the Council’s water assets.

The cost and structure of the programme have been independently reviewed by Morrison Low, providing assurance that the investment is both reasonable and sufficient. Their review supports the conclusion that the programme is financially sound and aligned with best practice.

Financing sufficiency

Over the WSDP period, over $150.5m of capital investment is forecast, with approximately $78.5m of this expected to be debt funded, with total debt reaching around $112.6m in FY34. Borrowing by the WSCCO, once established, will be undertaken through the LGFA and guaranteed by the participating Councils while:

- Targeting or maintaining an FFO-to-debt ratio of 10%, compared to the LGFA covenant of 9%.

- Maintaining an interest coverage ratio above the 1.5x covenant.

SWDC’s water services will meet the targeted 10% FFO to debt ratio by FY32 and the ICR requirement from transition.

The transition to the 10% target has been phased to smooth the required price increases for the community, which are required due to the Council’s starting debt position and capital programme over the WSDP period. Financial covenants are achieved from FY32 as presented in Part D and Parts E of this plan.

LGFA has reviewed the WSCCO’s and SWDC’s financial position and has confirmed they would support the WSCCO and SWDC through this transition period. The LGFA noted that it would look at the WSCCO as a whole, and that a transition period of up to 5-years would generally be acceptable.

Actions to achieve financially sustainable delivery of water services

SWDC cannot achieve financially sustainable delivery of water services on a standalone basis – it has consulted with the community and chose to join the other Wairarapa and Tararua Partner Councils to form a WSCCO. This decision has benefits for SWDC (as well as the other Partner Councils) which are discussed in Part A of this plan.

Even within a WSCCO model, due to the ring-fencing of water services, each council faces a unique transition path to financial sustainability, with SWDC experiencing the most challenging transition. For SWDC, modelling shows that financial sustainability targets can be met through phased revenue increases. These increases are necessary to support capital investment, meet service delivery standards, and comply with borrowing covenants and financial sustainability requirements.

The modelling underpinning this plan is based on the SWDC’s existing investment programmes as set out in the LTP, with a reduction in the water services capital programme of 45%, following independent advice (see Appendix 4).  The WSCCO will have choices about how it manages the programme and may undertake an early assessment of the phasing and priorities of works to manage costs, achieve efficiencies through bundling of work, or to better reflect a regional view of necessary investment. Given SWDC’s affordability challenge, this plan proposes a reassessment of that part of the programme to manage costs for the community and to determine whether there is work that is not compliance or core renewal related that could be reprioritised or rephased over a longer period to spread costs more evenly between current and future customers.

Risks to achieving financially sustainable water services

SWDC has a particular challenge to achieve financially sustainable water services given the combination of ageing, town-specific infrastructure, low population density, existing debt levels, large necessary capital programme and resulting high per-connection investment requirements.

In the short term (years 1 to five of the WSDP), SWDC requires significant capital investment, with resulting higher debt levels, and higher customer pricing. In the following years, capital expenditure will stabilise, improved asset condition will reduce operating costs and enhance service reliability, operational efficiencies of the regional model will be accruing, and revenue requirements will stabilise.

- Capital investment requirements – SWDC requires substantial infrastructure upgrades to meet drinking water, wastewater, and stormwater to comply with performance expectations. These investments are front-loaded, with critical work needed in the early years to address regulatory compliance, consent conditions, and service reliability. The district’s fragmented infrastructure—separate treatment plants and networks for each town—combined with a small customer base, creates a high cost-to-serve and places pressure on cash flow, borrowing capacity, and financial ratios. SWDC is proactively taking control of its capital investment programme ahead of transition. The Council is independently assessing the investment required to meet regulatory and growth needs, informed by updated growth studies, evolving regional council consent requirements, national regulatory changes, and independent expert advice in order to determine opportunities to manage costs.

- Price differences across Councils – Partner Councils have agreed not to harmonise water pricing during the initial nine-year period. For SWDC, this means that water prices will continue to reflect the district’s high infrastructure investment needs. While price increases are expected, they will be lower than if SWDC were to operate water services independently, due to the WSCCO’s ability to spread financial impacts and manage debt more effectively.

- Financial targets – until FY32, the SWDC (and consequently WSCCO) FFO to debt ratio is below the 10% targeted; however this slower phasing to manage community price increases has been discussed with the LGFA who are supportive of the arrangement.

- Revenue tools – the WSCCO will have access to a broader and more flexible set of revenue tools than Councils do currently. This flexibility enhances its ability to achieve revenue sufficiency while managing affordability and equity across different customer groups. The WSCCO will be able to consider how best to use volumetric charging, differentiated pricing, and targeted cost recovery to manage through a period of significant early investment (particularly for SWDC) and maintain longer-term sustainable financial metrics.

There are several other risks to financially sustainable services, which are common across the four Partner Councils:

- Cost escalation - actual costs, particularly for large projects, may exceed estimates. Factors contributing to this include rising construction costs, increased material and labour prices, and changes in project scope due to unforeseen asset conditions.

- Inflation and interest rate volatility - Higher-than-forecast inflation or adverse interest rate movements may increase the cost of borrowing, placing upward pressure on water charges. Rapid rate increases or extended high-rate environments could affect financial sustainability and constrain future capital investment or lead to price increases.

- Revenue constraints and affordability - projected price paths are designed to balance cost recovery with community affordability. However, sustained increases in charges may encounter public resistance, particularly among fixed-income households. Any delays or political adjustments to planned price increases could create funding shortfalls.

- Regulatory shocks - new or revised drinking water, wastewater, or stormwater regulations could trigger additional unplanned investment. More stringent compliance measures introduced within the forecast period could impact both operating costs and capital priorities.

- Supply chain constraints - availability of skilled staff, contractors, engineers, and materials could impact the Council’s and WSO’s ability to deliver the capital programme on time. This has already been observed during past weather and pandemic events. Delays can lead to cost inflation and deferment of service improvements.

- Incomplete or evolving asset data - investment decisions are based on the best available asset condition data, but gaps or outdated information could lead to misalignment between investment timing and actual asset needs. This could result in inefficient allocation of capital or emergency spending.

- Transition and governance risks - establishment of a new WSO involves changes in governance, systems, and accountability. Any delays or misalignment in these transitions, particularly around financial systems or staffing, could temporarily affect delivery capacity or financial controls.

- Climate change and resilience – climate change and natural disaster risk (e.g., earthquake) poses increasing risks to water services through more frequent extreme weather events, rising sea levels, and changing rainfall patterns. These impacts can damage assets, raise costs, and disrupt service delivery. Building resilience into planning and asset management will help avoid unplanned costs and protect service reliability.

## D2: Financial sustainability assessment - revenue sufficiency

SWDC Figure 1: Water services revenue and expenses

Average projected charges for water services

SWDC Table 17: Average projected charges for water services

| Average charge per connection including GST |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Average drinking water bill (including GST) |  |  | 1,578 | 1,644 | 1,760 | 1,884 | 2,142 | 2,136 | 2,253 | 2,299 | 2,309 | 2,329 |
| Average wastewater bill (including GST) |  |  | 1,172 | 1,400 | 1,519 | 1,945 | 2,225 | 2,824 | 3,347 | 3,993 | 3,713 | 3,827 |
| Average stormwater bill (including GST) |  |  | 250 | 167 | 168 | 174 | 185 | 193 | 250 | 346 | 413 | 449 |
| Average charge per connection including GST |  |  | 3,000 | 3,211 | 3,447 | 4,003 | 4,551 | 5,152 | 5,850 | 6,637 | 6,435 | 6,605 |
| Projected increase |  |  | 26.2% | 7.0% | 7.4% | 16.1% | 13.7% | 13.2% | 13.5% | 13.5% | -3.1% | 2.6% |
| Projected number of connections |  |  | 4,148 | 4,194 | 4,236 | 4,278 | 4,321 | 4,364 | 4,408 | 4,452 | 4,496 | 4,542 |
| Projected median household income |  |  | 102,233 | 105,607 | 109,303 | 113,129 | 117,088 | 121,069 | 125,185 | 129,442 | 133,843 | 138,393 |
| Water services charges as % of household income |  |  | 2.9% | 3.0% | 3.2% | 3.5% | 3.9% | 4.3% | 4.7% | 5.1% | 4.8% | 4.8% |

Projected operating surpluses/(deficits) for water services

Operating surpluses over the 10-year period are forecast at $13.4m. SWDC has an operating deficit in years 1 and 2 of WSCCO (FY28 and FY29) and returns to surplus in FY30, within increasing surpluses over the period. Surpluses generated are expected to be retained within the WSCCO to manage prices, accelerate investment or reduce reliance on borrowing. These early years deficits are accounting, not cash, deficits and reflect the incorporation of depreciation – but the WSCCO will not fund deprecation from cash as the Council does now. SWDC within the WSCCO generates strong operating cashflow surpluses over the period of $104m.

SWDC Table 18: Projected operating surpluses/(deficits) for water services

| Operating surplus ratio |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Operating surplus/(deficit) excluding capital revenues |  |  | (1,238) | (1,201) | (519) | (348) | (1,338) | 962 | 3,308 | 5,100 | 4,384 | 4,276 | 13,386 |
| Total operating revenue |  |  | 11,975 | 12,580 | 12,918 | 15,196 | 17,449 | 20,031 | 22,996 | 26,396 | 25,796 | 26,746 | 192,084 |
| Operating surplus ratio |  |  | (10.3%) | (9.5%) | (4.0%) | (2.3%) | (7.7%) | 4.8% | 14.4% | 19.3% | 17.0% | 16.0% | 7.0% |

Projected operating cash surpluses for water services

SWDC Table 19: Projected operating cash surpluses for water services

| Operating cash ratio |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Operating surplus/(deficit) + depreciation + interest costs - capital revenue |  |  | 2,203 | 2,853 | 4,687 | 7,071 | 7,711 | 11,189 | 14,929 | 17,539 | 17,709 | 17,873 | 103,764 |
| Total operating revenue |  |  | 11,975 | 12,580 | 12,918 | 15,196 | 17,449 | 20,031 | 22,996 | 26,396 | 25,796 | 26,746 | 192,084 |
| Operating cash ratio |  |  | 18.4% | 22.7% | 36.3% | 46.5% | 44.2% | 55.9% | 64.9% | 66.4% | 68.7% | 66.8% | 54.0% |

## D3: Financial sustainability assessment - investment sufficiency

Figure 2 an investment programme with significant investment:

- Asset replacement

- Service level improvements

- Growth-related demand

The proposed investment is intended to meet current service levels, comply with regulatory standards, and support future growth. Using depreciation as a proxy for available funding from existing asset values in the early years, total investment exceeds depreciation, indicating a need for additional funding through revenue or financing. By the later years of the plan, depreciation exceeds renewals investment, suggesting a potential surplus in funding capacity for asset replacement.

Growth investment is critical for South Wairarapa, particularly in Greytown and Martinborough, where temporary suspensions on new network connections are currently preventing further development (and this investment is planned in years 2 to 6 of the WSDP period). This constraint not only limits housing and business expansion but also restricts the ability to collect financial contributions from developers—funds that are essential for upgrading and expanding network capacity. Without these contributions, the district faces a vicious cycle: insufficient infrastructure limits growth, and limited growth restricts the funding needed to improve infrastructure.

SWDC Figure 2: Water services investment requirements

Renewals requirements for water services

The proposed renewals investment plan has been developed in alignment with SWDC’s Infrastructure Strategy and asset management planning. In the early years of the plan (FY2024/25 to FY2026/27), capital expenditure on renewals significantly exceeds depreciation, resulting in a positive asset sustainability ratio. This reflects a deliberate strategy to address the aging condition of the network and reduce the backlog of deferred renewals, ensuring critical assets are replaced or refurbished to maintain service levels and regulatory compliance.

From FY2027/28 onward, the asset sustainability ratio turns negative, indicating that renewals investment falls below projected depreciation. This trend is not necessarily a sign of underinvestment but reflects a shift in focus (to levels of service and growth investment) following the initial surge in renewal activity. It is also influenced by the revised capital programme, which was adjusted downwards by 45% following an independent assurance review of initial budgeted programme cost structures. That review found conservative margins and contingencies in previous estimates, allowing SWDC to recalibrate its investment while still meeting infrastructure needs.

While the lower ratio in later years suggests a slower pace of renewal relative to asset aging, this is considered appropriate given the front-loaded investment and the expected improvement in asset condition. SWDC and the WSCCO will continue to monitor asset performance and adjust renewal planning as new information becomes available, ensuring long-term sustainability and alignment with lifecycle asset management principles.

SWDC Table 20: Renewal requirements for water services

| Asset sustainability ratio |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Capital expenditure on renewals |  |  | 5,807 | 6,415 | 5,034 | 1,934 | 1,890 | 4,652 | 4,993 | 5,339 | 5,327 | 5,762 | 47,154 |
| Depreciation |  |  | 2,490 | 2,524 | 2,970 | 3,265 | 3,993 | 4,413 | 5,340 | 5,842 | 6,572 | 6,785 | 44,194 |
| Asset sustainability ratio |  |  | 133.2% | 154.2% | 69.5% | (40.7%) | (52.7%) | 5.4% | (6.5%) | (8.6%) | (19.0%) | (15.1%) | 6.7% |

Total required water services investment

The levels of investment have been refined following an independent assurance review of the capital programme’s cost structures, which identified that early design processes had applied conservative margins and contingencies. As a result, SWDC has adjusted its capital investment programme downward by approximately 45%, and these revised costs have been incorporated into the financial modelling underpinning this WSDP. SWDC is actively taking ownership of its capital investment programme in the lead-up to transition. We are independently reviewing the investment required to meet consent conditions, regulatory obligations, and future growth, drawing on new and emerging information. This includes updated growth projections, evolving regional council requirements, changes in national regulation, and independent expert advice—beyond that provided for budgeting —to ensure our investment decisions are robust, future-focused, and tailored to the district’s specific needs.

SWDC Table 21: Total water services investment

| Asset investment ratio |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Capital expenditure |  |  | 13,315 | 13,488 | 19,708 | 16,674 | 18,443 | 15,130 | 14,214 | 15,557 | 11,498 | 12,504 | 150,530 |
| Depreciation |  |  | 2,490 | 2,524 | 2,970 | 3,265 | 3,993 | 4,413 | 5,340 | 5,842 | 6,572 | 6,785 | 44,194 |
| Asset investment ratio |  |  | 434.7% | 434.4% | 563.6% | 410.7% | 361.9% | 242.9% | 166.2% | 166.3% | 75.0% | 84.3% | 240.6% |

Average remaining useful life of network assets

The increased focus on renewals in the early years of SWDC’s investment plan reflects the aging condition of the district’s network assets. While this targeted investment is expected to improve the serviceability and reliability of critical infrastructure, the overall asset consumption ratio is projected to decline over the 10-year period. This indicates that, despite increased renewals, the network’s book value is decreasing relative to its replacement value—highlighting the scale of aging infrastructure and the need for sustained investment beyond FY2033/34. SWDC’s Infrastructure Strategy approach supports ongoing renewal planning to ensure long-term asset replacement needs are met and service levels maintained.

SWDC Table 22: Average remaining useful life of network assets

| Asset consumption ratio |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Book value of infrastructure assets |  |  | 140,888 | 151,852 | 175,655 | 189,064 | 213,085 | 223,802 | 243,548 | 253,262 | 270,490 | 276,210 |
| Total estimated replacement value of infrastructure assets |  |  | 164,313 | 177,801 | 205,782 | 222,455 | 252,160 | 267,290 | 294,487 | 310,044 | 336,603 | 349,108 |
| Asset consumption ratio |  |  | 85.7% | 85.4% | 85.4% | 85.0% | 84.5% | 83.7% | 82.7% | 81.7% | 80.4% | 79.1% |

## D4: Financial sustainability assessment - financing sufficiency

SWDC Figure 3: Water services borrowings against limits

Council borrowing against limits

SWDC cannot sustainably retain its water services as Council borrowing limits are significantly exceeded through the full WSDP period. SWDC can only meet financial sustainability requirements by shifting to a WSCCO structure with the other Partner Councils. Even within the WSCCO, SWDC has a challenging transition to sustainability, as evidenced by the projected water borrowings path and the price impacts for the community.

Projected borrowings for water services and borrowing headroom/(shortfall)

The profile of borrowings aligns with the timing of investment requirements, as operating expenses (including interest and depreciation) increase in step with capital investment needs. The projected net debt to operating revenue narrows significantly in FY26 and FY27 and exceeds borrowing limits in the short term of WSCCO operations (FY28-FY30), reflecting the upfront investment required to meet regulatory standards, maintain service levels and support growth. However, borrowing returns to within limits from FY31 onwards (under a debt to revenue assessment) and to within FFO to debt target from FY32, as operating revenues grow and capital pressures ease.

Importantly, SWDC has recently undertaken an independent assurance review of the programme’s costs structures. This review concluded that early estimates included conservative margins and contingencies, and as a result, SWDC has reduced its capital investment programme by approximately 45%. These revised costs have been incorporated into the financial modelling, improving projected debt levels and increasing borrowing headroom in the outer years of the plan.

While the reassessment of the programme has improved borrowing position and affordability, risks remain—particularly in the early years where borrowing headroom is minimal or limits exceeded. This limits flexibility to respond to unforeseen events or cost escalations. To mitigate these risks, SWDC will continue to refine its capital programme as new information becomes available. This includes updated growth forecasts, evolving regulatory requirements, and independent infrastructure advice as the individual components of the programme design are refined. This adaptive approach ensures that investment decisions remain fit-for-purpose and financially sustainable.

SWDC Table 23: Projected borrowings for water services

| Net debt to operating revenue |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total net debt (gross debt less cash) |  |  | 34,072 | 45,837 | 62,694 | 77,301 | 92,689 | 102,044 | 107,210 | 111,425 | 111,566 | 112,610 |
| Operating revenue |  |  | 11,975 | 12,580 | 12,918 | 15,196 | 17,449 | 20,031 | 22,996 | 26,396 | 25,796 | 26,746 |
| Net debt to operating revenue |  |  | 285% | 364% | 485% | 509% | 531% | 509% | 466% | 422% | 432% | 421% |

SWDC Table 24: Projected borrowing headroom/(shortfall) for water services (by debt to revenue and FFO to debt)

| Borrowings headroom/(shortfall) against limit |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Operating revenue |  |  | 11,975 | 12,580 | 12,918 | 15,196 | 17,449 | 20,031 | 22,996 | 26,396 | 25,796 | 26,746 |
| Debt to revenue limit |  |  | 500% | 500% | 500% | 500% | 500% | 500% | 500% | 500% | 500% | 500% |
| Maximum allowable net debt |  |  | 59,875 | 62,901 | 64,590 | 75,982 | 87,245 | 100,154 | 114,981 | 131,982 | 128,981 | 133,730 |
| Total net debt |  |  | 34,072 | 45,837 | 62,694 | 77,301 | 92,689 | 102,044 | 107,210 | 111,425 | 111,566 | 112,610 |
| Borrowing headroom/ (shortfall) against limit |  |  | 25,803 | 17,064 | 1,896 | (1,319) | (5,444) | (1,890) | 7,771 | 20,557 | 17,415 | 21,120 |

| Projected water services debt headroom (FFO) | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Water services FFO covenant (LGFA) | 9.0% | 9.0% | 9.0% | 9.0% | 9.0% | 9.0% | 9.0% | 9.0% | 9.0% | 9.0% |
| Free funds from operations (LGFA) ($m) | 1.5 | 1.5 | 2.7 | 3.1 | 2.9 | 5.6 | 8.8 | 11.1 | 11.2 | 11.3 |
| Net debt ($m) | 34.1 | 45.8 | 62.7 | 77.3 | 92.7 | 102.0 | 107.2 | 111.4 | 111.6 | 112.6 |
| Debt headroom to FFO covenant ($000s) | (17.8) | (28.9) | (33.2) | (42.7) | (61.0) | (40.1) | (8.9) | 12.4 | 12.4 | 12.5 |

Free funds from operations

The WSCCO will borrow from the LGFA, guaranteed by the participating Councils (with the form of the guarantee to be agreed through transition), under the following limits:

- Targeting or maintaining an FFO-to-debt ratio of 10%, compared to the LGFA covenant of 9%.

- Maintaining an interest coverage ratio above the 1.5x covenant.

SWDC within the WSCCO will meet the targeted 10% FFO to debt ratio by FY32 and the ICR requirement from transition.  The transition to the 10% target has been phased to smooth the required price increases for the community, which are required due to the Council’s starting debt position and capital programme over the WSDP period. LGFA has reviewed the WSCCO’s and SWDC’s financial position and has confirmed they would support the WSCCO and SWDC through this transition period.

SWDC Table 25: Free funds from operations

| Free funds from operations (FFO) to debt ratio |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total net debt |  |  | 34,072 | 45,837 | 62,694 | 77,301 | 92,689 | 102,044 | 107,210 | 111,425 | 111,566 | 112,610 |
| Funds from operations |  |  | 1,460 | 1,523 | 2,651 | 3,116 | 2,855 | 5,574 | 8,847 | 11,142 | 11,157 | 11,261 |
| FFO to debt ratio |  |  | 4.3% | 3.3% | 4.2% | 4.0% | 3.1% | 5.5% | 8.3% | 10.0% | 10.0% | 10.0% |

# Part E: Projected financial statements for water services

SWDC Table 26: Funding impact statement – water services

| Funding impact statement ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sources of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |
| General rates |  |  | 87 | 58 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Targeted rates |  |  | 10,843 | 11,815 | 12,819 | 15,157 | 17,409 | 19,991 | 22,957 | 26,357 | 25,757 | 26,706 |
| Subsidies and grants for operating purposes |  |  | 1,000 | 542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Local authorities fuel tax, fines, infringement fees and other receipts |  |  | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Fees and charges |  |  | 45 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |
| Total operating funding |  |  | 11,975 | 12,580 | 12,918 | 15,196 | 17,449 | 20,031 | 22,996 | 26,396 | 25,796 | 26,746 |
| Applications of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Payments to staff and suppliers |  |  | 8,754 | 8,746 | 7,233 | 7,268 | 8,882 | 7,959 | 7,194 | 7,976 | 7,211 | 7,993 |
| Finance costs |  |  | 951 | 1,530 | 2,236 | 4,154 | 5,056 | 5,814 | 6,281 | 6,597 | 6,753 | 6,812 |
| Internal charges and overheads applied |  |  | 1,018 | 980 | 998 | 857 | 856 | 883 | 874 | 881 | 876 | 880 |
| Other operating funding applications |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of operating funding |  |  | 10,723 | 11,257 | 10,467 | 12,280 | 14,794 | 14,656 | 14,349 | 15,454 | 14,840 | 15,685 |
| Surplus/(deficit) of operating funding |  |  | 1,252 | 1,324 | 2,451 | 2,916 | 2,655 | 5,375 | 8,647 | 10,942 | 10,957 | 11,061 |
| Sources of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Subsidies and grants for capital expenditure |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Development and financial contributions |  |  | 416 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 |
| Increase/(decrease) in debt |  |  | 10,610 | 11,765 | 16,857 | 14,607 | 15,388 | 9,355 | 5,166 | 4,214 | 142 | 1,044 |
| Gross proceeds from sales of assets |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Other dedicated capital funding |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total sources of capital funding |  |  | 11,025 | 12,165 | 17,257 | 15,007 | 15,788 | 9,755 | 5,566 | 4,614 | 542 | 1,443 |
| Applications of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital expenditure - to meet additional demand |  |  | 0 | 993 | 2,984 | 5,225 | 3,300 | 2,199 | 0 | 0 | 0 | 0 |
| Capital expenditure - to improve levels of services |  |  | 7,507 | 6,080 | 11,690 | 9,514 | 13,253 | 8,278 | 9,221 | 10,218 | 6,172 | 6,742 |
| Capital expenditure - to replace existing assets |  |  | 5,807 | 6,415 | 5,034 | 1,934 | 1,890 | 4,652 | 4,993 | 5,339 | 5,327 | 5,762 |
| Increase/(decrease) in reserves |  |  | (1,037) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Increase/(decrease) in investments |  |  | 0 | 0 | 0 | 1,250 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of capital funding |  |  | 12,278 | 13,488 | 19,708 | 17,924 | 18,443 | 15,130 | 14,214 | 15,557 | 11,498 | 12,504 |
| Surplus/(deficit) of capital funding |  |  | (1,252) | (1,324) | (2,451) | (2,916) | (2,655) | (5,375) | (8,647) | (10,942) | (10,957) | (11,061) |
| Funding balance |  |  | (0) | 0 | 0 | 0 | (0) | 0 | 0 | 0 | 0 | 0 |

SWDC Table 27: Funding impact statement – drinking water

| Funding impact statement ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sources of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |
| General rates |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Targeted rates |  |  | 5,603 | 5,901 | 6,381 | 6,899 | 7,921 | 7,979 | 8,497 | 8,759 | 8,885 | 9,053 |
| Subsidies and grants for operating purposes |  |  | 800 | 542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Local authorities fuel tax, fines, infringement fees and other receipts |  |  | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Fees and charges |  |  | 11 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |
| Total operating funding |  |  | 6,414 | 6,578 | 6,391 | 6,909 | 7,931 | 7,989 | 8,508 | 8,769 | 8,895 | 9,063 |
| Applications of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Payments to staff and suppliers |  |  | 4,825 | 4,776 | 4,093 | 4,072 | 4,910 | 4,111 | 4,126 | 4,134 | 4,151 | 4,162 |
| Finance costs |  |  | 149 | 352 | 666 | 1,466 | 1,601 | 1,585 | 1,345 | 1,178 | 1,157 | 1,174 |
| Internal charges and overheads applied |  |  | 497 | 483 | 492 | 310 | 301 | 315 | 304 | 308 | 300 | 303 |
| Other operating funding applications |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of operating funding |  |  | 5,471 | 5,611 | 5,250 | 5,848 | 6,812 | 6,011 | 5,774 | 5,620 | 5,609 | 5,639 |
| Surplus/(deficit) of operating funding |  |  | 943 | 967 | 1,141 | 1,061 | 1,119 | 1,978 | 2,733 | 3,149 | 3,286 | 3,424 |
| Sources of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Subsidies and grants for capital expenditure |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Development and financial contributions |  |  | 178 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 |
| Increase/(decrease) in debt |  |  | 9,061 | 7,877 | 5,587 | 1,215 | 1,950 | 1,800 | 1,606 | 1,435 | 1,371 | 1,381 |
| Gross proceeds from sales of assets |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Other dedicated capital funding |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total sources of capital funding |  |  | 9,239 | 8,049 | 5,758 | 1,387 | 2,122 | 1,971 | 1,777 | 1,607 | 1,542 | 1,553 |
| Applications of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital expenditure - to meet additional demand |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Capital expenditure - to improve levels of services |  |  | 4,397 | 3,829 | 2,736 | 534 | 1,846 | 1,866 | 2,068 | 2,036 | 2,041 | 1,742 |
| Capital expenditure - to replace existing assets |  |  | 4,955 | 5,187 | 4,163 | 1,394 | 1,394 | 2,083 | 2,443 | 2,720 | 2,787 | 3,235 |
| Increase/(decrease) in reserves |  |  | 829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Increase/(decrease) in investments |  |  | 0 | 0 | 0 | 519 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of capital funding |  |  | 10,182 | 9,016 | 6,899 | 2,447 | 3,241 | 3,949 | 4,510 | 4,756 | 4,829 | 4,977 |
| Surplus/(deficit) of capital funding |  |  | (943) | (967) | (1,141) | (1,061) | (1,119) | (1,978) | (2,733) | (3,149) | (3,286) | (3,424) |
| Funding balance |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

SWDC Table 28: Funding impact statement – wastewater

| Funding impact statement ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sources of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |
| General rates |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Targeted rates |  |  | 4,461 | 5,389 | 5,903 | 7,637 | 8,821 | 11,310 | 13,537 | 16,313 | 15,322 | 15,952 |
| Subsidies and grants for operating purposes |  |  | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Local authorities fuel tax, fines, infringement fees and other receipts |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Fees and charges |  |  | 34 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 |
| Total operating funding |  |  | 4,695 | 5,418 | 5,932 | 7,667 | 8,850 | 11,339 | 13,567 | 16,342 | 15,351 | 15,981 |
| Applications of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Payments to staff and suppliers |  |  | 3,461 | 3,625 | 2,805 | 2,830 | 3,618 | 3,559 | 2,779 | 3,554 | 2,773 | 3,545 |
| Finance costs |  |  | 811 | 1,178 | 1,570 | 2,583 | 3,314 | 4,048 | 4,689 | 5,048 | 5,090 | 5,043 |
| Internal charges and overheads applied |  |  | 444 | 423 | 430 | 466 | 472 | 484 | 485 | 488 | 490 | 491 |
| Other operating funding applications |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of operating funding |  |  | 4,716 | 5,226 | 4,806 | 5,880 | 7,404 | 8,091 | 7,954 | 9,090 | 8,352 | 9,079 |
| Surplus/(deficit) of operating funding |  |  | (21) | 192 | 1,127 | 1,787 | 1,446 | 3,248 | 5,613 | 7,252 | 6,999 | 6,902 |
| Sources of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Subsidies and grants for capital expenditure |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Development and financial contributions |  |  | 238 | 229 | 229 | 229 | 229 | 229 | 229 | 229 | 229 | 229 |
| Increase/(decrease) in debt |  |  | 1,931 | 3,759 | 11,160 | 12,945 | 12,942 | 6,582 | 2,025 | 935 | (2,530) | (969) |
| Gross proceeds from sales of assets |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Other dedicated capital funding |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total sources of capital funding |  |  | 2,168 | 3,987 | 11,389 | 13,173 | 13,170 | 6,811 | 2,254 | 1,164 | (2,302) | (741) |
| Applications of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital expenditure - to meet additional demand |  |  | 0 | 993 | 2,984 | 5,225 | 3,300 | 2,199 | 0 | 0 | 0 | 0 |
| Capital expenditure - to improve levels of services |  |  | 3,110 | 2,251 | 8,954 | 8,870 | 11,021 | 5,478 | 5,503 | 5,983 | 2,344 | 3,819 |
| Capital expenditure - to replace existing assets |  |  | 646 | 936 | 577 | 378 | 295 | 2,382 | 2,364 | 2,433 | 2,353 | 2,342 |
| Increase/(decrease) in reserves |  |  | (1,609) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Increase/(decrease) in investments |  |  | 0 | 0 | 0 | 487 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of capital funding |  |  | 2,147 | 4,180 | 12,515 | 14,961 | 14,617 | 10,059 | 7,867 | 8,416 | 4,697 | 6,161 |
| Surplus/(deficit) of capital funding |  |  | 21 | (192) | (1,127) | (1,787) | (1,446) | (3,248) | (5,613) | (7,252) | (6,999) | (6,902) |
| Funding balance |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

SWDC Table 29: Funding impact statement – stormwater

| Funding impact statement ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sources of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |
| General rates |  |  | 87 | 58 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Targeted rates |  |  | 779 | 526 | 535 | 621 | 668 | 702 | 922 | 1,285 | 1,550 | 1,702 |
| Subsidies and grants for operating purposes |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Local authorities fuel tax, fines, infringement fees and other receipts |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Fees and charges |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total operating funding |  |  | 866 | 584 | 595 | 621 | 668 | 702 | 922 | 1,285 | 1,550 | 1,702 |
| Applications of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Payments to staff and suppliers |  |  | 468 | 346 | 335 | 366 | 355 | 289 | 289 | 288 | 287 | 286 |
| Finance costs |  |  | (9) | 0 | 0 | 105 | 140 | 181 | 247 | 370 | 505 | 595 |
| Internal charges and overheads applied |  |  | 77 | 75 | 76 | 81 | 82 | 84 | 85 | 85 | 86 | 86 |
| Other operating funding applications |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of operating funding |  |  | 535 | 420 | 412 | 553 | 578 | 554 | 621 | 743 | 878 | 967 |
| Surplus/(deficit) of operating funding |  |  | 331 | 164 | 183 | 68 | 90 | 148 | 301 | 541 | 672 | 735 |
| Sources of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Subsidies and grants for capital expenditure |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Development and financial contributions |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Increase/(decrease) in debt |  |  | (382) | 129 | 110 | 447 | 496 | 974 | 1,535 | 1,844 | 1,301 | 632 |
| Gross proceeds from sales of assets |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Other dedicated capital funding |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total sources of capital funding |  |  | (382) | 129 | 110 | 447 | 496 | 974 | 1,535 | 1,844 | 1,301 | 632 |
| Applications of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital expenditure - to meet additional demand |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Capital expenditure - to improve levels of services |  |  | 0 | 0 | 0 | 110 | 385 | 935 | 1,649 | 2,199 | 1,786 | 1,181 |
| Capital expenditure - to replace existing assets |  |  | 206 | 293 | 293 | 162 | 201 | 187 | 187 | 186 | 186 | 186 |
| Increase/(decrease) in reserves |  |  | (257) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Increase/(decrease) in investments |  |  | 0 | 0 | 0 | 243 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of capital funding |  |  | (51) | 293 | 293 | 516 | 586 | 1,122 | 1,836 | 2,385 | 1,972 | 1,366 |
| Surplus/(deficit) of capital funding |  |  | (331) | (164) | (183) | (68) | (90) | (148) | (301) | (541) | (672) | (735) |
| Funding balance |  |  | (0) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

SWDC Table 30: Projected statement of comprehensive revenue and expenses – water services

| Statement of comprehensive revenue and expense ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Operating revenue |  |  | 11,975 | 12,580 | 12,918 | 15,196 | 17,449 | 20,031 | 22,996 | 26,396 | 25,796 | 26,746 |
| Other revenue |  |  | 416 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 |
| Total revenue |  |  | 12,391 | 12,980 | 13,318 | 15,596 | 17,849 | 20,431 | 23,396 | 26,796 | 26,196 | 27,146 |
| Operating expenses |  |  | 8,754 | 8,746 | 7,233 | 7,268 | 8,882 | 7,959 | 7,194 | 7,976 | 7,211 | 7,993 |
| Finance costs |  |  | 951 | 1,530 | 2,236 | 4,154 | 5,056 | 5,814 | 6,281 | 6,597 | 6,753 | 6,812 |
| Overheads and support costs |  |  | 1,018 | 980 | 998 | 857 | 856 | 883 | 874 | 881 | 876 | 880 |
| Depreciation & amortisation |  |  | 2,490 | 2,524 | 2,970 | 3,265 | 3,993 | 4,413 | 5,340 | 5,842 | 6,572 | 6,785 |
| Total expenses |  |  | 13,213 | 13,781 | 13,437 | 15,545 | 18,787 | 19,069 | 19,688 | 21,296 | 21,412 | 22,470 |
| Net surplus / (deficit) |  |  | (822) | (801) | (119) | 51 | (938) | 1,362 | 3,708 | 5,500 | 4,784 | 4,676 |
| Revaluation of infrastructure assets |  |  | 3,543 | 0 | 7,065 | 0 | 9,571 | 0 | 10,871 | 0 | 12,302 | 0 |
| Total comprehensive income |  |  | 2,721 | (801) | 6,946 | 51 | 8,634 | 1,362 | 14,579 | 5,500 | 17,087 | 4,676 |
| Cash surplus / (deficit) from operations (excl depreciation) |  |  | 1,668 | 1,723 | 2,851 | 3,316 | 3,055 | 5,774 | 9,047 | 11,342 | 11,357 | 11,461 |

SWDC Table 31: projected statement of comprehensive revenue and expenses – drinking water

| Statement of comprehensive revenue and expense ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Operating revenue |  |  | 6,414 | 6,578 | 6,391 | 6,909 | 7,931 | 7,989 | 8,508 | 8,769 | 8,895 | 9,063 |
| Other revenue |  |  | 178 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 |
| Total revenue |  |  | 6,592 | 6,749 | 6,562 | 7,080 | 8,102 | 8,161 | 8,679 | 8,941 | 9,066 | 9,235 |
| Operating expenses |  |  | 4,825 | 4,776 | 4,093 | 4,072 | 4,910 | 4,111 | 4,126 | 4,134 | 4,151 | 4,162 |
| Finance costs |  |  | 149 | 352 | 666 | 1,466 | 1,601 | 1,585 | 1,345 | 1,178 | 1,157 | 1,174 |
| Overheads and support costs |  |  | 497 | 483 | 492 | 310 | 301 | 315 | 304 | 308 | 300 | 303 |
| Depreciation & amortisation |  |  | 1,310 | 1,486 | 1,744 | 1,813 | 2,024 | 2,091 | 2,348 | 2,423 | 2,656 | 2,730 |
| Total expenses |  |  | 6,781 | 7,097 | 6,994 | 7,661 | 8,836 | 8,102 | 8,122 | 8,043 | 8,264 | 8,369 |
| Net surplus / (deficit) |  |  | (189) | (348) | (432) | (581) | (734) | 58 | 557 | 897 | 802 | 865 |
| Revaluation of infrastructure assets |  |  | 1,376 | 0 | 3,075 | 0 | 3,768 | 0 | 3,948 | 0 | 4,358 | 0 |
| Total comprehensive income |  |  | 1,186 | (348) | 2,642 | (581) | 3,034 | 58 | 4,505 | 897 | 5,160 | 865 |
| Cash surplus / (deficit) from operations (excl depreciation) |  |  | 1,121 | 1,138 | 1,312 | 1,232 | 1,290 | 2,150 | 2,905 | 3,320 | 3,458 | 3,596 |

SWDC Table 32: projected statement of comprehensive revenue and expenses – wastewater

| Statement of comprehensive revenue and expense ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Operating revenue |  |  | 4,695 | 5,418 | 5,932 | 7,667 | 8,850 | 11,339 | 13,567 | 16,342 | 15,351 | 15,981 |
| Other revenue |  |  | 238 | 229 | 229 | 229 | 229 | 229 | 229 | 229 | 229 | 229 |
| Total revenue |  |  | 4,933 | 5,647 | 6,161 | 7,895 | 9,079 | 11,568 | 13,795 | 16,571 | 15,580 | 16,210 |
| Operating expenses |  |  | 3,461 | 3,625 | 2,805 | 2,830 | 3,618 | 3,559 | 2,779 | 3,554 | 2,773 | 3,545 |
| Finance costs |  |  | 811 | 1,178 | 1,570 | 2,583 | 3,314 | 4,048 | 4,689 | 5,048 | 5,090 | 5,043 |
| Overheads and support costs |  |  | 444 | 423 | 430 | 466 | 472 | 484 | 485 | 488 | 490 | 491 |
| Depreciation & amortisation |  |  | 850 | 874 | 1,042 | 1,269 | 1,763 | 2,106 | 2,733 | 3,117 | 3,538 | 3,629 |
| Total expenses |  |  | 5,566 | 6,100 | 5,848 | 7,148 | 9,167 | 10,196 | 10,686 | 12,207 | 11,890 | 12,709 |
| Net surplus / (deficit) |  |  | (633) | (453) | 313 | 747 | (88) | 1,371 | 3,109 | 4,363 | 3,690 | 3,501 |
| Revaluation of infrastructure assets |  |  | 1,417 | 0 | 2,709 | 0 | 4,334 | 0 | 5,380 | 0 | 6,148 | 0 |
| Total comprehensive income |  |  | 783 | (453) | 3,022 | 747 | 4,246 | 1,371 | 8,489 | 4,363 | 9,838 | 3,501 |
| Cash surplus / (deficit) from operations (excl depreciation) |  |  | 217 | 421 | 1,355 | 2,016 | 1,675 | 3,477 | 5,842 | 7,480 | 7,227 | 7,130 |

SWDC Table 33: projected statement of comprehensive revenue and expenses – stormwater

| Statement of comprehensive revenue and expense ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Operating revenue |  |  | 866 | 584 | 595 | 621 | 668 | 702 | 922 | 1,285 | 1,550 | 1,702 |
| Other revenue |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total revenue |  |  | 866 | 584 | 595 | 621 | 668 | 702 | 922 | 1,285 | 1,550 | 1,702 |
| Operating expenses |  |  | 468 | 346 | 335 | 366 | 355 | 289 | 289 | 288 | 287 | 286 |
| Finance costs |  |  | (9) | 0 | 0 | 105 | 140 | 181 | 247 | 370 | 505 | 595 |
| Overheads and support costs |  |  | 77 | 75 | 76 | 81 | 82 | 84 | 85 | 85 | 86 | 86 |
| Depreciation & amortisation |  |  | 330 | 164 | 183 | 183 | 206 | 216 | 259 | 302 | 379 | 425 |
| Total expenses |  |  | 865 | 584 | 595 | 736 | 783 | 770 | 880 | 1,045 | 1,257 | 1,392 |
| Net surplus / (deficit) |  |  | 1 | 0 | 0 | (115) | (116) | (68) | 41 | 239 | 293 | 309 |
| Revaluation of infrastructure assets |  |  | 750 | 0 | 1,282 | 0 | 1,470 | 0 | 1,544 | 0 | 1,797 | 0 |
| Total comprehensive income |  |  | 751 | 0 | 1,282 | (115) | 1,354 | (68) | 1,586 | 239 | 2,090 | 309 |
| Cash surplus / (deficit) from operations (excl depreciation) |  |  | 331 | 164 | 183 | 68 | 90 | 148 | 301 | 541 | 672 | 735 |

SWDC Table 34: projected statement of cashflows – water services

| Statement of cashflows ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cashflows from operating activities |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash surplus / (deficit) from operations |  |  | 1,668 | 1,723 | 2,851 | 3,316 | 3,055 | 5,774 | 9,047 | 11,342 | 11,357 | 11,461 |
| [other items] |  |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from operating activities |  |  | 1,668 | 1,723 | 2,851 | 3,316 | 3,055 | 5,774 | 9,047 | 11,342 | 11,357 | 11,461 |
| Cashflows from investment activities |  |  |  |  |  |  |  |  |  |  |  |  |
| [other items] |  |  | 0 | 0 | 0 | (1,250) | 0 | 0 | 0 | 0 | 0 | 0 |
| Capital expenditure |  |  | (13,315) | (13,488) | (19,708) | (16,674) | (18,443) | (15,130) | (14,214) | (15,557) | (11,498) | (12,504) |
| Net cashflows from investment activities |  |  | (13,315) | (13,488) | (19,708) | (17,924) | (18,443) | (15,130) | (14,214) | (15,557) | (11,498) | (12,504) |
| Cashflows from financing activities |  |  |  |  |  |  |  |  |  |  |  |  |
| New borrowings |  |  | 11,646 | 11,765 | 16,857 | 14,607 | 15,388 | 9,355 | 5,166 | 4,214 | 142 | 1,044 |
| Repayment of borrowings |  |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from financing activities |  |  | 11,646 | 11,765 | 16,857 | 14,607 | 15,388 | 9,355 | 5,166 | 4,214 | 142 | 1,044 |
| Net increase/(decrease) in cash and cash equivalents |  |  | (0) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | (0) |
| Cash and cash equivalents at beginning of year |  |  | 0 | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) |
| Cash and cash equivalents at end of year |  |  | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) |

SWDC Table 35: projected statement of cashflows – drinking water

| Statement of cashflows ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cashflows from operating activities |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash surplus / (deficit) from operations |  |  | 1,121 | 1,138 | 1,312 | 1,232 | 1,290 | 2,150 | 2,905 | 3,320 | 3,458 | 3,596 |
| [other items] |  |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from operating activities |  |  | 1,121 | 1,138 | 1,312 | 1,232 | 1,290 | 2,150 | 2,905 | 3,320 | 3,458 | 3,596 |
| Cashflows from investment activities |  |  |  |  |  |  |  |  |  |  |  |  |
| [other items] |  |  |  |  |  | (519) |  |  |  |  |  |  |
| Capital expenditure |  |  | (9,352) | (9,016) | (6,899) | (1,928) | (3,241) | (3,949) | (4,510) | (4,756) | (4,829) | (4,977) |
| Net cashflows from investment activities |  |  | (9,352) | (9,016) | (6,899) | (2,447) | (3,241) | (3,949) | (4,510) | (4,756) | (4,829) | (4,977) |
| Cashflows from financing activities |  |  |  |  |  |  |  |  |  |  |  |  |
| New borrowings |  |  | 8,232 | 7,877 | 5,587 | 1,215 | 1,950 | 1,800 | 1,606 | 1,435 | 1,371 | 1,381 |
| Repayment of borrowings |  |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from financing activities |  |  | 8,232 | 7,877 | 5,587 | 1,215 | 1,950 | 1,800 | 1,606 | 1,435 | 1,371 | 1,381 |
| Net increase/(decrease) in cash and cash equivalents |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Cash and cash equivalents at beginning of year |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Cash and cash equivalents at end of year |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

SWDC Table 36: projected statement of cashflows – wastewater

| Statement of cashflows ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cashflows from operating activities |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash surplus / (deficit) from operations |  |  | 217 | 421 | 1,355 | 2,016 | 1,675 | 3,477 | 5,842 | 7,480 | 7,227 | 7,130 |
| [other items] |  |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from operating activities |  |  | 217 | 421 | 1,355 | 2,016 | 1,675 | 3,477 | 5,842 | 7,480 | 7,227 | 7,130 |
| Cashflows from investment activities |  |  |  |  |  |  |  |  |  |  |  |  |
| [other items] |  |  |  |  |  | (487) |  |  |  |  |  |  |
| Capital expenditure |  |  | (3,756) | (4,180) | (12,515) | (14,473) | (14,617) | (10,059) | (7,867) | (8,416) | (4,697) | (6,161) |
| Net cashflows from investment activities |  |  | (3,756) | (4,180) | (12,515) | (14,961) | (14,617) | (10,059) | (7,867) | (8,416) | (4,697) | (6,161) |
| Cashflows from financing activities |  |  |  |  |  |  |  |  |  |  |  |  |
| New borrowings |  |  | 3,540 | 3,759 | 11,160 | 12,945 | 12,942 | 6,582 | 2,025 | 935 | (2,530) | (969) |
| Repayment of borrowings |  |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from financing activities |  |  | 3,540 | 3,759 | 11,160 | 12,945 | 12,942 | 6,582 | 2,025 | 935 | (2,530) | (969) |
| Net increase/(decrease) in cash and cash equivalents |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Cash and cash equivalents at beginning of year |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Cash and cash equivalents at end of year |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

SWDC Table 37: projected statement of cashflows – stormwater

| Statement of cashflows ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cashflows from operating activities |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash surplus / (deficit) from operations |  |  | 331 | 164 | 183 | 68 | 90 | 148 | 301 | 541 | 672 | 735 |
| [other items] |  |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from operating activities |  |  | 331 | 164 | 183 | 68 | 90 | 148 | 301 | 541 | 672 | 735 |
| Cashflows from investment activities |  |  |  |  |  |  |  |  |  |  |  |  |
| [other items] |  |  | 0 | 0 | 0 | (243) | 0 | 0 | 0 | 0 | 0 | 0 |
| Capital expenditure |  |  | (206) | (293) | (293) | (272) | (586) | (1,122) | (1,836) | (2,385) | (1,972) | (1,366) |
| Net cashflows from investment activities |  |  | (206) | (293) | (293) | (516) | (586) | (1,122) | (1,836) | (2,385) | (1,972) | (1,366) |
| Cashflows from financing activities |  |  |  |  |  |  |  |  |  |  |  |  |
| New borrowings |  |  | (125) | 129 | 110 | 447 | 496 | 974 | 1,535 | 1,844 | 1,301 | 632 |
| Repayment of borrowings |  |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from financing activities |  |  | (125) | 129 | 110 | 447 | 496 | 974 | 1,535 | 1,844 | 1,301 | 632 |
| Net increase/(decrease) in cash and cash equivalents |  |  | (0) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Cash and cash equivalents at beginning of year |  |  | 0 | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) |
| Cash and cash equivalents at end of year |  |  | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) |

SWDC Table 38: projected statement of financial position – water services

| Statement of financial position ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Assets |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash and cash equivalents |  |  | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) |
| Other current assets |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Infrastructure assets |  |  | 140,888 | 151,852 | 175,655 | 189,064 | 213,085 | 223,802 | 243,548 | 253,262 | 270,490 | 276,210 |
| Other non-current assets |  |  | 0 | 0 | 0 | 1,250 | 1,250 | 1,250 | 1,250 | 1,250 | 1,250 | 1,250 |
| Total assets |  |  | 140,888 | 151,852 | 175,655 | 190,314 | 214,335 | 225,052 | 244,797 | 254,512 | 271,740 | 277,459 |
| Liabilities |  |  |  |  |  |  |  |  |  |  |  |  |
| Borrowings - current portion |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Other current liabilities |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Borrowings - non-current portion |  |  | 34,072 | 45,836 | 62,693 | 77,301 | 92,688 | 102,044 | 107,210 | 111,424 | 111,566 | 112,610 |
| Other non-current liabilities |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total liabilities |  |  | 34,072 | 45,836 | 62,693 | 77,301 | 92,688 | 102,044 | 107,210 | 111,424 | 111,566 | 112,610 |
| Net assets |  |  | 106,816 | 106,015 | 112,961 | 113,013 | 121,646 | 123,008 | 137,587 | 143,087 | 160,174 | 164,850 |
| Equity |  |  |  |  |  |  |  |  |  |  |  |  |
| Revaluation reserve |  |  | 3,543 | 3,543 | 10,608 | 10,608 | 20,179 | 20,179 | 31,051 | 31,051 | 43,353 | 43,353 |
| Other reserves |  |  | 103,273 | 102,473 | 102,353 | 102,405 | 101,467 | 102,829 | 106,537 | 112,037 | 116,821 | 121,497 |
| Total equity |  |  | 106,816 | 106,015 | 112,961 | 113,013 | 121,646 | 123,008 | 137,587 | 143,087 | 160,174 | 164,850 |

SWDC Table 39: projected statement of financial position – drinking water

| Statement of financial position ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Assets |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash and cash equivalents |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Other current assets |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure assets |  |  | 58,550 | 66,079 | 74,309 | 74,424 | 79,408 | 81,266 | 87,376 | 89,709 | 96,239 | 98,486 |
| Other non-current assets |  |  | 0 | 0 | 0 | 519 | 519 | 519 | 519 | 519 | 519 | 519 |
| Total assets |  |  | 58,550 | 66,079 | 74,309 | 74,943 | 79,927 | 81,785 | 87,896 | 90,228 | 96,759 | 99,005 |
| Liabilities |  |  |  |  |  |  |  |  |  |  |  |  |
| Borrowings - current portion |  |  |  |  |  |  |  |  |  |  |  |  |
| Other current liabilities |  |  |  |  |  |  |  |  |  |  |  |  |
| Borrowings - non-current portion |  |  | 10,877 | 18,754 | 24,341 | 25,556 | 27,507 | 29,306 | 30,912 | 32,347 | 33,718 | 35,100 |
| Other non-current liabilities |  |  |  |  |  |  |  |  |  |  |  |  |
| Total liabilities |  |  | 10,877 | 18,754 | 24,341 | 25,556 | 27,507 | 29,306 | 30,912 | 32,347 | 33,718 | 35,100 |
| Net assets |  |  | 47,673 | 47,325 | 49,968 | 49,387 | 52,421 | 52,479 | 56,984 | 57,881 | 63,040 | 63,906 |
| Equity |  |  |  |  |  |  |  |  |  |  |  |  |
| Revaluation reserve |  |  | 1,376 | 1,376 | 4,450 | 4,450 | 8,218 | 8,218 | 12,165 | 12,165 | 16,523 | 16,523 |
| Other reserves |  |  | 46,297 | 45,950 | 45,518 | 44,937 | 44,203 | 44,261 | 44,818 | 45,715 | 46,517 | 47,383 |
| Total equity |  |  | 47,673 | 47,325 | 49,968 | 49,387 | 52,421 | 52,479 | 56,984 | 57,881 | 63,040 | 63,906 |

SWDC Table 40: projected statement of financial position – wastewater

| Statement of financial position ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Assets |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash and cash equivalents |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Other current assets |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure assets |  |  | 54,915 | 58,221 | 72,403 | 85,608 | 102,795 | 110,748 | 121,262 | 126,561 | 133,869 | 136,400 |
| Other non-current assets |  |  | 0 | 0 | 0 | 487 | 487 | 487 | 487 | 487 | 487 | 487 |
| Total assets |  |  | 54,915 | 58,221 | 72,403 | 86,095 | 103,282 | 111,236 | 121,750 | 127,048 | 134,356 | 136,888 |
| Liabilities |  |  |  |  |  |  |  |  |  |  |  |  |
| Borrowings - current portion |  |  |  |  |  |  |  |  |  |  |  |  |
| Other current liabilities |  |  |  |  |  |  |  |  |  |  |  |  |
| Borrowings - non-current portion |  |  | 23,315 | 27,073 | 38,234 | 51,178 | 64,120 | 70,702 | 72,727 | 73,663 | 71,132 | 70,163 |
| Other non-current liabilities |  |  |  |  |  |  |  |  |  |  |  |  |
| Total liabilities |  |  | 23,315 | 27,073 | 38,234 | 51,178 | 64,120 | 70,702 | 72,727 | 73,663 | 71,132 | 70,163 |
| Net assets |  |  | 31,601 | 31,148 | 34,169 | 34,916 | 39,162 | 40,533 | 49,022 | 53,386 | 63,223 | 66,725 |
| Equity |  |  |  |  |  |  |  |  |  |  |  |  |
| Revaluation reserve |  |  | 1,417 | 1,417 | 4,125 | 4,125 | 8,459 | 8,459 | 13,839 | 13,839 | 19,987 | 19,987 |
| Other reserves |  |  | 30,184 | 29,731 | 30,044 | 30,791 | 30,703 | 32,074 | 35,183 | 39,547 | 43,236 | 46,738 |
| Total equity |  |  | 31,601 | 31,148 | 34,169 | 34,916 | 39,162 | 40,533 | 49,022 | 53,386 | 63,223 | 66,725 |

SWDC Table 41: projected statement of financial position – stormwater

| Statement of financial position ($000) |  |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Assets |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash and cash equivalents |  |  | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) | (0) |
| Other current assets |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure assets |  |  | 27,423 | 27,551 | 28,943 | 29,032 | 30,882 | 31,788 | 34,909 | 36,992 | 40,382 | 41,323 |
| Other non-current assets |  |  | 0 | 0 | 0 | 243 | 243 | 243 | 243 | 243 | 243 | 243 |
| Total assets |  |  | 27,422 | 27,551 | 28,943 | 29,275 | 31,125 | 32,031 | 35,152 | 37,235 | 40,626 | 41,567 |
| Liabilities |  |  |  |  |  |  |  |  |  |  |  |  |
| Borrowings - current portion |  |  |  |  |  |  |  |  |  |  |  |  |
| Other current liabilities |  |  |  |  |  |  |  |  |  |  |  |  |
| Borrowings - non-current portion |  |  | (120) | 9 | 119 | 566 | 1,062 | 2,036 | 3,571 | 5,414 | 6,715 | 7,347 |
| Other non-current liabilities |  |  |  |  |  |  |  |  |  |  |  |  |
| Total liabilities |  |  | (120) | 9 | 119 | 566 | 1,062 | 2,036 | 3,571 | 5,414 | 6,715 | 7,347 |
| Net assets |  |  | 27,542 | 27,542 | 28,824 | 28,709 | 30,064 | 29,996 | 31,581 | 31,821 | 33,910 | 34,220 |
| Equity |  |  |  |  |  |  |  |  |  |  |  |  |
| Revaluation reserve |  |  | 750 | 750 | 2,032 | 2,032 | 3,502 | 3,502 | 5,046 | 5,046 | 6,843 | 6,843 |
| Other reserves |  |  | 26,792 | 26,792 | 26,792 | 26,677 | 26,562 | 26,494 | 26,535 | 26,775 | 27,067 | 27,377 |
| Total equity |  |  | 27,542 | 27,542 | 28,824 | 28,709 | 30,064 | 29,996 | 31,581 | 31,821 | 33,910 | 34,220 |

# Water Services Delivery Plan: additional information

## Significant capital projects

SWDC Table 42: drinking water projects

| Significant capital projects - drinking water | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Projects to meet additional demand |  |  |  |  |  |  |  |  |  |  |
| Total investment to meet additional demand | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Projects to improve levels of services |  |  |  |  |  |  |  |  |  |  |
| Greytown WTP upgrades stage 3 | 3,141 | 2,131 | 2,101 |  |  |  |  |  |  |  |
| Greytown WTP upgrades stage 2 | 104 |  |  |  |  |  |  |  |  |  |
| PW Tanker fill points | 52 |  |  |  | 28 | 55 | 275 | 275 | 275 | 0 |
| Waiohine WTP stage 3 upgrade | 1,047 |  | 1,632 |  |  |  |  |  |  |  |
| Fire fighting upgrades |  |  |  | 121 | 1,819 | 1,819 | 1,819 | 1,819 | 1,819 | 1,819 |
| WTP wellfeild security | 52 | 99 | 746 | 413 |  |  |  |  |  |  |
| Resource consent for Pirinoa water take - reconsenting |  | 79 | 99 |  |  |  |  |  |  |  |
| Total investment to improve levels of services | 4,396 | 2,309 | 4,578 | 534 | 1,847 | 1,874 | 2,094 | 2,094 | 2,094 | 1,819 |
| Projects to replace existing assets |  |  |  |  |  |  |  |  |  |  |
| FSTN water main renewals | 211 | 1,926 | 1,999 | 2,077 | 2,141 |  |  |  |  |  |
| Tauwhareniikau pipeline crossing | 3,485 | 2,047 |  |  |  |  |  |  |  |  |
| SWDC drinking water pipe renewals |  |  |  |  |  | 1,724 | 2,069 | 2,387 | 2,387 | 2,387 |
| Boar Bush PW trun main and resrvoir outlet | 52 | 149 | 1,492 |  |  |  |  |  |  |  |
| Annual recurring projects | 743 | 655 | 657 | 363 | 363 | 365 | 388 | 363 | 363 | 363 |
| consenting of water races (Moroa) |  | 248 | 149 |  |  |  |  |  |  |  |
| SWDC VHCA reservoir water quality renewals |  | 199 |  |  |  |  |  |  |  |  |
| Waiohine WTP filtration | 52 |  |  |  |  |  |  |  | 83 | 550 |
| SWDC VHCA reservoir water quality renewals | 157 |  |  |  |  |  |  |  |  |  |
| Total investment to replace existing assets | 4,700 | 5,224 | 4,297 | 2,440 | 2,504 | 2,089 | 2,457 | 2,750 | 2,833 | 3,300 |
| Total investment in drinking water assets | 9,096 | 7,533 | 8,875 | 2,974 | 4,351 | 3,963 | 4,551 | 4,844 | 4,927 | 5,119 |

SWDC Table 43: wastewater projects

| Significant capital projects - wastewater | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Projects to meet additional demand |  |  |  |  |  |  |  |  |  |  |
| MTB WWTP growth capacity upgrade |  | 496 | 1,492 | 1,650 | 1,650 | 1,100 |  |  |  |  |
| GTN WWTP growth capaicty upgrade |  | 496 | 1,492 | 1,650 | 1,650 | 1,100 |  |  |  |  |
| GTN Papawai road wastewater upgrade stage 2 |  |  |  | 1,925 |  |  |  |  |  |  |
| Total investment to meet additional demand | 0 | 992 | 2,984 | 5,225 | 3,300 | 2,200 | 0 | 0 | 0 | 0 |
| Projects to improve levels of services |  |  |  |  |  |  |  |  |  |  |
| MTB WWTP compliance upgrades - stage 2b winter storage |  |  |  |  |  |  | 275 | 550 | 1,100 | 3,300 |
| FSTN WWTP long-term consent stage 2 and major plant upgrade 2 |  |  |  |  |  |  |  |  | 275 | 550 |
| FSTN WWTP consent renewal | 1,256 |  |  |  |  |  |  |  |  |  |
| GTN WWTP compliance upgrades - stage 2a land irrigaiton | 806 | 1,072 | 3,482 | 2,200 | 2,200 | 2,200 | 1,760 | 715 | 440 |  |
| Construction works from consent - lake ferry |  |  |  |  | 110 | 440 | 825 | 825 | 550 |  |
| FSTN pressure wastewater system - stage 1 |  |  |  |  |  | 176 | 704 | 2,816 |  |  |
| MTB WWTP compliance upgrades - stage 2a land irrigiation |  | 596 | 3,979 | 1,730 | 2,665 | 2,665 | 1,950 | 1,100 |  |  |
| FSTN WWTP consent renewal and upgrades | 1,047 | 834 | 1,493 | 4,941 | 6,047 |  |  |  |  |  |
| Total investment to improve levels of services | 3,109 | 2,502 | 8,954 | 8,871 | 11,022 | 5,481 | 5,514 | 6,006 | 2,365 | 3,850 |
| Projects to replace existing assets |  |  |  |  |  |  |  |  |  |  |
| Annually recurring projects | 444 | 506 | 507 | 281 | 281 | 281 | 281 | 281 | 281 | 281 |
| Waterwater pipe renewals |  |  |  |  |  | 2,079 | 2,079 | 2,079 | 2,079 | 2,079 |
| Reconsenting lake ferry treatment plant | 202 | 50 | 50 |  |  |  |  |  |  |  |
| Total investment to replace existing assets | 646 | 556 | 557 | 281 | 281 | 2,360 | 2,360 | 2,360 | 2,360 | 2,360 |
| Total investment in wastewater assets | 3,755 | 4,050 | 12,495 | 14,377 | 14,603 | 10,041 | 7,874 | 8,366 | 4,725 | 6,210 |

SWDC Table 44: stormwater projects

| Significant capital projects - stormwater | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Projects to meet additional demand |  |  |  |  |  |  |  |  |  |  |
| Total investment to meet additional demand | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Projects to improve levels of services |  |  |  |  |  |  |  |  |  |  |
| Flooding improvements |  |  |  | 110 | 385 | 935 | 1,650 | 2,200 | 1,788 | 1,183 |
| Total investment to improve levels of services | 0 | 0 | 0 | 110 | 385 | 935 | 1,650 | 2,200 | 1,788 | 1,183 |
| Projects to replace existing assets |  |  |  |  |  |  |  |  |  |  |
| Annually recurring projects |  | 293 | 293 | 162 | 201 | 187 | 187 | 187 | 187 | 187 |
| Total investment to replace existing assets | 0 | 293 | 293 | 162 | 201 | 187 | 187 | 187 | 187 | 187 |
| Total investment in stormwater assets | 0 | 293 | 293 | 272 | 586 | 1,122 | 1,837 | 2,387 | 1,975 | 1,370 |

## Risks and assumptions

SWDC is in a unique position transitioning from Wellington Water Ltd as a shareholding council to the Wairarapa-Tararua WSCCO. In the interim, Council is actively taking ownership of its capital investment programme in the lead-up to transition.  We are independently reviewing the investment required to meet consent conditions, regulatory obligations, and future growth, drawing on new and emerging information. This includes growth projections, evolving regional council requirements, changes in national regulation, and independent expert advice. This work will be completed to ensure that our investment decisions are robust, future-focused, and tailored to the district’s specific needs.

As SWDC works through the hand-over information provided by Wellington Water Ltd, it is expected that it will be possible to make adjustments within the final five years of our capital programme regarding delivery timeframes of approximately $32m– with a view to improve pricing impacts where possible. However, our primary assumption is that future water service delivery for our community is contingent on the imminent requirement to address consenting and infrastructure upgrades (as outlined within this WSDP).

The following table summarises the key issues/constraints, risks and assumptions within the operation of water services delivery. Key issues and constraints are matters which have been addressed or considered within asset management planning and the programme outlined in this WSDP. Council’s Infrastructure Strategy 2024-2055 includes a priority to prepare for the future and improve the practices for managing here water assets, particularly data reliability. The approaches adopted for the 2024 Strategy set the foundations to improve the underlying asset data (bottom up).

SWDC Table 45: risks and assumptions

| Parameters | Drinking supply | Wastewater | Stormwater |
| --- | --- | --- | --- |
| Key Risks/Constraints - Future water service delivery - Network performance - Regulatory compliance - Delivery of Capital Programme - Organisational capacity - Long term issues e.g. providing for growth, climate change | - Source water capacity and supporting growth in the district - Managing growth - Regulatory change and compliance - Pipe renewals - Economic impacts were not quantified for the 2025 LTP. | - Wastewater (sewage treatment and disposal) - Inflow and Infiltration - Adapting to climate change and reducing emissions - Pipe renewals - Economic impacts were not quantified for the 2025 LTP. | - Stormwater management areas to facilitate growth - Management of overland flow paths - Economic impacts were not quantified for the 2025 LTP. |
| Significant assumptions - Future water service delivery - Network performance - Regulatory compliance - Delivery of Capital Programme - Organisational capacity - Long term issues e.g. providing for growth, climate change | Council will continue to implement strategies to manage leaks to an acceptable level as per the Infrastructure Strategy 2024-2055 The 2027 Infrastructure Strategy will include risks and consequences of economic impacts on infrastructure. | Bringing capital expenditure back in-house brings with it the following benefits: more cost control, cost efficiency, on-time delivery, local contractor delivery. It will also allow for programme optimisation leading into the new entity as part of the negotiations with the partner councils. The 2027 Infrastructure Strategy will include risks and consequences of economic impacts on infrastructure. | The Featherston Masterplan considered climate change factors. The implementation plan includes improvements to strengthen the resilience of stormwater infrastructure. The 2027 Infrastructure Strategy will include risks and consequences of economic impacts on infrastructure. |

# Part F: Wairarapa Tararua WSCCO combined financial summary

WSCCO Table 1: Funding impact statement – water services

| Funding impact statement ($000) |  | FY23/24 |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sources of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |  |
| General rates |  | 1,283 |  | 751 | 855 | 982 | 990 | 1,058 | 1,122 | 1,186 | 1,162 | 1,171 | 1,202 |
| Targeted rates |  | 36,869 |  | 42,816 | 48,131 | 53,282 | 60,080 | 66,096 | 73,004 | 77,416 | 81,525 | 81,617 | 82,784 |
| Subsidies and grants for operating purposes |  | 623 |  | 1,911 | 1,083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Local authorities fuel tax, fines, infringement fees and other receipts |  | 680 |  | 147 | 272 | 152 | 154 | 158 | 162 | 165 | 169 | 172 | 185 |
| Fees and charges |  | 2,012 |  | 2,303 | 2,047 | 1,938 | 1,988 | 2,039 | 2,088 | 2,136 | 2,184 | 2,231 | 2,278 |
| Total operating funding |  | 41,466 |  | 47,928 | 52,388 | 56,353 | 63,213 | 69,352 | 76,376 | 80,903 | 85,040 | 85,191 | 86,448 |
| Applications of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Payments to staff and suppliers |  | 19,232 |  | 21,693 | 21,845 | 19,934 | 21,533 | 23,468 | 22,854 | 22,414 | 23,342 | 22,802 | 23,839 |
| Finance costs |  | 4,556 |  | 5,279 | 5,786 | 7,354 | 14,772 | 17,150 | 18,520 | 19,349 | 19,919 | 20,168 | 20,255 |
| Internal charges and overheads applied |  | 5,690 |  | 7,105 | 7,533 | 7,650 | 7,630 | 7,839 | 8,105 | 8,207 | 8,427 | 8,642 | 8,766 |
| Other operating funding applications |  | 37 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of operating funding |  | 29,514 |  | 34,077 | 35,164 | 34,938 | 43,936 | 48,457 | 49,479 | 49,971 | 51,688 | 51,613 | 52,860 |
| Surplus/(deficit) of operating funding |  | 11,952 |  | 13,851 | 17,224 | 21,414 | 19,278 | 20,894 | 26,897 | 30,932 | 33,351 | 33,579 | 33,588 |
| Sources of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Subsidies and grants for capital expenditure |  | 3,098 |  | 1,770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Development and financial contributions |  | 1,243 |  | 835 | 825 | 830 | 834 | 837 | 838 | 840 | 842 | 844 | 846 |
| Increase/(decrease) in debt |  | 7,827 |  | 19,518 | 24,864 | 29,792 | 36,378 | 30,358 | 13,372 | 10,181 | 9,618 | 4,151 | 6,852 |
| Gross proceeds from sales of assets |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Other dedicated capital funding |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total sources of capital funding |  | 12,169 |  | 22,123 | 25,689 | 30,622 | 37,212 | 31,195 | 14,210 | 11,021 | 10,460 | 4,995 | 7,698 |
| Applications of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital expenditure - to meet additional demand |  | 5,037 |  | 1,070 | 6,622 | 4,341 | 7,802 | 4,485 | 4,488 | 1,255 | 1,993 | 344 | 351 |
| Capital expenditure - to improve levels of services |  | 13,151 |  | 11,421 | 15,880 | 25,977 | 25,395 | 26,831 | 12,016 | 13,071 | 13,587 | 7,754 | 9,519 |
| Capital expenditure - to replace existing assets |  | 18,123 |  | 29,033 | 30,722 | 27,124 | 30,567 | 21,734 | 25,575 | 30,247 | 24,078 | 28,610 | 24,662 |
| Increase/(decrease) in reserves |  | (9,866) |  | (5,550) | (10,310) | (5,406) | (12,274) | (961) | (971) | (2,620) | 4,155 | 1,866 | 6,754 |
| Increase/(decrease) in investments |  | 155 |  | 0 | 0 | 0 | 5,000 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of capital funding |  | 26,600 |  | 35,974 | 42,913 | 52,036 | 56,490 | 52,090 | 41,107 | 41,953 | 43,812 | 38,574 | 41,285 |
| Surplus/(deficit) of capital funding |  | (14,431) |  | (13,851) | (17,224) | (21,414) | (19,278) | (20,894) | (26,897) | (30,932) | (33,351) | (33,579) | (33,588) |
| Funding balance |  | (2,479) |  | (0) | (0) | 0 | (0) | 0 | 0 | 0 | 0 | 0 | 0 |

WSCCO Table 2: Funding impact statement – drinking water

| Funding impact statement ($000) |  | FY23/24 |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sources of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |  |
| General rates |  | 262 |  | 183 | 257 | 312 | 341 | 365 | 387 | 423 | 434 | 434 | 448 |
| Targeted rates |  | 16,157 |  | 18,677 | 21,050 | 22,978 | 26,077 | 30,452 | 33,241 | 34,646 | 35,055 | 35,463 | 35,745 |
| Subsidies and grants for operating purposes |  | 521 |  | 1,234 | 836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Local authorities fuel tax, fines, infringement fees and other receipts |  | 290 |  | 94 | 220 | 98 | 100 | 103 | 105 | 107 | 110 | 112 | 114 |
| Fees and charges |  | 699 |  | 610 | 658 | 511 | 525 | 539 | 553 | 566 | 579 | 592 | 605 |
| Total operating funding |  | 17,929 |  | 20,798 | 23,021 | 23,899 | 27,044 | 31,459 | 34,286 | 35,743 | 36,178 | 36,600 | 36,912 |
| Applications of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Payments to staff and suppliers |  | 9,366 |  | 11,050 | 11,492 | 10,311 | 11,061 | 12,052 | 11,367 | 11,571 | 11,641 | 11,758 | 11,907 |
| Finance costs |  | 1,152 |  | 1,384 | 1,626 | 2,401 | 5,902 | 6,731 | 6,883 | 6,663 | 6,482 | 6,330 | 6,248 |
| Internal charges and overheads applied |  | 2,788 |  | 3,041 | 3,279 | 3,284 | 3,155 | 3,237 | 3,351 | 3,387 | 3,482 | 3,569 | 3,623 |
| Other operating funding applications |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of operating funding |  | 13,307 |  | 15,475 | 16,397 | 15,996 | 20,117 | 22,019 | 21,601 | 21,622 | 21,605 | 21,657 | 21,778 |
| Surplus/(deficit) of operating funding |  | 4,623 |  | 5,323 | 6,624 | 7,903 | 6,927 | 9,440 | 12,685 | 14,121 | 14,573 | 14,943 | 15,134 |
| Sources of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Subsidies and grants for capital expenditure |  | 421 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Development and financial contributions |  | 280 |  | 306 | 302 | 305 | 307 | 309 | 310 | 311 | 313 | 314 | 316 |
| Increase/(decrease) in debt |  | 4,335 |  | 18,786 | 15,293 | 13,175 | 14,476 | 10,963 | 4,217 | 3,319 | 2,548 | 2,422 | 2,301 |
| Gross proceeds from sales of assets |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Other dedicated capital funding |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total sources of capital funding |  | 5,036 |  | 19,092 | 15,595 | 13,481 | 14,783 | 11,272 | 4,527 | 3,631 | 2,861 | 2,737 | 2,617 |
| Applications of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital expenditure - to meet additional demand |  | 1,069 |  | 532 | 3,004 | 556 | 2,022 | 609 | 1,688 | 631 | 1,749 | 92 | 94 |
| Capital expenditure - to improve levels of services |  | 2,363 |  | 6,425 | 6,993 | 10,868 | 9,713 | 8,947 | 4,905 | 5,305 | 2,762 | 2,872 | 2,492 |
| Capital expenditure - to replace existing assets |  | 8,594 |  | 20,228 | 20,006 | 14,660 | 18,225 | 11,041 | 12,449 | 16,583 | 11,737 | 15,614 | 12,022 |
| Increase/(decrease) in reserves |  | (1,855) |  | (2,769) | (7,784) | (4,700) | (10,232) | 115 | (1,829) | (4,768) | 1,185 | (900) | 3,141 |
| Increase/(decrease) in investments |  | (112) |  | 0 | 0 | 0 | 1,982 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of capital funding |  | 10,059 |  | 24,415 | 22,219 | 21,384 | 21,710 | 20,712 | 17,212 | 17,751 | 17,433 | 17,678 | 17,749 |
| Surplus/(deficit) of capital funding |  | (5,023) |  | (5,323) | (6,624) | (7,903) | (6,927) | (9,440) | (12,685) | (14,120) | (14,572) | (14,942) | (15,132) |
| Funding balance |  | (400) |  | 0 | 0 | 0 | (0) | 0 | 0 | 0 | 1 | 1 | 2 |

WSCCO Table 3: Funding impact statement – wastewater

| Funding impact statement ($000) |  | FY23/24 |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sources of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |  |
| General rates |  | 529 |  | 449 | 500 | 565 | 600 | 644 | 685 | 711 | 676 | 684 | 699 |
| Targeted rates |  | 18,831 |  | 21,085 | 23,830 | 26,685 | 30,310 | 31,777 | 35,694 | 38,274 | 41,465 | 40,744 | 41,442 |
| Subsidies and grants for operating purposes |  | 102 |  | 677 | 247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Local authorities fuel tax, fines, infringement fees and other receipts |  | 377 |  | 52 | 52 | 53 | 54 | 55 | 57 | 58 | 59 | 60 | 71 |
| Fees and charges |  | 1,311 |  | 1,691 | 1,387 | 1,424 | 1,461 | 1,497 | 1,532 | 1,568 | 1,602 | 1,637 | 1,670 |
| Total operating funding |  | 21,151 |  | 23,954 | 26,016 | 28,727 | 32,425 | 33,974 | 37,968 | 40,610 | 43,802 | 43,125 | 43,882 |
| Applications of operating funding |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Payments to staff and suppliers |  | 8,663 |  | 9,481 | 9,216 | 8,556 | 9,269 | 10,206 | 10,317 | 9,663 | 10,510 | 9,835 | 10,714 |
| Finance costs |  | 3,340 |  | 3,786 | 4,039 | 4,759 | 8,140 | 9,570 | 10,668 | 11,568 | 12,143 | 12,365 | 12,384 |
| Internal charges and overheads applied |  | 2,163 |  | 3,300 | 3,448 | 3,537 | 3,626 | 3,731 | 3,859 | 3,911 | 4,015 | 4,121 | 4,177 |
| Other operating funding applications |  | 37 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of operating funding |  | 14,203 |  | 16,567 | 16,703 | 16,852 | 21,034 | 23,507 | 24,844 | 25,142 | 26,668 | 26,320 | 27,274 |
| Surplus/(deficit) of operating funding |  | 6,947 |  | 7,387 | 9,313 | 11,875 | 11,391 | 10,466 | 13,124 | 15,469 | 17,134 | 16,805 | 16,608 |
| Sources of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Subsidies and grants for capital expenditure |  | 2,498 |  | 1,770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Development and financial contributions |  | 942 |  | 505 | 498 | 500 | 501 | 502 | 502 | 503 | 503 | 504 | 504 |
| Increase/(decrease) in debt |  | 4,107 |  | 905 | 8,082 | 15,325 | 20,532 | 18,312 | 6,977 | 4,524 | 4,420 | (725) | 2,126 |
| Gross proceeds from sales of assets |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Other dedicated capital funding |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total sources of capital funding |  | 7,547 |  | 3,180 | 8,579 | 15,824 | 21,032 | 18,814 | 7,479 | 5,027 | 4,923 | (222) | 2,629 |
| Applications of capital funding |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital expenditure - to meet additional demand |  | 2,514 |  | 281 | 2,921 | 3,517 | 5,780 | 3,877 | 2,800 | 624 | 244 | 252 | 256 |
| Capital expenditure - to improve levels of services |  | 10,788 |  | 4,997 | 7,799 | 13,995 | 14,946 | 17,028 | 5,694 | 5,624 | 8,626 | 3,095 | 5,846 |
| Capital expenditure - to replace existing assets |  | 9,071 |  | 7,861 | 9,437 | 9,628 | 10,420 | 8,723 | 11,054 | 11,781 | 10,460 | 11,061 | 10,662 |
| Increase/(decrease) in reserves |  | (7,224) |  | (2,572) | (2,263) | 559 | (992) | (348) | 1,055 | 2,465 | 2,727 | 2,175 | 2,472 |
| Increase/(decrease) in investments |  | 275 |  | 0 | 0 | 0 | 2,268 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of capital funding |  | 15,423 |  | 10,566 | 17,893 | 27,699 | 32,423 | 29,280 | 20,603 | 20,495 | 22,057 | 16,584 | 19,237 |
| Surplus/(deficit) of capital funding |  | (7,876) |  | (7,387) | (9,313) | (11,875) | (11,391) | (10,466) | (13,124) | (15,468) | (17,134) | (16,805) | (16,608) |
| Funding balance |  | (929) |  | 0 | (0) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

WSCCO Table 4: Funding impact statement – stormwater

| Funding impact statement ($000) |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sources of operating funding |  |  |  |  |  |  |  |  |  |  |  |
| General rates |  | 119 | 97 | 104 | 49 | 49 | 50 | 52 | 52 | 53 | 55 |
| Targeted rates |  | 3,055 | 3,250 | 3,619 | 3,694 | 3,868 | 4,069 | 4,496 | 5,006 | 5,410 | 5,596 |
| Subsidies and grants for operating purposes |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Local authorities fuel tax, fines, infringement fees and other receipts |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Fees and charges |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |
| Total operating funding |  | 3,177 | 3,350 | 3,726 | 3,745 | 3,919 | 4,121 | 4,550 | 5,060 | 5,466 | 5,654 |
| Applications of operating funding |  |  |  |  |  |  |  |  |  |  |  |
| Payments to staff and suppliers |  | 1,162 | 1,137 | 1,067 | 1,204 | 1,210 | 1,170 | 1,180 | 1,191 | 1,210 | 1,218 |
| Finance costs |  | 110 | 121 | 194 | 731 | 849 | 969 | 1,118 | 1,294 | 1,474 | 1,624 |
| Internal charges and overheads applied |  | 763 | 806 | 829 | 850 | 871 | 895 | 909 | 930 | 952 | 966 |
| Other operating funding applications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of operating funding |  | 2,035 | 2,063 | 2,090 | 2,785 | 2,930 | 3,033 | 3,207 | 3,415 | 3,635 | 3,807 |
| Surplus/(deficit) of operating funding |  | 1,141 | 1,287 | 1,636 | 960 | 988 | 1,088 | 1,343 | 1,645 | 1,830 | 1,846 |
| Sources of capital funding |  |  |  |  |  |  |  |  |  |  |  |
| Subsidies and grants for capital expenditure |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Development and financial contributions |  | 24 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 |
| Increase/(decrease) in debt |  | (173) | 1,490 | 1,292 | 1,371 | 1,083 | 2,178 | 2,337 | 2,650 | 2,455 | 2,426 |
| Gross proceeds from sales of assets |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Other dedicated capital funding |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total sources of capital funding |  | (149) | 1,515 | 1,317 | 1,397 | 1,109 | 2,204 | 2,363 | 2,676 | 2,481 | 2,452 |
| Applications of capital funding |  |  |  |  |  |  |  |  |  |  |  |
| Capital expenditure - to meet additional demand |  | 257 | 697 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Capital expenditure - to improve levels of services |  | 0 | 1,088 | 1,115 | 736 | 855 | 1,416 | 2,142 | 2,199 | 1,786 | 1,181 |
| Capital expenditure - to replace existing assets |  | 944 | 1,279 | 2,836 | 1,921 | 1,970 | 2,073 | 1,882 | 1,881 | 1,935 | 1,979 |
| Increase/(decrease) in reserves |  | (209) | (262) | (1,265) | (1,050) | (727) | (197) | (317) | 242 | 591 | 1,140 |
| Increase/(decrease) in investments |  | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total applications of capital funding |  | 993 | 2,802 | 2,954 | 2,357 | 2,098 | 3,292 | 3,707 | 4,322 | 4,312 | 4,300 |
| Surplus/(deficit) of capital funding |  | (1,142) | (1,287) | (1,636) | (960) | (988) | (1,088) | (1,343) | (1,646) | (1,832) | (1,848) |
| Funding balance |  | (0) | (0) | 0 | 0 | 0 | 0 | (1) | (1) | (1) | (2) |

WSCCO Table 5: Projected statement of comprehensive review and expenses – water services

| Statement of comprehensive revenue and expense ($000) |  | FY23/24 |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Operating revenue |  | 41,466 |  | 47,928 | 52,388 | 56,353 | 63,213 | 69,352 | 76,376 | 80,903 | 85,040 | 85,191 | 86,448 |
| Other revenue |  | 4,341 |  | 2,605 | 825 | 830 | 834 | 837 | 838 | 840 | 842 | 844 | 846 |
| Total revenue |  | 45,808 |  | 50,533 | 53,213 | 57,183 | 64,047 | 70,189 | 77,214 | 81,743 | 85,882 | 86,035 | 87,294 |
| Operating expenses |  | 19,269 |  | 21,693 | 21,845 | 19,934 | 21,533 | 23,468 | 22,854 | 22,414 | 23,342 | 22,802 | 23,839 |
| Finance costs |  | 4,556 |  | 5,279 | 5,786 | 7,354 | 14,772 | 17,150 | 18,520 | 19,349 | 19,919 | 20,168 | 20,255 |
| Overheads and support costs |  | 5,690 |  | 7,105 | 7,533 | 7,650 | 7,630 | 7,839 | 8,105 | 8,207 | 8,427 | 8,642 | 8,766 |
| Depreciation & amortisation |  | 0 |  | 16,563 | 17,166 | 19,298 | 20,118 | 21,732 | 23,448 | 24,753 | 25,798 | 27,276 | 27,729 |
| Total expenses |  | 29,514 |  | 50,640 | 52,330 | 54,236 | 64,053 | 70,189 | 72,926 | 74,723 | 77,487 | 78,889 | 80,589 |
| Net surplus / (deficit) |  | 16,293 |  | (107) | 883 | 2,947 | (6) | (1) | 4,287 | 7,020 | 8,395 | 7,147 | 6,705 |
| Revaluation of infrastructure assets |  | 0 |  | 8,561 | 16,219 | 16,765 | 17,685 | 22,196 | 19,414 | 24,416 | 20,139 | 27,074 | 21,223 |
| Total comprehensive income |  | 16,293 |  | 8,454 | 17,102 | 19,711 | 17,679 | 22,195 | 23,701 | 31,436 | 28,534 | 34,220 | 27,928 |
| Cash surplus / (deficit) from operations (excl depreciation) |  | 16,293 |  | 16,456 | 18,049 | 22,244 | 20,111 | 21,731 | 27,735 | 31,772 | 34,193 | 34,423 | 34,434 |

WSCCO Table 6: Projected statement of comprehensive review and expenses – drinking water

| Statement of comprehensive revenue and expense ($000) |  | FY23/24 |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Operating revenue |  | 17,929 |  | 20,798 | 23,021 | 23,899 | 27,044 | 31,459 | 34,286 | 35,743 | 36,178 | 36,600 | 36,912 |
| Other revenue |  | 701 |  | 306 | 302 | 305 | 307 | 309 | 310 | 311 | 313 | 314 | 316 |
| Total revenue |  | 18,630 |  | 21,104 | 23,324 | 24,204 | 27,351 | 31,768 | 34,597 | 36,054 | 36,491 | 36,915 | 37,228 |
| Operating expenses |  | 9,366 |  | 11,050 | 11,492 | 10,311 | 11,061 | 12,052 | 11,367 | 11,571 | 11,641 | 11,758 | 11,907 |
| Finance costs |  | 1,152 |  | 1,384 | 1,626 | 2,401 | 5,902 | 6,731 | 6,883 | 6,663 | 6,482 | 6,330 | 6,248 |
| Overheads and support costs |  | 2,788 |  | 3,041 | 3,279 | 3,284 | 3,155 | 3,237 | 3,351 | 3,387 | 3,482 | 3,569 | 3,623 |
| Depreciation & amortisation |  | 0 |  | 7,531 | 7,722 | 8,660 | 8,940 | 9,651 | 10,258 | 10,789 | 11,196 | 11,940 | 12,113 |
| Total expenses |  | 13,307 |  | 23,006 | 24,120 | 24,656 | 29,056 | 31,670 | 31,859 | 32,410 | 32,801 | 33,597 | 33,891 |
| Net surplus / (deficit) |  | 5,324 |  | (1,902) | (796) | (451) | (1,706) | 98 | 2,737 | 3,644 | 3,690 | 3,317 | 3,337 |
| Revaluation of infrastructure assets |  | 0 |  | 3,788 | 5,125 | 7,926 | 5,928 | 10,157 | 7,009 | 10,779 | 7,385 | 12,045 | 7,822 |
| Total comprehensive income |  | 5,324 |  | 1,886 | 4,329 | 7,475 | 4,222 | 10,255 | 9,746 | 14,423 | 11,076 | 15,362 | 11,159 |
| Cash surplus / (deficit) from operations (excl depreciation) |  | 5,324 |  | 5,629 | 6,927 | 8,209 | 7,234 | 9,749 | 12,995 | 14,432 | 14,886 | 15,257 | 15,450 |

WSCCO Table 7: Projected statement of comprehensive review and expenses – wastewater

| Statement of comprehensive revenue and expense ($000) |  | FY23/24 |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Operating revenue |  | 21,151 |  | 23,954 | 26,016 | 28,727 | 32,425 | 33,974 | 37,968 | 40,610 | 43,802 | 43,125 | 43,882 |
| Other revenue |  | 3,440 |  | 2,275 | 498 | 500 | 501 | 502 | 502 | 503 | 503 | 504 | 504 |
| Total revenue |  | 24,590 |  | 26,229 | 26,514 | 29,227 | 32,926 | 34,475 | 38,469 | 41,113 | 44,304 | 43,629 | 44,386 |
| Operating expenses |  | 8,700 |  | 9,481 | 9,216 | 8,556 | 9,269 | 10,206 | 10,317 | 9,663 | 10,510 | 9,835 | 10,714 |
| Finance costs |  | 3,340 |  | 3,786 | 4,039 | 4,759 | 8,140 | 9,570 | 10,668 | 11,568 | 12,143 | 12,365 | 12,384 |
| Overheads and support costs |  | 2,163 |  | 3,300 | 3,448 | 3,537 | 3,626 | 3,731 | 3,859 | 3,911 | 4,015 | 4,121 | 4,177 |
| Depreciation & amortisation |  | 0 |  | 7,463 | 7,990 | 9,045 | 9,516 | 10,323 | 11,317 | 12,015 | 12,562 | 13,117 | 13,325 |
| Total expenses |  | 14,203 |  | 24,030 | 24,693 | 25,898 | 30,550 | 33,830 | 36,161 | 37,157 | 39,230 | 39,437 | 40,600 |
| Net surplus / (deficit) |  | 10,387 |  | 2,198 | 1,821 | 3,329 | 2,375 | 645 | 2,308 | 3,956 | 5,074 | 4,192 | 3,786 |
| Revaluation of infrastructure assets |  | 0 |  | 3,298 | 8,846 | 6,310 | 9,293 | 9,087 | 9,774 | 10,561 | 10,030 | 11,590 | 10,588 |
| Total comprehensive income |  | 10,387 |  | 5,497 | 10,666 | 9,639 | 11,668 | 9,732 | 12,082 | 14,517 | 15,104 | 15,782 | 14,374 |
| Cash surplus / (deficit) from operations (excl depreciation) |  | 10,387 |  | 9,661 | 9,811 | 12,374 | 11,891 | 10,968 | 13,626 | 15,971 | 17,636 | 17,309 | 17,111 |

WSCCO Table 8: Projected statement of comprehensive review and expenses – stormwater

| Statement of comprehensive revenue and expense ($000) |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Operating revenue |  | 3,177 | 3,350 | 3,726 | 3,745 | 3,919 | 4,121 | 4,550 | 5,060 | 5,466 | 5,654 |
| Other revenue |  | 24 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 |
| Total revenue |  | 3,201 | 3,375 | 3,751 | 3,771 | 3,945 | 4,147 | 4,576 | 5,086 | 5,492 | 5,680 |
| Operating expenses |  | 1,162 | 1,137 | 1,067 | 1,204 | 1,210 | 1,170 | 1,180 | 1,191 | 1,210 | 1,218 |
| Finance costs |  | 110 | 121 | 194 | 731 | 849 | 969 | 1,118 | 1,294 | 1,474 | 1,624 |
| Overheads and support costs |  | 763 | 806 | 829 | 850 | 871 | 895 | 909 | 930 | 952 | 966 |
| Depreciation & amortisation |  | 1,568 | 1,454 | 1,593 | 1,662 | 1,758 | 1,872 | 1,949 | 2,040 | 2,219 | 2,291 |
| Total expenses |  | 3,604 | 3,517 | 3,683 | 4,447 | 4,689 | 4,906 | 5,156 | 5,456 | 5,854 | 6,098 |
| Net surplus / (deficit) |  | (403) | (142) | 69 | (676) | (744) | (758) | (580) | (370) | (363) | (418) |
| Revaluation of infrastructure assets |  | 1,475 | 2,248 | 2,528 | 2,464 | 2,952 | 2,631 | 3,076 | 2,723 | 3,439 | 2,813 |
| Total comprehensive income |  | 1,072 | 2,106 | 2,597 | 1,788 | 2,208 | 1,872 | 2,496 | 2,354 | 3,076 | 2,395 |
| Cash surplus / (deficit) from operations (excl depreciation) |  | 1,165 | 1,312 | 1,661 | 986 | 1,014 | 1,114 | 1,369 | 1,671 | 1,856 | 1,872 |

WSCCO Table 9: Projected statement of cashflows – water services

| Statement of cashflows ($000) |  | FY23/24 |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cashflows from operating activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash surplus / (deficit) from operations |  | 16,293 |  | 16,456 | 18,049 | 22,244 | 20,111 | 21,731 | 27,735 | 31,772 | 34,193 | 34,423 | 34,434 |
| [other items] |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from operating activities |  | 16,293 |  | 16,456 | 18,049 | 22,244 | 20,111 | 21,731 | 27,735 | 31,772 | 34,193 | 34,423 | 34,434 |
| Cashflows from investment activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| [other items] |  | (155) |  | 0 | 0 | 0 | (5,000) | 0 | 0 | 0 | 0 | 0 | 0 |
| Capital expenditure |  | (36,311) |  | (41,524) | (53,223) | (57,442) | (63,763) | (53,050) | (42,078) | (44,573) | (39,657) | (36,708) | (34,532) |
| Net cashflows from investment activities |  | (36,466) |  | (41,524) | (53,223) | (57,442) | (68,763) | (53,050) | (42,078) | (44,573) | (39,657) | (36,708) | (34,532) |
| Cashflows from financing activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| New borrowings |  | 17,693 |  | 25,068 | 35,174 | 35,198 | 48,652 | 31,319 | 14,344 | 12,801 | 5,464 | 2,285 | 98 |
| Repayment of borrowings |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from financing activities |  | 17,693 |  | 25,068 | 35,174 | 35,198 | 48,652 | 31,319 | 14,344 | 12,801 | 5,464 | 2,285 | 98 |
| Net increase/(decrease) in cash and cash equivalents |  | (2,479) |  | (0) | (0) | 0 | (0) | 0 | 0 | 0 | 0 | 0 | 0 |
| Cash and cash equivalents at beginning of year |  | (12,789) |  | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) |
| Cash and cash equivalents at end of year |  | (15,268) |  | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) |

WSCCO Table 10: Projected statement of cashflows – drinking water

| Statement of cashflows ($000) |  | FY23/24 |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cashflows from operating activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash surplus / (deficit) from operations |  | 5,324 |  | 5,629 | 6,927 | 8,209 | 7,234 | 9,749 | 12,995 | 14,432 | 14,886 | 15,257 | 15,450 |
| [other items] |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from operating activities |  | 5,324 |  | 5,629 | 6,927 | 8,209 | 7,234 | 9,749 | 12,995 | 14,432 | 14,886 | 15,257 | 15,450 |
| Cashflows from investment activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| [other items] |  |  |  |  |  |  | (1,982) |  |  |  |  |  |  |
| Capital expenditure |  | (12,026) |  | (27,184) | (30,003) | (26,083) | (29,960) | (20,597) | (19,042) | (22,519) | (16,248) | (18,579) | (14,608) |
| Net cashflows from investment activities |  | (12,026) |  | (27,184) | (30,003) | (26,083) | (31,942) | (20,597) | (19,042) | (22,519) | (16,248) | (18,579) | (14,608) |
| Cashflows from financing activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| New borrowings |  | 6,190 |  | 21,555 | 23,077 | 17,875 | 24,708 | 10,848 | 6,046 | 8,087 | 1,363 | 3,323 | (841) |
| Repayment of borrowings |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from financing activities |  | 6,190 |  | 21,555 | 23,077 | 17,875 | 24,708 | 10,848 | 6,046 | 8,087 | 1,363 | 3,323 | (841) |
| Net increase/(decrease) in cash and cash equivalents |  | (512) |  | 0 | 0 | 0 | (0) | 0 | 0 | 0 | 1 | 1 | 2 |
| Cash and cash equivalents at beginning of year |  | 1,223 |  | 711 | 711 | 711 | 712 | 711 | 711 | 711 | 712 | 713 | 714 |
| Cash and cash equivalents at end of year |  | 711 |  | 711 | 711 | 712 | 711 | 711 | 711 | 712 | 713 | 714 | 716 |

WSCCO Table 11: Projected statement of cashflows – wastewater

| Statement of cashflows ($000) |  | FY23/24 |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cashflows from operating activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash surplus / (deficit) from operations |  | 10,387 |  | 9,661 | 9,811 | 12,374 | 11,891 | 10,968 | 13,626 | 15,971 | 17,636 | 17,309 | 17,111 |
| [other items] |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from operating activities |  | 10,387 |  | 9,661 | 9,811 | 12,374 | 11,891 | 10,968 | 13,626 | 15,971 | 17,636 | 17,309 | 17,111 |
| Cashflows from investment activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| [other items] |  |  |  |  |  |  | (2,268) |  |  |  |  |  |  |
| Capital expenditure |  | (22,372) |  | (13,139) | (20,156) | (27,140) | (31,146) | (29,628) | (19,548) | (18,030) | (19,330) | (14,408) | (16,765) |
| Net cashflows from investment activities |  | (22,372) |  | (13,139) | (20,156) | (27,140) | (33,414) | (29,628) | (19,548) | (18,030) | (19,330) | (14,408) | (16,765) |
| Cashflows from financing activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| New borrowings |  | 4,107 |  | 3,477 | 10,345 | 14,766 | 21,523 | 18,660 | 5,922 | 2,059 | 1,693 | (2,901) | (347) |
| Repayment of borrowings |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from financing activities |  | 4,107 |  | 3,477 | 10,345 | 14,766 | 21,523 | 18,660 | 5,922 | 2,059 | 1,693 | (2,901) | (347) |
| Net increase/(decrease) in cash and cash equivalents |  | (7,878) |  | 0 | (0) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Cash and cash equivalents at beginning of year |  | (8,849) |  | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) |
| Cash and cash equivalents at end of year |  | (16,727) |  | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) |

WSCCO Table 12: Projected statement of cashflows – stormwater

| Statement of cashflows ($000) |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cashflows from operating activities |  |  |  |  |  |  |  |  |  |  |  |
| Cash surplus / (deficit) from operations |  | 1,165 | 1,312 | 1,661 | 986 | 1,014 | 1,114 | 1,369 | 1,671 | 1,856 | 1,872 |
| [other items] |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from operating activities |  | 1,165 | 1,312 | 1,661 | 986 | 1,014 | 1,114 | 1,369 | 1,671 | 1,856 | 1,872 |
| Cashflows from investment activities |  |  |  |  |  |  |  |  |  |  |  |
| [other items] |  |  |  |  | (750) |  |  |  |  |  |  |
| Capital expenditure |  | (1,201) | (3,064) | (4,219) | (2,657) | (2,825) | (3,489) | (4,024) | (4,079) | (3,721) | (3,160) |
| Net cashflows from investment activities |  | (1,201) | (3,064) | (4,219) | (3,407) | (2,825) | (3,489) | (4,024) | (4,079) | (3,721) | (3,160) |
| Cashflows from financing activities |  |  |  |  |  |  |  |  |  |  |  |
| New borrowings |  | 36 | 1,752 | 2,557 | 2,421 | 1,811 | 2,375 | 2,655 | 2,408 | 1,863 | 1,285 |
| Repayment of borrowings |  |  |  |  |  |  |  |  |  |  |  |
| Net cashflows from financing activities |  | 36 | 1,752 | 2,557 | 2,421 | 1,811 | 2,375 | 2,655 | 2,408 | 1,863 | 1,285 |
| Net increase/(decrease) in cash and cash equivalents |  | (0) | (0) | 0 | 0 | 0 | 0 | (1) | (1) | (1) | (2) |
| Cash and cash equivalents at beginning of year |  | 748 | 748 | 747 | 747 | 747 | 747 | 747 | 747 | 746 | 745 |
| Cash and cash equivalents at end of year |  | 748 | 747 | 747 | 747 | 747 | 747 | 747 | 746 | 745 | 743 |

WSCCO Table 13: Projected statement of financial position – water services

| Statement of financial position ($000) |  | FY23/24 |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Assets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash and cash equivalents |  | (15,268) |  | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) | (15,268) |
| Other current assets |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Infrastructure assets |  | 621,550 |  | 655,073 | 707,349 | 762,258 | 823,589 | 877,104 | 915,148 | 959,385 | 993,382 | 1,029,888 | 1,057,914 |
| Other non-current assets |  | 0 |  | 0 | 0 | 0 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 |
| Total assets |  | 606,282 |  | 639,805 | 692,081 | 746,990 | 813,321 | 866,836 | 904,880 | 949,117 | 983,114 | 1,019,620 | 1,047,646 |
| Liabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Borrowings - current portion |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Other current liabilities |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Borrowings - non-current portion |  | 114,435 |  | 139,504 | 174,678 | 209,876 | 258,528 | 289,847 | 304,191 | 316,992 | 322,455 | 324,741 | 324,839 |
| Other non-current liabilities |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total liabilities |  | 114,435 |  | 139,504 | 174,678 | 209,876 | 258,528 | 289,847 | 304,191 | 316,992 | 322,455 | 324,741 | 324,839 |
| Net assets |  | 491,847 |  | 500,301 | 517,403 | 537,114 | 554,793 | 576,988 | 600,690 | 632,125 | 660,659 | 694,879 | 722,807 |
| Equity |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Revaluation reserve |  | 0 |  | 8,561 | 24,780 | 41,545 | 59,230 | 81,426 | 100,840 | 125,256 | 145,395 | 172,469 | 193,692 |
| Other reserves |  | 491,847 |  | 491,740 | 492,623 | 495,569 | 495,563 | 495,562 | 499,849 | 506,869 | 515,264 | 522,411 | 529,115 |
| Total equity |  | 491,847 |  | 500,301 | 517,403 | 537,114 | 554,793 | 576,988 | 600,690 | 632,125 | 660,659 | 694,879 | 722,807 |

WSCCO Table 14: Projected statement of financial position – drinking water

| Statement of financial position ($000) |  | FY23/24 |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Assets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash and cash equivalents |  | 711 |  | 711 | 711 | 712 | 711 | 711 | 711 | 712 | 713 | 714 | 716 |
| Other current assets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure assets |  | 232,318 |  | 255,760 | 283,166 | 308,516 | 335,465 | 356,568 | 372,360 | 394,870 | 407,308 | 425,991 | 436,308 |
| Other non-current assets |  |  |  | 0 | 0 | 0 | 1,982 | 1,982 | 1,982 | 1,982 | 1,982 | 1,982 | 1,982 |
| Total assets |  | 233,029 |  | 256,471 | 283,877 | 309,228 | 338,158 | 359,261 | 375,054 | 397,564 | 410,003 | 428,687 | 439,006 |
| Liabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Borrowings - current portion |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other current liabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Borrowings - non-current portion |  | 33,637 |  | 55,193 | 78,270 | 96,145 | 120,853 | 131,701 | 137,747 | 145,835 | 147,197 | 150,520 | 149,679 |
| Other non-current liabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total liabilities |  | 33,637 |  | 55,193 | 78,270 | 96,145 | 120,853 | 131,701 | 137,747 | 145,835 | 147,197 | 150,520 | 149,679 |
| Net assets |  | 199,392 |  | 201,279 | 205,608 | 213,083 | 217,305 | 227,560 | 237,307 | 251,730 | 262,805 | 278,167 | 289,326 |
| Equity |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Revaluation reserve |  | 0 |  | 3,788 | 8,913 | 16,840 | 22,768 | 32,925 | 39,934 | 50,713 | 58,099 | 70,143 | 77,965 |
| Other reserves |  | 199,392 |  | 197,490 | 196,694 | 196,243 | 194,537 | 194,635 | 197,373 | 201,016 | 204,707 | 208,024 | 211,361 |
| Total equity |  | 199,392 |  | 201,279 | 205,608 | 213,083 | 217,305 | 227,560 | 237,307 | 251,730 | 262,805 | 278,167 | 289,326 |

WSCCO Table 15: Projected statement of financial position – wastewater

| Statement of financial position ($000) |  | FY23/24 |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Assets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash and cash equivalents |  | (16,727) |  | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) | (16,727) |
| Other current assets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure assets |  | 291,804 |  | 300,778 | 321,789 | 346,194 | 377,117 | 405,510 | 423,515 | 440,090 | 456,888 | 469,769 | 483,796 |
| Other non-current assets |  |  |  | 0 | 0 | 0 | 2,268 | 2,268 | 2,268 | 2,268 | 2,268 | 2,268 | 2,268 |
| Total assets |  | 275,077 |  | 284,051 | 305,062 | 329,467 | 362,659 | 391,051 | 409,056 | 425,631 | 442,429 | 455,310 | 469,338 |
| Liabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Borrowings - current portion |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other current liabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Borrowings - non-current portion |  | 79,408 |  | 82,886 | 93,231 | 107,996 | 129,520 | 148,180 | 154,102 | 156,161 | 157,854 | 154,954 | 154,607 |
| Other non-current liabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total liabilities |  | 79,408 |  | 82,886 | 93,231 | 107,996 | 129,520 | 148,180 | 154,102 | 156,161 | 157,854 | 154,954 | 154,607 |
| Net assets |  | 195,669 |  | 201,165 | 211,832 | 221,471 | 233,139 | 242,871 | 254,954 | 269,471 | 284,575 | 300,357 | 314,731 |
| Equity |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Revaluation reserve |  | 0 |  | 3,298 | 12,144 | 18,454 | 27,747 | 36,834 | 46,608 | 57,169 | 67,199 | 78,789 | 89,377 |
| Other reserves |  | 195,669 |  | 197,867 | 199,688 | 203,017 | 205,392 | 206,037 | 208,345 | 212,301 | 217,376 | 221,568 | 225,354 |
| Total equity |  | 195,669 |  | 201,165 | 211,832 | 221,471 | 233,139 | 242,871 | 254,954 | 269,471 | 284,575 | 300,357 | 314,731 |

WSCCO Table 16: Projected statement of financial position – stormwater

| Statement of financial position ($000) |  | FY24/25 | FY25/26 | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | FY31/32 | FY32/33 | FY33/34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Assets |  |  |  |  |  |  |  |  |  |  |  |
| Cash and cash equivalents |  | 748 | 747 | 747 | 747 | 747 | 747 | 747 | 746 | 745 | 743 |
| Other current assets |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure assets |  | 98,535 | 102,394 | 107,548 | 111,007 | 115,026 | 119,273 | 124,424 | 129,187 | 134,128 | 137,810 |
| Other non-current assets |  | 0 | 0 | 0 | 750 | 750 | 750 | 750 | 750 | 750 | 750 |
| Total assets |  | 99,283 | 103,141 | 108,296 | 112,505 | 116,523 | 120,771 | 125,921 | 130,682 | 135,622 | 139,302 |
| Liabilities |  |  |  |  |  |  |  |  |  |  |  |
| Borrowings - current portion |  |  |  |  |  |  |  |  |  |  |  |
| Other current liabilities |  |  |  |  |  |  |  |  |  |  |  |
| Borrowings - non-current portion |  | 1,426 | 3,178 | 5,735 | 8,156 | 9,966 | 12,341 | 14,996 | 17,404 | 19,267 | 20,552 |
| Other non-current liabilities |  |  |  |  |  |  |  |  |  |  |  |
| Total liabilities |  | 1,426 | 3,178 | 5,735 | 8,156 | 9,966 | 12,341 | 14,996 | 17,404 | 19,267 | 20,552 |
| Net assets |  | 97,857 | 99,964 | 102,561 | 104,349 | 106,557 | 108,429 | 110,925 | 113,279 | 116,355 | 118,750 |
| Equity |  |  |  |  |  |  |  |  |  |  |  |
| Revaluation reserve |  | 1,475 | 3,723 | 6,251 | 8,715 | 11,667 | 14,298 | 17,374 | 20,097 | 23,536 | 26,349 |
| Other reserves |  | 96,383 | 96,241 | 96,309 | 95,634 | 94,890 | 94,131 | 93,551 | 93,182 | 92,819 | 92,400 |
| Total equity |  | 97,857 | 99,964 | 102,561 | 104,349 | 106,557 | 108,429 | 110,925 | 113,279 | 116,355 | 118,750 |

# Appendix 1: Commitment Agreement

# Appendix 2: Modelling assumptions

In the development of the WSDP and supporting financials, the Council used 2024/34 LTPs and 2025/26 Annual Plans as the base dataset, with some key adjustments and assumptions to reflect the proposed shift to a WSCCO including operating costs, efficiencies and the cost of borrowing. Additional allowances were also made to reflect the costs associated with Local Water Done Well. These assumptions are as follows:

| Assumption | Commentary | Basis of assumption / source |
| --- | --- | --- |
| Financing | LGFA has indicated that for multi-council WSOs the borrowing margin would be based on the weighted average borrowing margin of the participating councils. LGFA 10-year bond rate for unrated councils + 5bps (6%) | LGFA |
| Target covenant | LGFA guidance indicates that the WSO would have FFO-to-debt floor of 9%. The model targets 10% FFO-to-debt. | LGFA |
| Governance and incremental costs | Additional opex associated with a WSO include additional management costs, board fees, audit and other costs. These are assumed at approx.. $1.5m p.a. |  |
| Establishment costs (one-off) | There are a series of capital costs associated with establishing an entity (fit out, staff IT equipment/networks etc.). Councils have provided an assumption of $5 million, split equally between Councils. | Note: It is assumed that operating costs associated with establishment will be debt funded. |
| Levies | Commerce Commission and Taumata Arowai levies will be built into the base case. | Commerce Commission and Taumata Arowai + population statistics |
| Operating efficiencies | Operating efficiencies are driven by a number of factors, including productivity gains arising from effective management practices, purchasing power, and more streamlined operations and maintenance. Efficiencies are modelled to being two years after the entity’s establishment (FY30) and ramp to 0.35% p.a. (the midpoint of the efficiency range) until peak operating efficiency is achieved at FY44. | Martin Jenkins case study research |
| Capital efficiencies | Capital efficiencies reflect reductions in real unit costs from prudent investment decisions, streamlined cost structures, and market power from a larger entity having long-term investment policies. They are modelled to begin two years after the entity’s establishment (FY3) and ramp to 0.4% p.a. (the midpoint of the efficiency range) until peak capital efficiency is achieved in FY44. | Martin Jenkins case study research |
| Price harmonisation | No price harmonisation* | Agreed by Councils |
| Establishment date | Joint WSO is operational from 1 July 2027. | Agreed by Councils |
| Three waters | Water supply, wastewater and stormwater transferred to the entity. | Agreed by Councils |

* Determining a non-harmonised price path.

- The model takes the initial debt, revenues, and expenditures for each constituent council, effectively ringfencing borrowing, revenues, and expenditures.

- Establishment costs and ongoing incremental costs are allocated back to each council using the agreed basis for apportionment. E.G. If the costs are $5 million, and Council A’s apportionment is 20%, then $1 million is allocated to Council A.

- Entity level efficiency assumptions are applied each individual council’s forecast opex and capex projections.

- In summary, the net cashflow impact of the establishment and incremental costs are allocated back to each council’s starting operating and debt positions. The price path for each council is then recalculated by solving, at the council level, for the revenues required to maintain the FFO-to-debt ratio at 10%. 
Note, this calculation is performed for each council, resulting in varying revenue per connection at council level.

This approach has the effect of sharing the net benefits of efficiency savings with each district, by lowering prices relative to their standalone price path, but does not result in cost sharing between districts.

# Appendix 3: MDC 20 August 2025 Council resolution

Resolution  2025/98

Moved by Mayor G Caffell

Seconded by Councillor B Johnson

That Council:

- ​Receives the Local Water Done Well - Water Services Delivery Plan report.

- ​Adopts the Water Services Delivery Plan for Masterton District Council including Commitment Agreement (Attachment 1) as part of a Wairarapa Tararua Water Services Council Controlled Organisation.

- ​Notes the Water Services Delivery Plan will be submitted to the Secretary for Local Government via the Department of Internal Affairs by 3 September 2025.

- ​Approves $1.25m of unbudgeted expenditure to meet Masterton District Council’s share of the Wairarapa Tararua Water Services Council Controlled Organisation establishment costs as set out in the Commitment Agreement.

- ​Notes the unbudgeted expenditure will be funded by borrowing and then transferred to the Wairarapa Tararua Water Services Council Controlled Organisation at go live (no later than 30 June 2027) as part of the Council’s transfer of water-related debt.

- Delegates authority to the Chief Executive to update the WSDP prior to certification to reflect feedback from the Department of Internal Affairs on matters of consistency and detail which do not alter the Council’s intent as reflected in the attached WSDP.

- ​Delegates to the Chief Executive the preparation of the Water Services Council Controlled Organisation Constitution and Shareholders’ Agreement in line with the commercial agreements appended to the Commitment Agreement.

- ​Notes that final form versions of the Constitution and Shareholders' Agreement will be brought back to the Council for approval in September 2025.​

In Favour:       Mayor Gary Caffell, Councillor Bex Johnson, Councillor Craig Bowyer, Councillor David Holmes, Councillor Stella Lennox, Councillor Marama Tuuta

Against:           Councillor Brent Goodwin, Councillor Tom Hullena, Councillor Tim Nelson

CARRIED 6/3

# Appendix 4: Capital programme assurance report

Greytown Wastewater Treatment Plant connections   - SWDC and Martinborough Wastewater Treatment Plant Connections - SWDC

SWDC-2025-34-Long-Term-Plan-Final2.pdf